# 2022-23 PAKISTAN Development Program Progress ReportING

## Progress against COVID-19 development Response plan results indicators

### Health Security

| **Key Results Indicators** | **Progress/Result** |
| --- | --- |
| Number of medical products to which Australia has contributed that are available in Pakistan:  Personal protective equipment (PPE) and ventilators procured and distributed (227,620 PPE, 31 ventilators) | No data available. The supporting investment - Asian Development Bank managed COVID-19 response project - ended in May 2022. |
| Number of contraceptive protections from unplanned pregnancies made available through Australian support (target: Couple Year Protection (CYP) 3,500 in 2020-21) | 595,539 CYP were generated in FY 2022-23. This included 472,782 contraceptive protection methods from unplanned pregnancies made available by Rahnuma-Family Planning Association of Pakistan (R-FPAP), 116,065 CYP generated by Marie Stopes Society (MSS) and 6,692 provided by the United Nations Population Fund (UNFPA). |
| Number of safe deliveries attended by a skilled birth attendant (target: 9,000 in 2020-21) | 25,563 deliveries were attended by a skilled birth attendant in the reporting period. This included: 15,193 deliveries by UNFPA and 10,370 through R-FPAP. |
| Number of unplanned pregnancies and unsafe abortions averted through the Australian support[[1]](#footnote-2) | 68,390 unplanned pregnancies and 35,402 unsafe abortions averted through Australian supported sexual and reproductive health (SRH) programs in 2022-23. This included 56,599 unplanned pregnancies and 28, 355 unsafe abortions averted by R-FPAP; and 11,791 unplanned pregnancies and 7,047 unsafe abortions averted by MSS. |
| Number of vulnerable people reached with emergency assistance in conflict and crisis situations (target: 146,370 men, 140,630 women in 2020-21) | In response to the 2022 Pakistan floods, the Australian contribution benefitted 277, 267 (including approximately 125,000 women and girls) flood-affected food-insecure people across Pakistan through the provision of 4,367 metric tons of in-kind mixed food commodities through the World Food Program (WFP). |
| Number of women and children reached with nutrition assistance[[2]](#footnote-3) | 53,294 children (6-59 months old) and 82,305 women and girls were reached with nutrition assistance through the United Nations Children's Fund. This included screening of children, provision of micronutrient and iron and folic acid supplements and counselling of mothers on infant and young child feeding practices. |
| Health system and preparedness: number of partner countries where Australia has contributed to strengthened health systems including preparedness for health emergencies with examples[[3]](#footnote-4) | In addition to the continuation of the SRH services to the Afghan refugees, UNFPA responded to 2022 flood humanitarian emergency and contributed to the development of the Pakistan Floods 2022: Resilient Recovery, Rehabilitation, and Reconstruction Framework and the Regional Refugee Response Plan. |
| The Water for Women Fund assisted communities transition their villages to Open Defecation Free sites | No data available. No relevant targets were specified for the reporting year under the supporting investment, Water for Women Fund. |

### Stability

| **Key Results Indicators** | **Progress/Result** |
| --- | --- |
| Improved urban water resource governance in two communities | Technical assistance as part of the Australia Pakistan Water Security Initiative (APWSI) has established governance and oversight structures involving key stakeholders to support the Water and Sanitation Agency of the Government of Punjab urban flood management in Lahore. |
| By 2025, four disadvantaged communities in South Asian cities have transitioned towards water sensitive cities[[4]](#footnote-5) | The APWSI has contributed to making disadvantaged communities in two urban informal settlements (Farash and James Towns) more water sensitive through constructing structures, such as rain gardens, rainwater harvesting and installation of filtration units. |
| Number of women and girls' survivors of gender-based violence (GBV) received services (target: 5,587 in 2020-21) | 69,277 women and girl survivors of GBV received services in 2022-23. This included: 36, 358 from R-FPAP, 31, 678 from UNFPA and 1,241 from MSS supported projects. These services comprised health and psycho-social support and referral for follow-on support. |
| Number of additional girls and boys enrolled in schools (M/F)[[5]](#footnote-6) | No data available - supporting investment Khyber Pakhtunkhwa Education Sector Program ended in June 2021. |
| Policy and technical advice to improve governance and enhance social protection | The World Bank’s Multi-Donor Trust Fund (MDTF) supported the enactment of the Public Finance Management Law in Khyber Pakhtunkhwa, improved the efficiency of the Public Sector Development Program in Balochistan and facilitated the geo-tagging of public infrastructure in the Newly Merged Districts and Balochistan. |
| Number of children in disadvantaged districts supported with inclusive distance learning as part of response and recovery from COVID-19 crisis (target: 27,700 by December 2021) | No data available from the supporting investment Global Partnership for Education (GPE), owing to the low utilisation of GPE grants in Pakistan. |
| Number of people reached by digitised violence against women (VAW) messaging (target: 50,000 in 2020-21) | No data available - supporting investment Oxfam Curbing violence against women and girls (VAWG) through arts and entertainment ended in February 2021. |
| Number of people reached with VAW video content through social and electronic media (target: 10,000,000 in 2020-21) | No data available - supporting investment Oxfam Curbing VAWG through arts and entertainment ended in February 2021. |
| Social protection measures: numbers reached with new or improved social protection programs, including remote communities (M/F)[[6]](#footnote-7) | No data available for 2022-23 from the contributing program (WFP humanitarian assistance to Afghan refugees and host communities). |
| Food security: countries where Australia has supported in the last 12 months with policy and technical advice and support on building capacity for food security (including examples of assistance provided and results achieved)[[7]](#footnote-8) | No data available for reporting in 2022-23. The supporting investment - the – Pakistan Humanitarian Support program - ended on 30 June 2022 |

### Economic Recovery

| **Key Results Indicators** | **Progress/Result** |
| --- | --- |
| Number of female entrepreneurs provided with financial and / or business development services (target: 11,921 to June 2021) | Australia's assistance to the WB MDTF in Border Areas through the Balochistan Livelihood and Enterprise Project assisted 1,008 women in establishing micro businesses, securing their livelihoods in 2022-23. |
| Number of poor women and men with increased incomes (Target: 40,317 women and 55,329 men to June 2022) | No data available - supporting investment Market Development Facility (MDF) Phase II ended in June 2020. |
| Value of Additional Market Transactions because of adoption of demonstrated models and innovations (Target: USD 31,295,000 to June 2022) | No data available - supporting investment MDF Phase II ended in June 2020. |
| Policy and technical advice provided to improve economic recovery | Australia’s funding through MDTF supported the Balochistan and Khyber Pakhtunkhwa Revenue Authorities with the implementation of improved revenue collection measures through sales tax on services. |

### Investment Performance ratings

| **Investment Details** | **Year** | **Effectiveness** | **Efficiency** | **Gender Equality** |
| --- | --- | --- | --- | --- |
| **World Bank Multi Donor Trust Fund for Border Areas** | 2023 | 4 | 4 | 3 |
| Investment duration: 2012-22; Budget: $46.7m | 2022 | 4 | 3 | 3 |

### Final Investment Performance ratings

| **Investment Details** | **Year** | **Effectiveness** | **Efficiency** | **Gender Equality** |
| --- | --- | --- | --- | --- |
| **Disaster Risk Reduction (NDRMF)** | 2023 FIMR | 4 | 3 | 3 |
| Investment duration: 2014-22; Budget: $10.5m | 2022 IMR | 4 | 3 | 3 |
| **Khyber Pakhtunkhwa Education Sector Program** | 2023 FIMR | 4 | 3 | 4 |
| Investment duration: 2012-21; Budget: $57.45m | 2022 IMR | 4 | 4 | 4 |

### Humanitarian Investment Performance ratings

| **Investment Details** | **Year** | **Effectiveness** | **Efficiency** | **Gender Equality** |
| --- | --- | --- | --- | --- |
| **Pakistan Floods Humanitarian Assistance 2022** | 2023 HIMR | 5 | 5 | 4 |
| Investment duration: 2022-23; Budget: $5m | 2022 HIMR | N/A | N/A | N/A |

1. This indicator was added in the Pakistan CDRP Progress Report for 2022 [↑](#footnote-ref-2)
2. This indicator was added in the Pakistan CDRP Progress Report for 2022-23 [↑](#footnote-ref-3)
3. This indicator was added in the Pakistan CDRP Progress Report for 2020-21 [↑](#footnote-ref-4)
4. This indicator was added in the Pakistan CDRP Progress Report for 2022-23 [↑](#footnote-ref-5)
5. This indicator was added in the Pakistan CDRP Progress Report for 2020-21. [↑](#footnote-ref-6)
6. This indicator was added in the Pakistan CDRP Progress Report for 2020-21. [↑](#footnote-ref-7)
7. This indicator was added in the Pakistan CDRP Progress Report for 2020-21. [↑](#footnote-ref-8)