|  |  |  | AusAID |
| --- | --- | --- | --- |
| Enterprise Challenge Fund – Mid-Term Review |  |  |  |
| Annex 2: Evaluation Plan |  |  |  |
| David Elliott |  |  |  |
| November 2009 |  |  |  |
|  |  | Suite One, 4 Saddler Street Durham DH1 3NP United Kingdom Tel: +44 191 383 1212 Fax: +44 191 383 1616 Email: global@ springfieldcentre.com |  |

Springfield Centre

Suite One

4 Saddler Street

Durham  DH1 3NP

United Kingdom

Tel: + 44 191 3831212

Fax: +44 191 3831616

global@springfieldcentre.com

springfieldcentre.com

To:	Tammy Malone

From:	David Elliott

Cc:	Alwyn Chilver, Rebecca Bryant, Bronwyn Wiseman

Date:	7/29/26

Re:	ECF Evaluation

# Purpose of note

The Springfield Centre has been approached by AusAID to lead the mid-term review of their Enterprise Challenge Fund.  Discussions on the Terms of Reference (ToR) are well advanced.  This note serves as a draft evaluation plan and is reflective of discussions and agreements made to date.  It is neither definitive nor exhaustive.  It may well need to be refined as follows:

- As the team gets into detailed background project reading;

- In light of logistical implications emerging from an agreement of priority stakeholder visits; and/or

- Any final revisions of the ToR and / or comments from AusAID.

But, for now, the note outlines our general approach and considerations for the evaluation task.  It is structured as follows:

- Comments on the general nature of the task

- Evaluation Method

- Evaluation Approach

- Team Composition and Roles

- Indicative Work Plan

# Comments on the general nature of the task

As agreed, the task is to conduct a rigorous and independent assessment of performance of the ECF.  The review will be constructive and forward looking in terms of its recommendations and proposed next steps.  This will set a clear platform for any concept development task should the findings be generally positive and supportive to the idea of a new phase of support to the ECF.

This note concentrates solely on the evaluation of the ECF.  Any discussions of a concept development task should be subject to the findings of the evaluation and conducted in detail at this time.

The ECF comprises a portfolio of projects contributing to rather broad developmental objectives.  It arguably presents a laboratory of experiences.  This presents challenges to any evaluation team.  The evaluation cannot visit and review each and every project.  On the other hand, with such a diverse portfolio, technically, and geographically, it is not always clear that the lessons from one project are reflective more generally across the portfolio.  These risks will be mitigated through the following measures:

- Reviewing the documents for all projects to get a general overview of the context;

- Choosing projects to be visited which are reflective of the types of business linkage / partnership pursued across other projects in the portfolio;

- Visiting a mixture of larger and smaller projects;

- Visiting projects in different country contexts; and

- Balancing these specific review findings with broader consultation to triangulate in on key themes and issues which do hold generally across the whole portfolio.

Such issues are reflected in our Evaluation Approach outlined below.

In a similar vein, the diversity of the portfolio presents challenges to any evaluation team to demonstrate a sufficient breadth of expertise and experience.  The appointed review team do well in this regard, however, it is open to the possibility that it might need to refer to more specialist sources of advice and input.  For example, if a project concerns a particular technology, it might be important to seek a specialist view on how well that technology has been adapted in similar settings, and hence be better able to form an opinion on the degree of good practice and innovation being applied in the ECF funded project.

As a multi-country Fund, the ECF would need to be complimentary and additional to AusAID Country Strategies and operations on the ground in each country where the ECF is active.  However, the competitive “demand driven” nature of challenge funds means that they can be difficult to “programme” into existing country operations.  The review will need to be sensitive to the relationships between centrally funded instruments, such as the ECF, and mission driven programmes in country.

# Evaluation Method

The evaluation method is well defined by AusAID, both in the ToR, and in the Annex to the ToR entitled Attachment E – Independent Progress Report.  We are happy to subscribe to this general evaluation method, but add some comments as follows:

Relevance

We will be considering this at two levels: Firstly, its relevance generally as an effective development instrument.  In especial, this refers to questions of rationale and questions of strategy (i.e. does the funding of a host of different and disparate projects sum up to more than its individual parts).  Secondly, we will need to consider its relevance as an instrument within the scope of intervention options open to AusAID.

Effectiveness

In log frame terms, this refers generally to the extent to which outputs are on track / have been achieved.  From other challenge funds that the review team have been involved with, there is a tendency for a disconnect between the Programme Log Frame (i.e. that for the ECF itself), and Project log frames (i.e. for the funded projects).  Either the latter does not exist, or if it does, it is rarely “nested” within the main Programme log frame.  In effect this means a break in the “logic” from project activities, to programme outputs, to programme impacts.  The challenge for the review team will be to look at both the systems being used for output and objective setting at programme and project levels, as well as to the actual performance against targets.

Efficiency

Generally this will look at issues of cost-effectiveness, timeliness, and organisational performance.  However, we believe that it is possible to make some comparison with certain indicators of performance from other challenge funds (albeit with clearly spelled out caveats).  For example, we could cross compare marketing strategies and costs, with concept notes generated; and/or, we could compare management costs as a proportion of overall funds.  To some extent this depends on being sure just what comparative information we can get from other challenge funds.  This will be a pre-mission task (see below for more detail).  Further, we will need to review closely the efficiency (and effectiveness) of the decision making and governance processes and structures.

Impact (M&E):

We understand that the oversight of the “evaluation” function has been contracted out to a third party (Triple Line).  Whilst the review team will not be completing and impact assessments per se as part of the evaluation, this is a critical area for the review to focus on.  We will need to look at systems, and at how those systems are being used in practice.  From our field visits we should also aim to check and confirm that the review team findings are consistent with those emerging from the M&E processes in place.  In other words, our focus is more on appraisal and validation, rather than impact assessment per se.  As such, and as discussed in the context of the ToR, we might be able to comment on cost-benefit issues, but will not be responsible for calculating cost-benefit equations for projects visited.

Cross-Cutting themes: gender / PACER

The team will be sensitive to the two explicit cross-cutting issues of gender mainstreaming, and as regards the relevance of ECF to the new PACER objectives.  We do not propose however to conduct specific and detailed gender audits or assessments.

# Evaluation Approach

As referred to above, the ECF is a portfolio of different and diffuse projects.  The review team will need to drill down into selected projects to determine performance at a project level.  It will also need to look for performance issues and lessons at a wider portfolio level.  Achieving this requires a multi-faceted approach to the evaluation.  At the project level we will need to review documents, engage with the fund management team, and make field visits to selected projects.  We will need to go beyond this at the programme level.  This will require consultation and engagement with AusAID HQ and Missions, wider stakeholders in the process, and with comparable challenge funds elsewhere in the world.  Taking this is turn our approach will involve:

- Document Review – the team will require full disclosure of all relevant project documentation at least 2-3 weeks prior to the field work.  This is not seen as a background exercise.  Rather it is a critical factor in confirming all of the main aspects of the proposal evaluation approach.  We would expect to update and finalise this draft evaluation plan in light of this review.

- Preliminary Discussions – emerging from the document review will be a number of issues of importance and about which we might well need to discuss across the evaluation team, with AusAID, and with the Fund Managers.

- Finalisation of Field Work and Logistics – emerging from these discussions we will be able to finalise logistics and work planning arrangements.  Given the nature of the task, such arrangements will be relatively complex.  They require good planning and arranging prior to any visit, and they will require active support whilst on the ground.  It is not clear whether the Fund Managers or AusAID will be responsible for such support.

- Consultation with Stakeholders - prior to the field visits, we would want to have engaged with a number of stakeholders.  In particular, we will want to have sought written (ideally) inputs from AusAID mission staff as to their opinions as to how, and how well, the ECF compliments (or not) their in-country operations.  We will also need to engage with other challenge funds to determine what data we can get which might be useable as some form of benchmark against which to measure ECF’s performance.

- Briefing with AusAID – as a first task, we’d expect to have a briefing in Canberra with the main AusAID officers involved with the ECF.  We’d suggest also that the Fund Manager (based in Sydney) joins us for this briefing.

- Engagement with Fund Managers – we understand that the main fund management team are based in Adelaide.  We feel it important that we see / talk to them in their own environment.  We will want to see for ourselves the level of organisation and management systems actually in place.

- Project Field Visits – we have had various exchanges with AusAID on this issue.  Our current thinking is that the full team travel together to Vanuatu, where three projects are being funded.  This will allow us to test a) our evaluation approach, and b) our respective roles on the team.  From here we’d propose a split with one team going to Laos (and possibly Cambodia if connections are efficient), and the other to Fiji.  The rationale here is that both Laos and Fiji boast two projects each.  This means we will have visited around two-thirds of all projects currently funded.  Whilst higher than typical in such reviews, it seems possible and manageable and would therefore be preferable.

- Triangulation with wider stakeholders – coming out of the field work we will be generating emerging issues and lessons.  We would want to structure our discussions with wider stakeholders around these issues and lessons.  We believe such focused engagement is preferable and more effective than a more general “cold-call” box-ticking approach to consultation.

- Debriefing with AusAID and the Fund Managers – the team will need to re-gather from the field work in Canberra.  We would need two days to review, discuss and agree on the main evaluation messages. We’d also need to agree respective report writing roles, and timing thereof.  We would also need to organise and deliver a debriefing session with AusAID (and we’d suggest, with the Fund Manager).

- Report Writing – as team leader, David Elliott would assume the overall responsibility for report writing.  However, he will require contributions and inputs from his team colleagues.  This does slightly extend the elapsed time to get a draft final report submitted to AusAID.  However, we’d expect the team members to have submitted their inputs to the team leader within one week of the mission, and he to complete the draft final report within the next week.

# Team Composition and Roles

As discussed with AusAID, the evaluation team will comprise three persons, two of which are being contracted through The Springfield Centre.  These include:

- David Elliott (Team Leader) – responsible for the overall conduct of the evaluation and for the final report.  Technically, David will focus on wider rationale, relevance and effectiveness questions.  He will visit Vanuatu and Laos (plus Cambodia if logistically convenient).

- Sarah Barlow (Consultant) - contributing generally across the review process, but specifically responsible for the component related to efficiency.  This plays to Sarah’s strengths as a former manager of the BEST-AC (business advocacy) challenge fund in Tanzania, and recent lead reviewed of the “sister” BUSAC challenge fund in Ghana.

- To be confirmed (Consultant) - ideally we would this consultant to have a) technical expertise in M&E within private sector development type projects, and b) direct AusAID understanding and experience.  Technically, we’d see this role as slightly more narrow in focus than either David’s or Sarah’s.  This person should review and comment on the M&E systems in place, and their role in the field work would be focused on checking and testing (validating) M&E findings on the ground.  Procedurally, we’d hope that this person could guide the other team members, as appropriate, in wider AusAID processes and procedures.

# Schedule

This schedule is entirely tentative and is intended to indicate the main stages in the review period.

| Date | Task | Location | Involved |
| --- | --- | --- | --- |
| August | Document Review | Home base | DE, SB, ANO |
| Sept 1-8 | Preliminary Discussions / Stakeholder Consultation | Home base | DE, SB, ANO AusAID HQ Fund Manager Other CF Managers AusAID Mission Staff |
| Sept 11-12 | Departure for Canberra | Canberra |  |
| Sept 14 | Briefing with AusAID | Canberra | DE, SB, ANO AusAID HQ Fund Manager |
| Sept 15 | Engagement with Fund Managers | Adelaide | DE, SB, ANO Fund Managers |
| Sept 17-21 | Project Visits | Vanuatu | DE, SB, ANO AusAID Mission staff Projects Key local informants |
| Sept 22-26 | Project Visits | Fiji Laos (Cambodia?) | SB, ANO DE AusAID Mission staff Projects Key local informants |
| Sept 27-28 | Team Debriefing | Canberra | DE, SB, ANO |
| Sept 29 | AusAID Debriefing | Canberra | DE, SB, ANO AusAID HQ Fund Manager |
| Sept 30 | Departure | Home base | DE, SB, ANO |
| Oct 9 | Deadline for team inputs | Home base | SB, ANO |
| Oct 16 | Deadline for Draft Final Report | Home base | DE |

We’d expect to speak directly with Hugh Scott from AECF and Jack Newnham, former manager of the BLCF.  We’d also expect to use written review sources from various challenge funds (BEST-AC, BUSAC and FDCF) as supplementary information.