|  |  |  | AusAID |
| --- | --- | --- | --- |
| Enterprise Challenge Fund – Mid-Term Review |  |  |  |
| Annex 3: Effectiveness – project evaluation framework and aide memoires |  |  |  |
| David Elliott |  |  |  |
| November 2009 |  |  |  |
|  |  | Suite One, 4 Saddler Street Durham DH1 3NP United Kingdom Tel: +44 191 383 1212 Fax: +44 191 383 1616 Email: global@ springfieldcentre.com |  |

Springfield Centre

Suite One

4 Saddler Street

Durham  DH1 3NP

United Kingdom

Tel: + 44 191 3831212

Fax: +44 191 3831616

global@springfieldcentre.com

springfieldcentre.com

To:	Tammy Malone, Alwyn Chilver, Bronwyn Wiseman

From:	David Elliott

Cc:

Date:	7/30/26

Re:	ECF Evaluation – draft evaluation framework (Output to Purpose Level)

# Dear Colleagues,

As required by AusAID, the review team has produced aide memoires for each of the projects visited in the recent fieldwork for the ECF Review.  These aide memoires are attached.  They are written against a framework, which was agreed prior to the review, and which is restated below for reference.  The synthesis of findings, conclusions and recommendations falling from the fieldwork will be presented in the main review report.  Hence, we simply offer here the framework, and the aide memoires in full format.

Project Evaluation Framework

At its core the ECF is concerned with funding economically viable projects that deliver clear benefits to the poor and which would not have happened without the ECF intervention.  Servicing the poor, whether as producers or consumers, demands changing perceptions and practices of corporate business.  Such change requires innovation, and it is this innovation which brings with it a risk profile beyond which commercial financiers (including corporate businesses themselves) are prepared to invest.  Innovation, as defined, refers in the main to the introduction of new business processes, practices or partnerships which overcome various dimensions of market system weakness.

So, the ECF wishes to fund commercially viable projects, which deliver clear pro-poor benefits, but which are innovative, transformational and which contribute to wider systemic change.  This is confirmed / reinforced in the ECF objectives restated below as:

- Poverty reduction – increased number of poor and disadvantaged men and women with jobs, income, goods and services provided by commercially sustainable businesses.

- Raise awareness broadly across the private sector in the Pacific and poorer parts of Asia of profit making opportunities in poor markets.

- Catalyse more commercial investment in poor markets.

- Help bring about sustainable change in corporate behaviour – an increased proportion of private sector resources get allocated to pro-poor business for commercial reasons.

- Improve conditions for profitable business in poor markets – in terms of more enabling rules and regulations, enhanced b-2-b services, improved infrastructure etc.

- Add value to PSD activities in the region, leveraging the efforts of businesses to help advance broader improvements in the enabling environment.

Clearly, the ECF is committed to systemic change objectives.  This is the route to sustainable poverty reduction at scale.  It is seeking to fund innovations which overcome various dimensions of systemic weakness.  Presently these innovations carry a risk profile which is beyond that at which full commercial investment is available.  ECF projects should therefore be demonstrative, in the sense of reducing the risk profile to investors.  Additionally, ECF projects should encourage an increase in risk appetites, leading to higher levels of replication and crowding in of pro-poor private investment.

Having reaffirmed the rationale, objectives and motivations of the ECF design, we now need to translate this into a practical framework for the evaluation as follows:

Commercial viability

ECF projects should be commercially viable.  This means that net positive benefits (returns) continue to be realised beyond the duration of the project.  The assessment should consider commercial risks and assumptions made at award stage, and review progress against these in the review.

Scope and scale of anticipated poverty impact

ECF projects should generate net positive financial and economic benefits for the poor.  How are the poor defined as a target group?  How will they benefit, and to what extent?  Compare and contrast projected figures with observed realities.

Systemic Change

Projects should contribute to wider systemic change.  We need to be clear what we mean by this.  Figure 1 presents a basic framework for understanding the market system around business and has several characteristics:

- The ‘core’ function in any market system is to provide – a commodity, product, service etc. Businesses are the key providers in markets in a transactional relationship with users/consumers.

- Activities in the core of the market, however, are shaped by/are a product of the environment (or the system) around it. How businesses behave here and in particular their ability to grow and change in response to new consumer needs depends critically on this environment – this wider system - around them.

- This environment can be seen as comprising other supporting functions and rules , including:

  - Information: this is a broad category and can take several forms – for instance, news of business trends transferred via word-of-mouth in networks, media exposure, specialised technical papers or formal research studies. In competitive and concentrated markets, where there is transfer of personnel between companies, informal information flow is enhanced. Markets in ECF targeted countries, in general, are more information-constrained than elsewhere - a key reason for their comparative inefficiency.

  - Services: in more developed and complex markets, specific services play a key role in improving business performance – say in relation to design and process efficiency. For example, manufacturing firms whose traditional basis for competitive advantage was low prices from low resource (especially labour) costs need to change as their cost advantage becomes eroded.  In order to move into higher value-added modes of operation competing on the basis price and other factors such as quality and reliability, they often need to access productivity-enhancing consulting or technology-based services.  In other spheres, services have a more public character that makes government delivery more appropriate.

- Financial services: financial services are a critical factor in the performance of other ‘systems’.  For example, the willingness and ability of providers to offer new financial products for emerging business ‘models’ (say, new variants of contract farming) impinges on growth and innovation.

- Skills/know-how: this might take the form of formal training/education services related to an innovation, offered by commercial or other providers.

- Regulations and standards: this might include more generic regulations relating to, for example, export/customs procedures or more specific certification standards and arrangements.

- Informal rules: this includes business norms and practices dealing with, for example, product/process development, relationships with small businesses and inter-firm cooperation. In other words, this deals with the wider ‘culture’ of business.

Systemic change means, therefore, change with respect to the above dimensions of the market system around businesses.  Bringing about change here offers the potential of more innovation and more impact, of bringing in other players and stimulating change beyond immediate recipient of grant support.

From an ECF perspective, in some cases, systemic change may result from the initial disruptive stimulus generated by one business innovation - such as M-PESA in Kenya which has stimulated a range of other services.  In strong environments, where incentives and capacities are well-developed, this may be sufficient.  In other cases, especially in weaker markets, wider systemic response may require active facilitation by an external catalyst – for example to generate the right information in the right form among the right networks, allowing others to learn.

Defining system in this way means that, in considering the potential of individual innovations to bring about systemic change, we are considering whether they will stimulate change with respect to, for example:

- Information – on trends and business practices

- Services – formal services aimed directly at businesses

- Financial services – availability and form of finance

- Skills/know-how – mechanisms or services aimed directly at skills

- Regulations and standards – related to products or processes

- Informal rules – business norms and culture.

Logically, innovations that don’t result in the kinds of changes highlighted above will not stimulate systemic change.

Level and Type of Innovation

For projects to be systemic, they have to be innovative (potential to be transformational).  It is this innovation which carries the risk element to which ECF funding is being targeted.  We need to define what we mean by innovation.  For ‘innovation’ to make sense, it is necessary to define two related dimensions.  First, the boundaries within which we are viewing ‘innovation’; i.e. is the innovation new for the company, the region, the operational conditions faced or the field/sector as a whole?  In doing so, we are also considering the nature of change (process, product etc) envisaged.  This is reflected the following figure:

Second, and related, we need to determine what the main motivations are for innovation; i.e. is it prompted by a sense of corporate social responsibility and development goals or primarily by a business desire for growth.  These questions don’t lend themselves to neat, clearly delineated answers – motivations are often mixed, boundaries of innovation unclear.  Nonetheless, they are important to consider in assessing the underlying potential for systemic change.  Generally, innovations that are new to the field as a whole and stimulated by business goals are more likely to have potential for systemic change.  Conversely, innovations with narrower boundaries and more socially-driven, are likely to have limited potential for generating wider change.  This is shown below as:

Defining system in this way means that, in considering the potential of individual innovations to bring about systemic change, we are considering whether they will stimulate change with respect to information, services, regulations, business norms etc.  Logically, innovations that don’t result in these kinds of changes will not stimulate systemic change.

Demonstration Effect

Is it clear what is being demonstrated, and to whom (stakeholders) it is being demonstrated.  For example, in the case of infrastructure (say, financing a boat which opens access to underserved populations) which has a wider economic impact on citizens, to what extent is learning being fed back to inform future Government public investment programmes?

Replication

Are their signs of replication happening spontaneously – within / across the lead firm, and/or from competitors / peers?  We are looking here at copycatting / spin off innovation.  Has there been a wider industry response – changed perceptions, practices, investment performance?

If change is unlikely to occur by itself, what actions are or might be taken? And by whom?  In particular, we are exploring here the extent to which ECF or other development players are / can take action to bring about change to build on the potential for change.

Framework Questions Template

The evaluation framework comprises the following dimensions:

•	Commercial viability

•	Scope and scale of anticipated poverty impact

•	Systemic change

•	Level and type of innovation

•	Demonstration effect

•	Replication potential

The definitions and background to the terms used above are given in the memo to this exercise.  Below we build on this and present a number of key questions that serve to frame and focus the project evaluations.  These questions merely offer guidance.  They are not definitive.

Commercial Viability

This is not particularly concerned with reviewing the financial forecasts and reinterpreting the work of the assessment panels (unless there is some glaring inaccuracy).  Rather, we are assessing more the following types of issues:

- Are there early signs of commercial progress (new contracts, increasing sales etc)…?

- If so, are these in line / in order with application forecasts…?

- The applications make a number of assumptions underpinning commercial forecasts.  Are there any signs that these assumptions were well founded, or not…?

Scope and scale of anticipated poverty impact

This assessment has clear links to the monitoring and evaluation frameworks for each project.  Key questions might include:

- Are the target beneficiaries clearly identified…?

- Is it clear how the poor are considered as partners in the process / how formally are beneficiaries included in the process / business model…?

- To what extent do projects invest in supplier linkages / moving to more relationship based arrangements (as opposed to undefined spot buying)…?

- Are income profiles of the poor clear now, so that additional impact attributable to the project can be measured…?

- Has the anticipated flow of benefits to the target group been sufficiently quantified…?

- Is the monitoring and evaluation framework for each project sufficient for capturing pro-poor impacts of projects…?

Systemic Change

The economic rationale for grants to private business is centred on market failure arguments.  Market failure, it is argued, is endemic in many areas critical to private sector growth in developing countries.  Externalities exist whereby the benefits of certain investments often spill over to others (copycatting) which have not invested, but nevertheless benefit in terms of learning about the results.  Because of such information externalities the socio-economic benefits of technology transfer investments are greater than the returns to any individual firm that undertakes them.  As a result the private sector can invest too little in technology transfer relative to what is socially optimal for sustained long term growth.  The definition of this is given in the memo.  Some key questions include:

- If supply chain investments are good for buyers and sellers then why exactly are they not making them already…?

- Has the exact cause of market failure (real or perceived) been understood by the applicant / application…?

Level and type of innovation

Key issues might include:

- Does the application represent new ways of working for the company…?

- Does the application represent a new way of working in the sector within the country…?

- Does the application represent the application of an existing practice in a new country…?

- Does the application represent a genuinely new innovation for the sector / field as a whole regionally / internationally…?

- What are the primary motivations behind the innovation (socially or commercially motivated)…?

Demonstration effect

Key issues might include:

- Is it clear exactly what is being demonstrated (in terms of overcoming identified market failures)…?

- Is it clear to whom this demonstration effect is / should be targeted to (e.g. government, competitors, private sector more broadly, banks, donors)…?

- Are there credible plans in place for ensuring that lessons are learned by those who need to learn them…?

Replication potential

Key issues might include:

- Are their signs of replication happening spontaneously – within / across the lead firm, and/or from competitors / peers?  We are looking here at copycatting / spin off innovation.

- Has there been a wider industry response – changed perceptions, practices, investment performance?

de

Aide Memoire

Future Forests Fiji Ltd

Overview of the Project

Future Forests Fiji Ltd (FFF) is a teak plantation, founded in 2004 by three partners.  The original idea behind the company was to plant teak trees on deforested, uncultivated grass lands.  Since 2004, FFF has developed and established its plantations in Ra Province in Viti Levu, Fiji’s main island.  At the time of first applying for the ECF grant, FFF owned almost 100 hectares of freehold land on which it had planted teak trees.  At the time of the review team visit (September 2009) it had added an additional 100 hectares of leasehold land to the company’s assets and is steadily planting this land with teak trees.

FFF’s approach to developing its plantation is to collect teak seeds locally, germinate the seeds themselves, grow seedlings from them and then plant the seedlings.  It has developed two business models around this practice:

- The first applies to FFF’s own land, both freehold and leasehold, on which it plants the teak seedlings it has germinated from seeds.  This generates employment for local villagers, and FFF intentionally works to ensure that the skills involved in this process, from germination to maintaining the trees, are acquired by these employees, many of whom are land owners in their own right.

- The second applies to FFF’s plans to develop several village nurseries for germinating seeds for local landlords to use on their underutilised land.  This will enable local landlords to germinate their own seeds for planting.  FFF will provide technical assistance and advice to the farmers and will offer a guaranteed market for the teak when it is time to harvest (although the farmers will not be obliged to sell their teak to FFF).

Commercial viability

The company is solely involved in teak production and as such has had to take a long term prospective on its profitability.  A teak seedling takes an estimated 22 years to reach full maturity although it can be harvested earlier (at 9 years) for a smaller return.  It is however making limited income in the meantime, from selling seedlings to NGOs, individuals and private companies.  This activity not only provides short term income, but FFF see it as a means for influencing and building the scale of production of teak in Fiji and influencing the quality of the Fijian teak brand, which will be important for FFF’s own marketing efforts.  FFF’s concept note was initially rejected by the ECF Regional Assessment panel because of the long term nature of the business case, but in a second concept note, FFF argued that the sales of seedlings and technical advice would realise sufficient income (over AU$300,000 per annum by the end of the three year project) to ensure the project is profitable within three years, as stipulated by ECF criteria.  In the longer term, FFF plans to harvest and plant 100,000 trees annually, producing 30,000 cubic meters of timber, ensuring sustainable profit.

At the time of the application, the company had twelve Fijian and international investors, and this has now increased (at the time of the review) to 27 investors, from whom FFF has raised a total of approximately F$2m (approx AU$1.3m).  Currently FFF is a company with limited liability and the shareholders own ordinary shares with a current price of 62.5 cents Fijian.  The company has plans to go public on the Fijian stock market, but is waiting for the current context of low levels of liquidity in the market to change.  The company Board has three founding Directors (all expats) and two non Executive Fijian Directors.  The structure and financial basis of the company appear sound, including its plans to raise more finance to support its development plans.  Australia Business Volunteer Service has provided some technical advice on the process of launching FFF on the stock exchange.

The staff and founding Directors of FFF started the company with limited forestry knowledge.  They have been supported by technical forestry assistance and advice from a volunteer adviser provided by the Australian Voluntary Business Service who visits the plantation fairly regularly and works closely with management and staff as they develop the plantation and business.  The market for FFF’s teak is predominantly India, and also China and has been growing steadily since the 1970s.  While it obviously impossible to be absolutely certain of market demand so far down the line, FFF’s confidence in the strength of this market and future growth at an estimated 5% per annum, appears credible.

FFF has been effective at attracting aid funds in addition to the ECF grant and beyond Australian volunteer support.  Small grants came through from the Global Green Fund and Conservation International.  The latter has commissioned FFF (with funding from Fuji Water) to provide local farmers with 6,000 seedlings.  While too much aid agency support might be a point of concern, in this case, the grants are relatively small and they don’t subsidise FFF’s core business model.

FFF’s financial forecasts and its long term plans appear credible, if slightly ambitious.  However, despite making impressive progress to date, FFF is a relatively new company working in a sector for which the financial returns are long term.  It has a very limited track record and its ability to realise the anticipated profits are untested.  FFF is therefore reasonably high risk.

The ECF grant of AU$190,000 is being used primarily to fund equipment and infrastructure in relation to improving the FFF’s nursery facilities (2 green houses, storage facilities etc), a tractor and a 4WD vehicle.  Most of these items appear to be necessary for implementing the project, for example the green houses are expected to improve rates of seed germination from a 50% success rate without greenhouse cover, to about 70-80% success.

Given the long term nature of the teak plantation and the risks involved in the business, it is very unlikely that FFF would have been able to access a commercial loan.  However, given its continuing success in attracting investors, and its plans to launch the company on the Fiji stock market, there is some question as to whether ECF funding was absolutely necessary for the project to go ahead.  The ECF grant funding has arguably not, however, replaced alternative investment options.

Scope and scale of anticipated poverty impact

The pro poor benefits of this project are clearly articulated in the application.  The maximum potential direct beneficiaries are:

- The employees of FFF, which have increased from approximately 50 last year, to 70 this year and is expected to increase by 20% per year for the next 2-3 years.  The wages received by these employees compares favourably with the wages they might earn from sugar cane cutting (approximately 30% higher).

- The local land owners, who are being provided with options, including the skills, for increasing the asset value of their land, and making it productive in the longer term.  For most of these land owners, the land is their only asset, and as most of it is uncultivated it has an extremely low value.  Sugar cane and small scale vegetable production are almost the only other options pursued by farmers.  The former is an increasingly uncompetitive sector providing farmers with very low returns and labourers with low wages; vegetable farming tends to be very small scale.  Growing teak is a low cost option, with minimal investment, which adds value to the land and has a long term return; FFF estimates that one hectare, planted with 1,000 trees will generate income of F$40,000 (standing timber value after approximately 22 years)

- Labourers and their families who may gain employment when land owners plant teak which needs germinating, planting and maintaining.

As the major part of the potential poverty impact is long term, it is crucial that the impact is effectively monitored and documented.  The grantee is not only capable of effective monitoring but is also already thinking of how to do this effectively.  For instance, FFF has developed links with the University of the South Pacific and is planning to use students to develop a baseline poverty assessment of local communities and then to monitor changes in household income and wellbeing.  This would be a very useful initiative.

Systemic change:

Large parts of this region of Fiji, and in fact the whole island, are uncultivated.  One of the main crops, sugar cane, is yielding ever lower returns, and landowners and leaseholders are struggling to understand what alternatives exist.  The market weakness being tackled in this project is the lack of knowledge (information and skills) in the local market to identify viable options such as teak, which will turn the land into a productive and valuable asset.

The project is enabling FFF to test the hypothesis that teak farming, starting with seeds that need to be germinated, rather than seedlings, is a viable long term business option for Fijian landowners.  If this hypothesis is correct, the systemic change from this project will be a new way of farming that will enable rural landowners to make a worthwhile livelihood from their land and to turn it into a productive asset, which also provides employment for rural labourers.  As far as FFF is concerned the project goes one step further than this; FFF suggests that the project will also provide an example of successful rural development, of which there are few in Fiji.

Level and type of innovation

There are two inter-related forms of innovation in this project, clearly articulated in the application:

The first is making use of previously uncultivated land for which no productive purpose had been identified.  Although teak is not new to Fiji (it was introduced approximately 100 years ago) it is not cultivated commercially in this region of the country.  The second is the new business model being adopted by FFF which a) involves following the teak growing process from germinating their own seeds through to the final tree harvesting.  This enables them to manage their own supply of seedlings as well as generate short term revenue by selling seedlings locally and elsewhere within Fiji; and b) working closely with the local community to ensure that they benefit directly from the business activities and have the opportunity to learn new skills and set up their own teak plantations.

FFF’s primary motivation to implement this project is commercial.  However, one of the founding Directors used to work with UNDP, and he both understands and appreciates the commercial value of combining developmental objectives and activities with traditional business ones.

It is worth noting that FFF has several other plans for the medium to longer term including diversification into other types of timber, the establishment of a timber mill and the possible development of a furniture making business.  The last two are aimed at ensure as much value is added to the timber in Fiji.  These are however, not part of the project.

Demonstration effect

The application clearly articulates what is being demonstrated by the project: firstly to local land owners, both freehold and leasehold, it is demonstrating a low cost route for developing their land which adds value and generates long term income.  When leasing land, FFF never leases more than a third of a landowners total land, in the hope that he will start planting seedlings on some of his remaining property.  FFF also provides access to seedlings and technical advice to further help landowners start up in teak.  Secondly, according to FFF, the project is demonstrating to aid agencies and Government that rural development is possible and a new route for achieving poverty reduction in rural areas.

Replication potential

It is largely too early to identify significant evidence of replication, but it is being actively encouraged by FFF.  There are examples of where some limited replication is taking place: one local farmer with leased land has planted 1000 trees, learning from FFF’s experience.  Several of FFF’s employees are planning similar ventures.  FFF has supplied seedlings to private land owners in other parts of the country, including the Shangri La Group which intends to start a community development project on one of its estates.  As mentioned above, other aid agencies have bought seedlings to help local communities plant teak on their own land.  If and as FF achieves returns, there is credible evidence that replication will take place.

Aide Memoire

MCS

Overview of the Project

Marine Consultancy Services (MCS) is a shipping company operating out of Santo Island, Vanuatu.  Its current owner, and driver of this project, entered the shipping sector in 2001 when he took a position with SeaLink.  In 2003, he left SeaLink, and leasing one vessel from his former employers, formed MCS.  In 2006 he reached an agreement to purchase the vessel.  This purchase, funded from cash flow, was completed after 2008 after just two years of operation.

Prior to the ECF project, MCS operated this one shipping vessel to provide a weekly shipping service between Santo and Port Vila, stopping at up to 4 islands on the way.  The service provides some passenger space but concentrates on freight.  As demand has increased between Port Vila and Santo, there has been less space for freight being delivered to and from the smaller islands along the route, and service to these islands has suffered.

There are several other shipping services operating on this and other routes; these include Chinese traders, which tend to offer the shipping services as a means to support their trading activities (mainly copra), and smaller shipping services with reduced freight capacity.  These competitors provide irregular and unreliable services and many islands can go several months without a visit from a ship.  When one does arrive it is often without any warning.  MCS’s business approach is to offer regular and reliable services, which islanders can depend upon.  This has resulted in increased demand for MCS’ services.

The project is based on the acquisition of a new boat to expand MCS’s service to under-served Northern and Outer islands, especially in the Banks and Torres Strait.  The business and developmental premise which underpins this expansion is twofold:

- Firstly, that a regular and reliable shipping service will encourage farmers and business people in these underserved islands to develop and increase their agriculture production, and their business and trading activity, which in turn will result in increased demand for MCS’s new service; and

- Secondly, that a regular and reliable service will allow for more regular deliveries of important public (and NGO) works.  The present system discourages this as chartering an entire service is prohibitively expensive, and coordinated pooling of different goods to make a charter worthwhile is simply too cumbersome for many to bother with.

Commercial viability

A regular shipping service to these islands is currently not deemed viable given that their small populations and the current low levels of economic activity translate into a lack of effective demand for the said shipping service.  The commercial viability of this project is based on the hypothesis that the inhabitants of the Northern and Outer islands will build and develop their businesses around the new reliable transportation services provided by MCS.  The ECF grant is being used by MCS to test whether this hypothesis is valid. While MCS is not able to provide any hard data to support this theory, anecdotal evidence, including its experience with its main shipping route, suggests that this hypothesis is credible.  At the time of the Progress Review MCS had made only one visit to the Banks and Torres Strait, so it is too early to say if this premise will be born out.

The manager/owner of MCS has demonstrated during the last seven years his ability to effectively manage a shipping business in this environment, and has generated sufficient cash flow to purchase a ship and purchase land at the Santo Wharf as well as build a storage facility.  Turnover and profit are relatively stable; MCS earned net profit in 2007 of V$37,442.  As such there are no obvious concerns about the commercial acumen of the Owner/Manager or the validity of MCS as a business.

There is a slight concern that the project was approved when less than 15% of the Owner’s contribution was made available in cash.  However, after the project was approved, he financed the additional Au $250,000 required for purchasing a more expensive boat than was originally planned, raising his overall and cash contribution substantially.

There is much more of a concern that the majority of matched funding was offered, and accepted, in the form of existing fixed assets – in effect his existing boat - which has no bearing (as far as we can tell at least) on the project being proposed.  Quite why this was deemed appropriate matched funding we find hard to ascertain.

Overall, the commercial viability of this project appears credible.  But what this actually means in terms of how regular any shipping service will be remains an open question.

In summary, the review team has three issues with the project.  Firstly, the question of whether it could have been financed in full, or in part, through some form of commercial lending.  Counter to popular wisdom, the CBA and discussions with a commercial bank in Port Vila as part of the Progress Review, suggest that sourcing commercial finance for the purchase of a AU$ 1m ship might not have been impossible.  In these circumstances, and given the sound basis of the company and the Owner’s history of paying off the purchase of the first boat through sound cash flow, a letter from the bank provides insufficient evidence that a bank genuinely would not have provided finance for the new ship.  However, even if commercial funding could have been found for the project, ECF funding is arguably still justifiable.

The second concern relates to the unsuitability of the new ship for the new route to the Northern and Outer islands.  MCS was not able to find an appropriate ship for the new route and purchased a ship that it was already leasing, but which was bigger than it needed and which had unsuitable cargo loading specs for the new islands.  MCS is therefore using the new ship on its existing shipping route between Santo and Port Vila where demand is stronger and has outstripped the capacity of its first ship.  The latter is being used on the new shipping route.  This makes clear commercial sense for MCS, and was agreed with ECF before the ship was purchased.  A smaller and therefore cheaper ship would clearly have been more appropriate for the project purpose, and it is unfortunate that one could not be found.

The third concern relates to Coffey’s ability to ensure MCS continue to use the ship to implement the project for the full project duration.  Project funds were provided to ensure that the new shipping route in the Northern and Outer islands is fully tested.  However, there may be commercial incentives for MCS to start using both ships on more profitable routes before the end of the project period.  This would not fit with the development objectives of the project.  While there is no reason to believe that MCS will renege on their agreement, there is no contractual or legal requirement for it to continue to do so, and Coffey seemingly has little recourse if MCS does not fulfil this obligation.

Scope and scale of anticipated poverty impact

The maximum potential direct beneficiaries of this project are the 9,000 inhabitants of the islands to be served by the proposed new shipping route.  However, there has been no economic or social research to identify the development needs of these island populations, what proportion will be affected, and how the project could and will benefit them.  One would have expected more information on this to be provided in the application, which could then have been used as a baseline for monitoring any impact.

However, anecdotal evidence provides a credible basis for the argument that the inhabitants of the targeted islands, who are currently served by unreliable shipping services, are likely to realise clear economic and social benefits from the project.  The latter include improved access to developmental services provided by aid agencies and Government.  However, the project anticipates that the islanders will respond to the improved transportation services automatically.  There is a significant missed opportunity in this approach, which should instead have incorporated activities to facilitate islanders to develop, diversify and grow their businesses around the new transportation opportunities.  This would ensure that the maximum number of islanders benefit, and in an inclusive and sustainable way.

It would not be reasonable to expect MCS, as a shipping business, to undertake this community development work, which requires specialized expertise.  However, one could have expected ECF to encourage, or even require, MCS to develop linkages with appropriate organisations (private sector as well as NGO) with experience of working with local communities, to help them respond effectively to the new services.  One example would be the coordinating and bulking produce from smallholders, to ensure maximum use of the new shipping service.  The incentive for MCS to do this would not just be as a condition for funding, but also because the community development work would, at a minimum, increase demand for the new regular shipping services more quickly than might otherwise happen.

Notwithstanding this missed opportunity, and the lack of reliable information on the economic and social context on the targeted islands, the review team believes there that the potential poverty impact of the project is significant – providing the service is offered with sufficient regularity to encourage investment by islanders in changed economic practices (as stated above, there is no minimum schedule of service enforceable in the ECF contract).

Lastly, it is worth noting that there is some concern, raised particularly in the report from the initial Cost Benefit Analysis, that the project will have enabled, and subsidised, MCS to become active in a market already served by other shipping companies, and that the grant funding has enabled them to crowd out these suppliers.  The review team was not able to substantiate this; in fact given that MCS had only made one trip on the new route, it seems unlikely that it will have had a significant impact on any other shipping service providers yet.

Systemic change:

The market weakness being tackled in this project is the isolation of the inhabitants of these target islands, which excludes them from markets and thereby constrains their economic and livelihood opportunities.  This is caused by a negative cycle of poor transport service delivery to the Northern and Outer islands, which results in low levels of economic activity, which in turn result in low levels of demand for transportation services.  And so the cycle starts again.

The project is enabling MCS to test the hypothesis that the provision of regular and reliable shipping services will stimulate sufficient economic activity, and thus demand for the shipping services, to make a previously unprofitable route, financially viable.  There is therefore huge value in monitoring and documenting this process, as this is a market weakness experienced in many other parts of the region.

The systemic change in this project is the provision of regular and reliable shipping transportation to islands, at a profit, which to date have relied on irregular and unreliable shipping services.

Level and type of innovation

The innovation in this project, clearly articulated in the application, is MCS’s business model, which is to provide a regular and reliable service to the specific islands being targeted.  This differs from its competitors who tend to provide unreliable services.  MCS has been following this approach (and proven its commercial validity) on its current routes, but it is new for these islands.

MCS’s primary motivation to implement this is commercial: by providing a better (regular and reliable) service than their competitors, they both develop demand for their service and improve their competitive position.  MCS is essentially applying the business approach they use on their main shipping route, to a new and different environment – remote islands with smaller populations.

Demonstration effect

The application clearly articulates what is being demonstrated by the project: i) the financial viability of providing transportation to previously fairly isolated islands; ii) a new business model (regular and reliable service) which increases demand and leads to commercial viability; and iii) the new business model provides pro poor benefits for islanders.

The target audiences are primarily other transportation providers (large and small); a secondary audience to consider would be the Government, to demonstrate the social and economic benefits of ensuring adequate transport services for other isolated areas of the country.  Lastly, business people on the previously isolated islands who can develop their businesses in new ways and with new markets are a key audience.

Replication potential

It is largely too early to identify evidence of replication.  The primary intention is that the project will encourage a different business approach amongst other shipping companies, who will be able to see firsthand how MCS was able to develop a profitable shipping route by servicing islands that were previously deemed unprofitable.

However, as this is a business model that MCS has been running for several years on more obviously profitable routes, and with considerable success, it is important to note that there is little evidence of replication amongst either bigger ship owners or indeed the small Ni-Vanuatu sea transport businesses.  In addition, there is no evidence of interest by Government in the approach.  This suggests that replication is unlikely to happen automatically and will need to be encouraged and stimulated.

An important factor in this will be the availability of credible information regarding the project’s impact on the economic activities and livelihoods of the islanders, as well as the profitability of the new route for MCS.  The monitoring and documentation of the impact of this initiative is therefore crucial; the MEF needs to be reviewed to ensure all relevant information is being effectively captured. This is a role for the ECF.

Aide Memoire

Natures Way

Overview of the project

In recent years Nature's Way has shown a steady gradual increase in the volume of treated and exported fruits and vegetables (eggplant, papaya, mango, breadfruit): from 656,645kg in 2004 to 794,619kg in 2005 to 1,176,482kg in 2006 to 994,789kg in 2007 to 863,898 in 2008.  The export jump between 2005 and 2006 could not be completely consolidated the next year.  In 2008 exports were affected by a cyclone.  The flooding in February 2009, when Nature’s Way had to virtually shut down for a month because no fresh harvest came from the land, will influence this year’s figures.

Nature's Way works with a strategic plan 2006-2012.  This strategic plan presents a broad vision for growth, which is based on a number of interrelated developments:

- New quarantine protocols coming in place for new markets (e.g., breadfruit to the United States) and products (e.g., bittergourd, bottle gourd, sponge gourd, jackfruit, 'wi' (local 'apple-like' fruit variety, local pumpkin varieties).  Various bilateral negotiations are taking place; when they will result in an agreement is difficult to predict.  There is a plan to hire a consultant to find out why progress has been slow.  New products were chosen on the basis of quick turn around and the expectation that these represent relatively underserviced markets, not dominated by multinationals such as Dole.

- Expanded market access in existing markets (New Zealand and Australia) beyond ethnic and corner shop-type niche markets into supermarkets.  An extensive market study on papaya has been undertaken recently in New Zealand, Australia, the United States and Japan to understand price levels, quality and existing supply in these markets.  Similar studies are planned for other major crops.

- Ensured seed supply for papaya.  Nature' Way currently imports seeds from (the university of) Hawaii.  It plans to promote the 'Fiji Red' brand for sweet, red papaya.  Ensuring a seed supply (and hence genetic purity) helps to ensure the quality and consistency of the fruit sold under the brand.  Next year a few farmers, taking up the role of a nursery, will start local multiplication of seed.

- Better agronomic practices applied by farmers.  This goes hand in hand with supplying good quality seeds and an emphasis on consistent, high-quality produce to penetrate the supermarkets.  An extension officer was hired last year, but he passed away.  A new person will be recruited next year.  Particular issues here relate to pest control and irrigation to lengthen the production season.  Also, the plan is to test organic cultivation (there is a market for this) and identifying production sites outside the Sigatoka Valley.  This could reduce risks related to bad weather.  Also, closer proximity to the airport reduces transportation costs and risk of damaging the produce.  There are potential pro-poor benefits here for cane farmers if they are able to switch to more profitable export crops.

- Quality control and reduction of post-harvest losses due to better handling.  Standard-size crates have been introduced for transporting produce to Nature's Way.  Also, a grading machine has been put into place to reduce manual handling of produce (again to reduce the risk of damaging due to inappropriate handling).  The plan to study the complete chain from farmer to retailer (overseas) to assess where produce gets damaged and losses (rejections) occur.

The above represents a larger growth strategy for Nature’s Way, into which the ECF grant feeds.  Specifically, the ECF grant will be put to funding a fourth heat treatment chamber, a grading machine, fork lifters to speed up the on and offloading (and by replacing heavy lifting work helping Nature's Way to acquire HACCP certification - important for the supermarket channel), an expanded loading area (suitable to fill up refill/sea containers, crates for transportation (set up as a revolving fund), extension services to farmers.

At the same time the EU FACT programme has funded the extensive papaya market study.  And ACIAR, funded amongst others by AusAID, is looking in to the above mentioned seed multiplication, improving agronomics and quality control.

Commercial Viability

All these dynamics make it difficult to properly assess the commercial viability of Nature's Way, and more specifically the particular viability of the ECF investment.  Nature's Way objectives and strategy are very ambitious, but also well articulated.  Their growth plan is rather compelling, and the activities mentioned above make sense and are generally considered to be 'needed' for Nature's Way, but also for the fruit and vegetable sector in general: better market research, diversification of markets, quarantine protocols, better quality produce, better extension services, better seeds, etc.  The reason why Nature's Way is able to attract support is that is perhaps the only institution in Fiji taking up all these issues.

Nature's Way current business model is based on charging F$ 0.35 for each kg of produce treated.  This generates a turnover of approximately F$ 300,000 per year, sufficient to cover the operational costs and build up a small reserve, but not to finance the variety of business development/expansion activities listed above.  If the projected expansion of export volume proves to be correct, Nature's Way is commercially viable.  At the same time this expansion is prone to certain risks: sufficient airfreight capacity, quarantine protocols getting approved, the ability to diversify and access new markets.

Nature's Way currently does not fully utilize the installed heat treatment capacity. The two old chambers have a combined capacity of 5 ton per shift, which means that for an export volume of around 1,000 tons, 200 runs are required, approximately one shift per working day.  However, in the peak season 30 runs per month are required.  In principle two runs per day are possible, which would imply that even during the peak season capacity utilization is only 68%.  However, one needs to take into consideration here that perfect coordination is difficult (9 exporters are involved, who in turn source from a few hundred farmers), and that, instead of 'steady production', treatment it is often a matter of getting as much as possible through as quickly as possible to fill up available freight space.  Nevertheless, the justification of additional treatment capacity is future expansion, not current under capacity.

The expansion forecasted in the strategy plan and the proposal is an increase in export value from F$ 2.8M in 2008 to F$ 6.7M in 2012.  It is not possible at this point in time to assess whether this projection is reasonable (as it is dependent on the developments and risk mentioned above); only that the groundwork for these projections is of good quality but that the opening up of markets partially is beyond Nature's Way control.  This means Nature's Way is likely to expand in the near future; how much and how significant this will be before 2012 is anybody's guess.

Scope and scale of anticipated poverty impact

The scope and scale of anticipated poverty impact is closely related to the expansion discussed above.  The application forecasts additional employment creation of 730 jobs, in the form of causal labour on farms and additional staff required by exporters to handle the additional export volume.  This predication is based on current employment - export volume ratio and is reasonable, provided that exports really expand to projected levels.

The farmers themselves should not be considered as poor.  Here the pro-poor aspect of export comes in only when new farmers will start growing export crops.  Again, this figure is difficult to estimate.  Farmers typically have abundant land (approximately 10 acres), might not utilize all their land, will grow export crops only on part of the utilized land, and produce a crop which is only partially suitable for export in terms of quality.  This means there is much scope for expansion of production among existing farmers.  At the same time is it known that very few farmers go for specialisation, that there is a range of factors which prevent farmers from doing so even if they want to (suitable land, availability of labour, sufficient capital), that exporters might not want to become too dependent on a few farmers, and that Nature's Way is considering to actively diversify production to other geographical areas.

Together with Nature's Way, the review team made an estimation of the potential number of new farmers moving into export crops.  If an additional export of 1690 tonnes of produce would solely come from an increase in papaya export, this would require an additional 1,300 acres of land under papaya cultivation (assuming that for each farmer only 50% of his crop is exportable).  Given an average plot size per farmer for papaya of 2 acres, this would mean there is room for 650 new farmers to start production.  Obviously part of that room will be taken up by existing farmers expanding production and new entry will be less.  However, even if only 325 new farmers enter, this represents a sizeable expansion of the current export production base of around 450 farmers.  Still more interesting is the additional income that in particular these new farmers would earn by switching to export crops.  However, there were no figures available to make such estimations within the time span of this review visit.

It should be emphasized that the merits of Nature's Way should not be measured in pro-poor outcomes per se.  First and foremost Nature's Way serves a strategic function in the Fiji horticulture sector by opening export markets.  In doing so what is of primary importance is growing crops of a sufficient quality in a sufficiently organized manner to meet export standards.  It should be recognized and appreciated that Nature's Way is an engine for export promotion, and only indirectly for poverty alleviation.

Level and type of innovation

In the light of the discussion above it does not make sense to discuss the ECF grant in isolation.  The grant is, and from Nature's Way perspective also intended to be, part of something bigger.  Nature's Way came into existence in 1995.  Since then it has set out on a course, which can be qualified as innovative.  The inspiration for Nature's Way came from two treatment facilities existing in the Pacific, and in this sense it is a copy cat, but making it work in the context of Fiji, the organizational set up and its technology all have innovative aspects to it.

The current phase of expansion as described in the introduction is probably the most ambitious to date given the fact that it aims to develop stronger backward linkages (seeds, extension) and stronger forward linkages (market research, marketing strategies, protocols). The ECF grant supports this and supports the core operation, the installation itself.

Key innovative features are:

- The organization itself, a cooperative of exporters and farmers brought together under the umbrella of quarantine treatment for export, unique in the context of Fiji, but also used internationally as an example of a successful public-private partnership, or perhaps better:  a hybrid organization, not public, but also not private in nature.

- Safeguarding, creating a common good, valuable to all those related to export, namely a product that, first, meet quarantine standards, and second is of a good and consistent quality. There are many aspects to this: rejecting produce for treatment, which does not meet standards (not sufficiently ripe, disease infested, wrong variety), introducing seeds to maintain genetic purity, developing a common Fiji brand. There is no other organization doing this in Fiji.

- Providing private extension services. With the exception perhaps of a few large agribusinesses there is no organization doing this, and, as far as known, certainly not in the vegetable sector.

- The heat treatment facility itself.

New steps for Nature's Way most directly related to the ECF grant are in the area of rural extension and quality control (crates, grading machine).

The innovations are commercially motivated, serve the bigger purpose of establish of an all-round service provider stimulating export, and can serve as a model for replication inside and outside Fiji.

Systemic Change

Nature's Way does represent systemic change in the sense that it has been able to connect market - Fijian fresh fruit and vegetables producers and the New Zealand and Australian consumers - which otherwise would not have connected.  This disconnect is not caused by a simple lack of information, but relates to the difficulty of finding the right institutional and technological arrangement to meet quarantine standards.  Nature's Way is more than a shed around a heat treatment chamber.  The various functions it serves are all part of what makes it work.  This includes creating the 'common good' discussed above, treading a fine line to ensure quality and reject produce from members who do not comply with standards without blowing up the cooperative and breaking new ground by developing extension services.  The ECF grant did not trigger this systemic change, but supported the ongoing process to build up Nature's Way.

Demonstration effect

Nature's Ways serves as an example of how exporters and producers can be united under a cooperative umbrella, which in turn performs functions that in other countries would be considered within the public domain.  Despite the fact that Nature's Way still need to reach full maturity and that some questions can be raised about its commercial viability if it cannot expand further, it is this business model that serves as an example for governments and exporters in the Pacific region.  However, given its complexity it would be unrealistic to expect copies of Nature's Ways across the island and the region.

Replication potential

Nature's Ways says it does not want to expand further.  Now it provides a common facility allowing aspiring exporters to grow and diversify.  By the time these exporters get so big that Nature's Way is getting to small for them they should have the capacity to set up their own treatment chamber.

Nature's Way is not being copied right.  And, as mentioned above, this should be surprising.  Under its room it probably brings together the most dynamic exporters on Fiji.  Instead of replication, at some points perhaps some of these will hive off their own treatment facility.  At that point in time, Nature's Way set up and practices can serve as an example to be replicated.

Aide Memoire

Reddy Farms Ltd, Fiji

Overview of the Project

Reddy Farms is a family owned business, which has been registered and operational for more than eleven years.  Up until 2006, the farm raised, reared and sold a local breed of ducks, Muscovy Campbell.  In 2006, in order to meet growing market demand, Reddy Farms began to import Peking ducks from New Zealand and sell to its existing market of hotels and restaurants.  There is a 27% duty on imported poultry in Fiji, which makes it far more expensive than local produced products.  Because of this, and as the cost of day olds and freight increased, the imported ducks became less competitive.  Reddy Farms stopped importing fully reared ducks, and instead imported a Peking breeder crop and a hatching machine from New Zealand which enabled it to breed, rear and raise its own Peking ducks.

Peking ducks provide better quality meat, and they take only 6-7 weeks to mature (as opposed to Muscovy Campbell which take 14 weeks).  Reddy Farms can therefore charge higher prices for its Peking ducks which cost less to rear.  Reddy Farms conducted some research amongst its existing market, which suggested that demand for Peking ducks has been increasing.

Reddy Farms’ ECF funded project essentially enables it to respond to this high level of demand by switching its duck stock to almost 100% Peking, and dramatically increasing its levels of production.  It plans to establish a hatchery, which will produce an estimated 1,125 ducklings a week (an increase of 75% on its current production levels).  Along with feed and medications, these ducklings will be distributed amongst contracted local cane farmers who will have been trained, by Reddy Farms, to rear them.  Reddy Farms will provide TA and advice to the farmers to help them with this process.  At the end of the fattening period of approximately 7 weeks, Reddy Farms will collect and weigh the ducklings, pay the farmers, and then process and freeze them.  They will be delivered to the market according to an agreed schedule.

This project is centred on Reddy Farms meeting future demand for Peking Ducks through a contracted small holder production model.  Their inspiration for this model comes from seeing it already being applied successfully in the poultry sector in Fiji.

Commercial viability

Reddy Farms’ rationale for this project is commercial.  The reported reason for not simply expanding the duck rearing capacity of the farm ‘in-house’, is that the cost of infrastructure (duck houses and expanded electricity supply etc) is too significant.  However, in the review team’s view that if a similar grant had been made available without the pro poor criteria, an expansion of Reddy Farm’s in house capacity would have been a simpler, lower risk and more commercially viable option, than the somewhat risky contracting out approach which the project is focused on.

Notwithstanding the above, Reddy Farms is a reasonably strong business with a good track record in duck farming and marketing.  The farm’s owners have demonstrated their ability to respond to market opportunities by their decision to start distributing Peking ducks and then eventually move to hatching them on their farm.  These have all proved to be sound business decisions.  The farm makes a steady profit, and the lease for the farm’s land was recently renewed with a 25 year extension.  Reddy Farms has an outstanding loan of F$60,000 with interest rate of 14%, with the Fiji Development Bank.  Reddy Farm has commissioned research into the market to ensure that there is sufficient demand for its proposed expansion.  The owner found the research valuable but admitted that without the ECF application process he would not have bothered to undertake this type of research.

As mentioned above, there are inherent risks with this project, which involves handing over a vulnerable asset to relatively unknown farmers.  Reddy Farms is aware of this and is putting in place important steps to mitigate these risks.  These include: a) having a formal contract with the farmers which while probably not enforceable, will provide a semblance of formality to the relationship; b) selecting farmers who live in close proximity to Reddy Farms which will help with monitoring and transport costs; c) selecting farmers who intend to rear the ducks close to their farmhouses, and helping ensure they have solidly built duck houses, as the threat from thieves is reasonably significant towards the end of the rearing period; d) providing extensive training and technical assistance and advice to the farmers to help them acquire the necessary skills for effectively rearing the ducklings; and e) spreading the risk by making sure that no farmer takes on more than 50 ducklings until he has proved he is capable and trustworthy.  However, despite these largely sensible measures, the risk with this venture remains significant.

Scope and scale of anticipated poverty impact

The pro poor benefits of this project are clearly articulated in the application.  The maximum potential direct beneficiaries are:

- The local small scale cane farmers, and their families, who are contracted by Reddy Farm to rear the ducks.  In the first instance, Reddy Farm intends to contract 150 farms and allocate 50 ducks to each farmer.  If the contracted farmer is successful he can take 6 batches of 50 ducks per year and will earn an additional net income of F$1,200, plus a bonus of 5% of the mature ducks he rears will be provided at cost (which he can eat or sell for an estimated 100% profit).  The average yearly income of the small scale cane farmers is estimated to be less than F$2,200, so this is a significant addition to his household earnings, at virtually no risk to himself.  However, it is important to emphasise that these projections are based on a problem free process and fairly efficient turn around between batches of ducks.

- There will be an increase in direct employment by Reddy Farm from 6 at the moment, to 12 employees during the course of the project.

- Local small scale pig farmers who will have access to duck offal, a bye product from Reddy Farms, at a competitive price.  Pig farmers can use duck offal as part of the feed for their pigs.

During the cane harvesting season (June to late November) the burden of rearing the ducks will inevitably fall on the women in the household who tend to be less involved in cane harvesting.  While this may strengthen their position within their households, it will of course add to their workload.

Reddy Farms has done little systematic research to identify potential contract farmers but it has developed links with the Ministry of Agriculture and the Fiji Sugar Corporation, whose Officers have good knowledge of the local farmers and can advise who are the right farmers to work with.

Systemic change:

There is no clear market weakness that this project is addressing.  There is a reasonably clear market demand for Peking duck and Reddy Farms and one other competitor are striving to meet this demand.  Reddy Farms has already started the process of hatching and rearing Peking ducks (as opposed to importing them) and this project will enable them to expand this process.

The contracting out of the rearing process is a clear change to the usual duck farming model, and as such represents a systemic change, but it is not clear what market weakness this new approach is specifically addressing.

Level and type of innovation

There are two inter related forms of innovation in this project, clearly articulated in the application:

The first is the hatching of ducklings from farm reared breeder Peking ducks.  This enables Reddy Farms to have a steady and relatively low cost supply of ducklings to rear.  The second is the contract farm model for rearing the ducks which will allow Reddy Farm to expand its productivity without making some of the necessary fixed cost investments.  Both of these innovations are designed to enable Reddy Farms to expand its production capacity significantly.

Demonstration effect

The application clearly articulates what is being demonstrated by the project: a new business model for duck farming which a) does not rely on imported ducklings, and b) enables significant production expansions by contracting out the rearing process to local small scale farmers.  What is less clear is who these lessons are being demonstrated to.  There is only one other Duck farmer in Fiji and his focus is on the local breed of ducks with some imports of Peking ducks from New Zealand, which he slaughters according to halal standards.  The market is not large enough to attract many other players.  Some chicken farmers in Fiji already follow the same model (in fact this was the stimulus for the Reddy Farms concept) and it seems unlikely that this model can be transferred to other livestock farming models.

Replication potential

As mentioned, this project is about Reddy Farms applying to Peking ducks a business model which is already applied in the wider poultry sector in Fiji.

Aide Memoire

Sarami Cattle

Overview of the Project

Sarami Plantation is a well-established livestock breeder, probably the most sophisticated farm of its kind on the island of Santo.  It comprises of two ranches of approximately 2,000 hectares each, one is used as a breeding pen for young animals, the other for fattening mature animals up to the level that they are ready to be sold to the abattoir.  The company has been operating for thirty years.

The Sarami project proposal involves three interrelated technical innovations to bring cattle raising to a higher level of intensity, and while these innovations take place on the Sarami plantation itself, there are linkages with the surrounding small-scale holders.

- Improving the breed.  For this embryos are to be imported from Australia. Vanuatu is currently 'disease-free' and embryos are the safest way of improving the breed without running the risk of contamination.  The other advantage is that it creates a 'pure breed', not influenced by the genetic stock on the island.  It should be noted that introducing new, 'improved' breeds is a common feature in the context of agricultural intensification.  The owner anticipates that a four-year breeding program is required to replace his stock of 4,000 animals with this new breed.  After that the plan is to provide young bulls to surrounding small holders on the principle of 'one young bull for free for every forty animals sold to Sarami for fattening'.  This should help improve the stock of surrounding small holders as well (however, it is noted that breed quality is not identified as any particular constraint to growth / competitiveness of the cattle sector in Vanuatu).  The benefit for both Sarami and the smallholders is explained under the next point.

- Buy semi-mature animals from surrounding smallholders after 2.5 years for final fattening up to grade 1 quality.  According to the owner smallholders can only produce grade 2 quality cattle, because their scrub pastures cannot provide the animals with sufficient feed to have them grow up to a certain size.  In practice this implies that smallholders sell off their cattle after four years at a (carcass) weight of around 230 kg or less, earning Vatu 80-120 per kg.  The owner's plan is to buy the cattle from the smallholders after 2.5 years, offering a price of Vatu 150 per kg, fatten them further up to 300kg (carcass weight) or more and sell them to the abattoir for Vatu 190-210 per kg.  The gain for the owner is being able to sell more grade 1 cattle; the gain for the smallholder is to sell off his cattle earlier (thus having a shorter cycle) and getting a better price.  If smallholders have the improved breed, which responds better to improved fodder, this makes the process more efficient.

- Improve pastures and produce silage to speed up fattening and be able to increase the 'stocking density' from 4 to 6 animals per hectare.  The owner plans to improve pastures, 'reinforced' with nitrogen binding legume, to be able to stock more animals.  He also plans to introduce a new grass variety, sorghum grass, to make silage, which in turn will be used to fatten the cattle.  Also this highly nutritious silage will be used to feed young calves.  The owner plans to buy young calves from small holders when their stock exceeds the capacity of their grazing grounds.  This reduces competition for fodder for the remaining cattle and speeds up the fattening.  By feeding the calves ('weaners') with silage one can avoid the calves losing weight when switching from milk to feed, which again speeds up the fattening.

To conclude, the premise of the Sarami plan is to function very similar to 'nucleus estates' such as found in the coconut or palm oil sector.  This model represents a hybrid of large-scale and small-scale land holding, in which the large-scale central estate ensures the availability of core services to ensure productivity (in the Sarami case a refined breeding and fattening process).  These services support the central estate, but also for surrounding small holders.  In this way the small holders gain from access to services they otherwise would not have had.  The central estate benefits from the additional scale that is brought in by incorporating smallholders.

One additional service not mentioned so far is providing private transportation services.  Private services are claimed to be up to 66% cheaper than the public service provided so far that eat up a more than sizeable chunk of the smallholder's profit on sales.  Sarami already uses private ni-Vanuatu contractors for occasional cattle purchases from smallholders and plans to continue to work on this basis when starting to purchase on a larger scale.  The application mentions that Sarami intends to offer this private service for free to smallholders selling to them.  The motivation for and commercial sustainability of this offer is not at all clear.

Commercial Viability

With a growing tourism sector in Vanuatu and stable exports to Japan, demand for Sarami's beef appears relatively secure.  The uncertainty of the project lies in the techno-economic feasibility of the innovation package rather than the commercial viability per se.  Sarami tested the idea of buying and fattening semi-mature animals before.  About six years ago they bought 1,200 semi-mature animals from smallholders.  The experience then was that the model was not very profitable.  One reason might have been that at the time the transaction was funded with a loan from ANZ.  The next year they could not buy due to a lack of working capital: apparently too much working capital was still locked up in cattle on the land.  Therefore another reason might have been the additional time and efforts needed to fatten the 'meagre' smallholders cows up to grade 1 quality (pasture land needed for additional fattening minus pasture land saved by having the animals feed the first 2-3 years on the smallholder's land).

The pattern repeated itself about three years ago, when Sarami again bought 2,000 very young animals, this time from a failing, large-scale Korean farm.  The young animals offered an opportunity to fatten animals up to grade 1 without having to go through the whole four-year cycle. But again, the next year Sarami could not buy more cattle because they had too much stock.

In other words, the techno-economic viability of the project depends on the interaction between the three innovations described above: being able to source reasonably sized animals from smallholders and being able to fatten them up reasonably quick up to grade 1 with the help of a breed that responds well to highly nutritious silage.  It is too early to say much about the chance of success.  The owner is a restless innovator who, as mentioned, tried the business model before and who also already experimented with silage.  It is clear that from a technical perspective he is running a sophisticated business, with well-managed pastures compared to his neighbours (clean, lush pasture versus pasture overgrown with weeds).  However it should also be noted that the project is only able to produce a small profit after three years, based on a five-fold turnover in sales.  It will take a full six years to recover the investments made.  At the same time, Sarami appears to be a healthy company with annual profits ranging between A$ 700,000 and A$ 1,200,000 per annum so there should be funds to buffer for setbacks.

Scope and scale of anticipated poverty impact

The 'surrounding smallholders' from whom Sarami intends to buy the semi-mature animals are in fact communities.  There is no concrete information on these communities, nor the degree of poverty faced by same.  Cattle raising is said to be the main source of cash income on parts of Santo island and with the figures provided, this might not always be a very profitable activity as a grade 2 bull fetches a price of around Vatu 15,000 at the abattoir, up to half of which needs to be spend on transportation costs.  However it is unlikely that other forms of cash income, from either kava, or copra, or cacao are completely absent.  More detailed information is needed here.

Perhaps a bigger issue is the scale of operations.  Due to the natural ceiling for expansion set by the carrying capacity of the pastures, Sarami believes it can expand its herd with maximum 2,000 animals at a time.  How often this additional stock can be replenished depends on market demand and the speed at which the animals can be fattened up.  This implies that on average perhaps around 2,000 individuals could benefit from this project (the application mentions 1,500), but in all likeness the number will be considerably less, as the average target smallholding community has herds of between 100 and 200 animals.  It is highly likely that Sarami will aim to buy as many cattle as possible from as limited a number of communities to reduce transaction costs.  Again, more exact information on effective outreach is needed here.

Also more information is needed on the significance of this outreach in relation to the total number of smallholder communities engaged in cattle raising.  This project represents a considerable grant investment by ECF, and outreach must extend beyond a relative few more capacitated communities for it to remain valid.

Benefits in terms of employment creation will be minimal. Sarami already employs around 50 persons for fencing and weed control.  This is not expected to increase substantially.

The benefits per animal sold to Sarami are relatively clearly presented.  Instead of earning Vatu 20,000 for a four-year animal (and paying perhaps Vatu 7,000 for transportation), Sarami offers Vatu 30,000 after approximately 2.5 to 3 years and no transportation costs (or maximum the private rate of Vatu 3,000).  This creates an additional income per animal per annum of roughly Vatu 7,000.  This needs to be compared with the gains from other cash earning activities to be able to assess the significance of this amount.

However, it is important to note here that it is unclear exactly why Sarami 'volunteers' to pay 50% more than the market price for smallholder animals and offers free transportation services and offers a free bull for every forty animals sold.  For each offer there is a justification (incentivizing smallholders to supply to them, ensuring that smallholders start to work with the improved breed), but the overall package seems particularly 'generous'.  At the same time, the same business model seems to be followed in Sarami's kava export business.  Paying a premium price ensures supply and cements relations (Sarami is vulnerable here, with its large herd of virtually unprotected animals).

Systemic Change

This project has two sides.  On the one hand Sarami could be viewed as a nucleus of innovation for the wider cattle-raising sector on Santo Island and beyond.  This is the most commonly heard 'justification' for the project.  This justification is not without reason: Sarami connects the sector to sources of innovation in breeding and silage (in Australia) and attempts to translate these in to a feasible practice on the ground in Santo.  Thus, Sarami could be of significant and strategic importance for the sector.  The two other large cattle raisers do not seem to be in the position to do so.  However, it should be noted that there is insufficient information on the cattle-raising sector in general to be able to estimate how unique Sarami's innovation package is.

On the other side, it still has to be seen how far-reaching the influence Sarami's innovation will be on the sector at large.  At mentioned, the direct outreach of the project is not clear at this point in time. Adaptation of Sarami's innovation package by the sector at large seems to be unlikely at this point in time. Large cattle raisers are behind in terms of proper pasture management. Current smallholder's practice does not seem to go beyond keeping cattle in any bush area as long as the cattle can feed there. The Sarami tries to influence the quality of smallholders' herds by buying up weaners, but the project does not involve other activities that could foster shared learning.

To conclude, one can see Sarami as a strategic innovation nucleus for the cattle-raising sector in Vanuatu and the Pacific; but one can also see it as funding the business expansion of a leader in the industry, with some fringe benefits for surrounding smallholders.

Level and type of innovation

Judging from the application form the project seems to represent a clear innovation for the company itself.  Although various elements of the package have been tried before (buying semi-mature animals, producing silage), the depth of the current package (the new breed, the introduction of a new grass variety for silage) justifies labelling the project as innovative.

However, an FAO report by Dr. Struthers, Principal Veterinary Officer for Vanuatu (ftp://ftp.fao.org/docrep/fao/010/a1250e/annexes/CountryReports/Vanuatu.pdf) does raise a number of questions about a) to what extent this project is responding to an identified constraint, and b) to what extent it is genuinely innovative compared to current practice.  For example, the report confirms:

- There are no major limitations to breed improvement [in Vanuatu]

- One breeder consistently introduces new genetics through artificial insemination.  Intermittently other breeders introduce some semen or embryos.

- The one research station has now disbanded their herd and left the genetic improvement to the private property owners.  This is working well and it would not be either useful or practical for research station involvement.

So, whilst the project itself can be seen to be innovative (in the sense of interlinking various components), the need for the innovation in terms of responding to a clearly identified sector constraint is perhaps less clear.

Demonstration effect & Replication potential

If successful, Sarami might set a new standard for large scale cattle raising and the various aspects related to that (ranging from pasture management to silage to breeds, etcetera).  Sarami might even represent a model for cattle raising combining the specialised knowhow of a 'central estate (as mentioned above) with the additional scale gained by involving smallholders.  However, too little is known at this point about the purchasing strategy and the sustainability of paying high prices and offering free services to be sure of this.

The target audience for this demonstration is varied.  Obviously this includes the Vanuatu cattle-raising sector (both private and public entities), but might also include neighbouring countries (Fiji for instance has abandoned pasture land and is looking for ways to bring that back into use).  However, there only one clearly defined way in which the lessons from the Sarami innovation package will reach this audience.  As part of the 'deal', the internal approved that approved the application inserted the obligation that Sarami needs to present its way of working across the Pacific.  Whether such a passive strategy is sufficient to spark wider change, time will tell.  The review team suspects not.

In this vein the potential for spontaneous replication seems limited at this point in time.  For this the gap between Sarami's practices and others in the sectors appears too big.

Aide Memoire

SUNLABOB

Overview of the Project

Sunlabob is a Laos based distributor and operator of alternative off-grid energy solutions.  Their application centres on the extension of electricity generation to currently unconnected villages in Laos.

There appears quite some divergence, and/or lack of clarity between the details offered in the approved application and the discussions held with Sunlabob.  To confirm, the project being proposed (based on discussions with Sunlabob) is structured as follows:

- Pilot 1: a small scale hydro scheme installed relatively close to the existing national grid (around 6km).  The site is dependent on assessments which are to be based on recent feasibility studies being completed by the Government of Laos (GoL) (under the Rural Electrification Project II).  The idea is that Sunlabob install the generating capacity, the village grid and operate retail provision.  In time, EDL, the national electricity utility will expand the grid, will take over maintenance and retail operations, and will buy electricity from Sunlabob who will revert to a generation and wholesale function only.

- Pilot 2: this is in partnership with Helvetas (a Swiss NGO).  The model is quite different.  It is not clear which technology will be used (solar or hydro).  This chosen village will be well away from the national grid, and will be stand alone.  The basic proposition is that Sunlabob install and manage the generation and retail of electricity.  Helvetas invest in various fixed infrastructure.  It is recognised that initially the village will not consume sufficient power for the scheme to be viable.  Hence, Helvetas intend working with villagers to upgrade their livelihood activities to be more energy intensive, and to raise incomes to a level where they can consume and pay sufficiently for the scheme to be viable.

Their proposal centres most of its detail on Pilot 1 above, whereas their previous experience, and half of the current project at least, centres on the model presented in Pilot 2.  The success claimed by Sunlabob in Nam Kha village (unqualified by the review team) relates to rehabilitating a small scale hydro plant, and falls under Pilot 2 above.

The application refers to a Memorandum of Understanding between Sunlabob and EDL.  This has not been provided in the information made available to the review team (though we’ve now asked the ECF Fund Manager for this).  Irrespective of this, at the time of the review team’s meeting with Sunlabob it was confirmed that there is still no contract in place between Sunlabob and EDL.  This is clearly a major risk to proceeding, as are concerns over the lack of capacity and finance within EDL to honour their side of any arrangement.  It is highly questionable as to why such a significant grant was awarded, unconditionally, before the signing of a contract between Sunlabob and EDL.

It is noted that if EDL do not sign the contract with Sunlabob, the latter has confirmed their intention to partner a second time with Helvetas and implement Pilot 2 above in a second site.  Again, it is felt that this is a significant deviation from the core of the application and needs to be reviewed closely by the ECF Fund Manager.

Commercial Viability

As confirmed above, there are two completely different propositions being offered by Sunlabob in their proposal.  Taking these in turn:

Pilot 1: clearly, EDL needs to sign, and then deliver on their contracted obligations.  These are to extend the grid to connect to Sunlabob’s generator.  To purchase 24/7 generation from Sunlabob and to take over and manage the retail connections.  There are significant risks with this approach, and these are acknowledged in the application.  It is beyond the remit of this review process to assess potential commercial viability of the scheme.  However, clearly this will be informed by the feasibility studies for whichever of the 40 proposed sites Sunlabob agrees on with EDL.  Really, the ECF Fund Manager should review commercial viability matters once Sunlabob chooses a location.

Pilot 2: commercial viability here is entirely dependent on villagers upgrading their livelihood activities to be more energy intensive, higher value, and to generate sufficient returns to be able to purchase sufficient power from Sunlabob for the latter to reach commercial viability.  The application refers to previous success in this regard with Helvetas, but offers no detail.  Certainly, the review team recognise significant risks in such an approach, but also the potential upsides if such a scheme can prove successful (though we are sure this is not new, and would have preferred the evaluation process to have sought advice from an expert in this area).

Scope and scale of anticipated poverty impact

This project views the poor as consumers of electricity.  In terms of outreach, it expects that the villages they enter will display around 300 households.  They expect benefits to accrue across the population, with more discernible benefits accruing to those wealthier families who can consume more power, but spillover benefits to those who consume less / no power directly.  There is no doubt that access to reliable and affordable power is highly likely to be poverty reducing and that various dimensions of poverty can be addressed.

As Sunlabob has not chosen its sites for either pilot, it is not possible to comment on the poverty profile of the villages in question.  This should be done, and poverty impact baselines should be calculated against which progress can be measured over time.  It can be expected that poverty will likely be more entrenched in the village more remote to the national grid, than that village relatively close to the grid.  As such, this project offers opportunities to compare and contrast poverty reduction impact and dynamics between two (likely) very different villages.

In principle, if the models being tested under this project can be shown to be successful and replicable, it could contribute significantly to poverty reduction in Laos.

Systemic Change

In principle, this project has the potential to be highly transformational and systemic.  Again, referring to the two different models:

Pilot 1: if successful this would be the first demonstration of a partnership between the public and private sector to collaborate on extending access to electricity to currently un/underserved rural areas.  As confirmed in the proposal, around 40 sites have already been identified as potentially suitable for public-private investment in small scale electricity generation and provision.  The experience could inform government, donors, and potential investors on how to (or how not to) replicate and scale up the model across Laos.

Pilot 2: again, if successful, this pilot could contribute to wider systemic change for more remote rural villages through demonstrating viable models for placing self contained and commercially viable generating capacity.  Though, given the intensive value chain upgrading work, it is likely that this will need to demonstrate lessons to donors as well as government.

Level and type of innovation

The innovation being offered by this project comes in at various levels:

- It represents innovation at the level of the company itself;

- It represents innovation at the sector level more broadly by shaping what is believed to be one of, if not the first, public-private partnership of its type in Laos;

- It represents innovation also in approaches linking the provision of power to the upgrading of livelihood activities.

Demonstration effect

As confirmed above, the potential for demonstration is considerable in principle.  However, the project has been funded in a seeming vacuum of understanding (at least by ECF) of the emerging context of rural electrification in Laos.  The review team has seen a detailed (albeit as yet unsigned) Memorandum of Understanding between the IFC and the GoL / EDL, to test and roll out exactly the type of partnership being proposed by Sunlabob under their Pilot 1 model.  Under this agreement, the IFC would work with EDL to review and finalise the feasibility studies for identified sites.  It would support EDL technically and financially to support the extension of the grid towards these smaller scale hydro plants.  It would prepare and market (and perhaps even finance / co-finance) investor prospectuses for private investment in the generating schemes.

At best, the Sunlabob project can inform and shape this IFC led process.  At worst it could derail it and do irreparable damage.  To ensure the former, and mitigate against the latter, strong coordination and cooperation between all parties is urgently required.

Finally, the question of whether this is the only agreement of its kind with EDL still remains however.  Information provided to the review team via key stakeholders suggests there may already be a number of other MoUs established with EDL and various power companies for the roll out of hydro electricity in remote areas of Laos.  While the review team didn’t have time to investigate this thoroughly, if this is true, Sunlabob’s ability to be a demonstration model could be significantly affected by others leading lessons learnt from these projects.

Replication potential

As mentioned above, in principle, there is significant replication potential offered by this project.  But this will only happen if the project is structured in such a way so as to support and inform wider efforts of the GoL and its development partners (rather than undermine them).

In this vein, it is commented that Sunlabob are clear that they see this as a test case in helping them to raise finance directly, and to replicate the experience directly.  This might mean that they would see any information sharing and engagement with the IFC process as undermining their future commercial plans.  Conversely, the IFC’s expansion of activities in hydro-power could limit or catalyse Sunlabob’s potential to replicate this project, depending on the future direction of IFC support for hydro-power.  Again, the ECF Management team need to get a strong grip on such issues and work with AusAID to make this project a real success, informing wider replication.

Aide Memoire

Teamworkz

Overview of the Project

Whl.Travel is an e-commerce travel network of local grassroots tour operators promoting 300 destinations across 90 countries.  It started as a project of the IFC Mekong Project Development Facility (MPDF) running from 2002-2006, at which point it was spun-off as a commercial concern.

Each local partner owns a whl.travel franchise for their destination, being responsible for providing diverse tourism services.  Teamworkz is the franchisee for Laos.  It took over the franchise from the Laos Hotel Association in 2006, after poor performance of the latter body.

Currently, Teamworkz processes bookings and payments online through three existing destination websites, working on either a commission or contractual basis with a wide range of hotels, guesthouses and tour operators in Vientiane, Luang Prabang and Vang Vieng.  It has three booking partners through Lonely Planet.

The primary purpose of the ECF grant is to facilitate expansion of the existing business model to three new provinces in Laos.  These being Luang Namtha, Champasak and Xieng Khuane provinces.  Secondary aims of the project are a) to improve online visibility to the international tourist market; and b) to raise the profile and marketing ability of partner hotels and guesthouses working with Teamworkz.

Commercial Viability

The financials for this project are a little confusing.  The business is established and operational.  The project is the expansion of the existing business model to three new provinces in Laos.  The confusion lies in the financial forecasts which should be limited to the expansion part of the project, rather than the business as a whole.  It is the “new” service which needs to be commercially viable after three years.  Unfortunately, the financials “hide” the new service within the existing business.

The review team certainly find it highly questionable, and rather concerning, that a total of AUD 450,000 (ECF Grant plus matched contribution) is being invested in a business which after three years of operation generates a lowly USD 30,000 in gross revenue.

Looking at the existing business, Teamworkz operates in the three largest tourism destinations in Laos – Vientiene, Vang Viene, and Luang Prabang.  After several years of working in these three principal cities, Teamworkz earned a total gross revenue (i.e. income before costs) of circa USD 30,000 in the last year.  Whilst this has been increasing year on year, it remains at a very low level of profitability.  This income is supplemented by other income earning activities undertaken by the principals of Teamworkz.  For example, Lee Sheridan, is contracted for 200 days this year as a Tourism Consultant to the Dutch NGO SNV.

The new destinations being extended under the ECF grant are weaker tourist destinations (in terms of assets and numbers of tourists).  Hence, arguably, the profitability of these new sites will be even lower than that of the existing business.

Teamworkz estimate that they need to generate around USD 10,000 per month in hotel bookings for each of the new sites.  At current commission levels, this represents around USD 1000 per month in commission earnings.  This is seen as, in effect, a breakeven point.

Without existing baseline data it’s not possible to comment further in detail.  However, performance in the existing three cities is encouraging.  Growth in bookings through Teamworkz has grown from USD 76k in 2006, to USD 133k in 2007, to USD 254k in 2008, and is projected to reach around USD 300k in 2009.  Hence their commission has grown from 7.6k to around 30k over this period.

Scope and scale of anticipated poverty impact

This is the weakest part of the project application.  Arguably, there are three main ways in which Teamworkz could impact on poverty:

- Facilitating additional tourists to visit its destinations in Laos (i.e. more tourists visit Laos than would have done without Teamworkz operating);

- Representing efficiencies in the tourism sector, therefore freeing capital for higher investment in tourism assets in Laos; and / or

- Raising standards across the tourism sector, which underpins the future attractiveness and competitiveness of Laos tourism.

Unfortunately, the review team could find no evidence of the above impacts, nor indeed that anyone is really thinking in detail about just how, and by how much, Teamworkz can / might impact on poverty.  The proposition that tourism is naturally and unquestionably pro-poor is not a credible one if wider development experience is any comparator.

One might argue that given Teamworkz operates on commission it has an incentive to promote the higher cost hotels (which equal higher commissions) at the expense of smaller and cheaper hotels and, more likely than not, less prosperous hoteliers.  In such a case, the project might well be diverting tourists from smaller to larger operators leading to economic displacement.  There is no evidence that this is happening.  But, equally, there is no evidence presented to confirm that it is not.

One would have thought it quite possible for the ECF Country Manager to have ran a couple of focus groups with hotel and tour operators in each of the three current centres of operation to try to establish some of the growth and poverty impacts of Teamworkz.  Certainly, this is something which the ECF Managers will need to do as part of their monitoring and evaluation work going forward.

Systemic Change

The systemic failure here relates to the prohibitively high cost of market entry for Teamworkz into the three new provinces.  The lack of cooperation and standards in the tourism sector in these provinces, means that they cannot deliver the “information” which Teamworkz requires to launch its service to these provinces.  The market failure therefore lies in the lack of knowledge, skills and coordination of hotels and tour operators in the three new provinces.  These failures represent a prohibitively high cost of market entry for Teamworkz.  Hence the grant is being used to help Teamworkz off-set these high entry costs.

Unfortunately, the grant is being used to “buy” market entry.  It does not show how market entry costs might be lowered to facilitate expansion to more sites in the future.

The value of this project really lies in the additional positive impact it might have on the tourism sectors in each of the three new sites.  Though as mentioned above, such impact cannot be simply taken as a given.

Level and type of innovation

There is no innovation in this project at any level.  It is simply financing the expansion of the existing business model to new areas in Laos.  The grant does not finance innovation.  It simply subsidises market entry costs resulting, arguably, from failures in knowledge, skills and coordination of hotel and tour operators in the three new provinces.

Demonstration effect

As confirmed in their application, Teamworkz see this project as a route to secure its position as market leader in this sector within Laos.  It is not clear that anyone can / will compete directly with Teamworkz.  However, there are certainly many others in Laos who market to tourists through websites, and even offer on-line bookings.  Though these tend to be for individual companies (hotels / tour operators), rather than the more “marketplace” offer from Teamworkz.

Replication potential

As confirmed above, it is not clear that there will be direct replication.  But there will be an increase in e-marketing and e-bookings within Laos.  Though not necessarily inspired by, or in response to, Teamworkz.

Aide Memoire

Volcanic Earth

Overview of the Project

Volcanic Earth is a small but growing local manufacturer, wholesaler, retailer and exporter of naturally organic skin care products.  Its products centre on locally sourced materials including Tamanu oil, virgin coconut oil, volcanic ash and volcanic pumice.  Currently, export sales are limited to small, individual orders mainly to the end consumers around the world.

The application is based a massive expansion push from a small lifestyle business, to a significant exporter of natural skin care products.  Target markets are centred on Australia and New Zealand.  The marketing strategy is centred on moving from direct internet sales, to selling through a network of agency agreements in destination markets.

As the business grows, so does its volume of procurement of local inputs.  In the main this centres on Tamanu oil.  The company is also building a small scale coconut oil processing operation.  It intends to substitute currently imported coconut oil with that which it produces locally (using locally sourced coconuts).

Commercial Viability

There are two key commercial dimensions of this project.  Firstly, are the exponential sales growth figures justified and believable?  If they are, then does the company have the requisite business management expertise and ability to manage such a rapid business expansion?

Sales to the end of 2008 totalled AUD 14k.  Projected sales at end of Yr 1 are AUD 150k, to Yr 2 are AUD 570k and to Yr 3 are AUD 850k.  In other words, they are predicting a year on year growth in sales revenue over the three years of the project of 971%, 280% and 49%.

The ECF appraisal form describes such targets as “aggressive”.  The term “incredible” might be a term more favoured by the review team.

The growth is predicated on Volcanic Earth changing the nature of the way it does business.  It needs to move from direct internet marketing, to selling through a network of agency agreements in key destination markets.  The likely success, or otherwise of this is dependent on a range of factors.  Firstly, it depends on the ability of the management team to manage such a fundamental change in marketing direction.  Secondly, it depends on the competitive nature of the market into which they are pitching their products.  In this vein, the following concerns can be expressed:

- There was no market study referenced in the application showing the dynamics of the natural skin care products sector in their target markets.  The review team are not specialists in the natural skin care products market.  However, it knows enough to be sure that it is a highly competitive, mature and international market.

- The unique sales points (USP) of Volcanic Earth’s products are not given.  Hence, their marketing strategy does not talk about how their products will expand / compete for market share with other natural oils based products.  What is different about Volcanic Earth and how does this meet a latent need in the destination markets of Australia and New Zealand.

- The application did not demonstrate any clear orders or agency agreements which might overcome the risks and lack of information referred to above.  Showing “cold” emails from a range of unqualified “leads” does not offer much comfort here.

The second area of concern centres on the business management capacity of the owners to effectively guide such rapid expansion.  The CV’s of the principals were offered as part of the application.  They do show some previous business management experience.  However, one might question the frequency with which they have moved from venture to venture, and the fact that neither has any business background in the natural skin care products market.

The principals of Volcanic Earth moved to Vanuatu to, in their words, retire.  They started Volcanic Earth four years ago.  In its last year of trading it achieved sales of AUD 14k, and posted an operating loss of around AUD 3k.  The rate of growth predicted over the next three years (under the project) would represent a significant deviation from the performance of the firm in previous three years.

As a final point, at the time of the ECF application, the business had net assets of AUD 33k, the majority of which comprises stock.  The cash in the business at the time stood at AUD 4k.  The review team finds it mildly astounding that the ECF made a grant award of AUD 190k into a business worth a mere fraction of this, and certainly without any clear market analysis which might offer credible support for the exponential growth projections.

Scope and scale of anticipated poverty impact

The pro-poor linkages are clearly defined in the application.  As Volcanic Earth grows its sales it will need to buy more locally produced raw materials.  In the main this centres on the purchase of Tamanu oil, and to some degree raw coconuts.

Whilst not described in the application (in detail), it is understood that Volcanic Earth buys Tamanu oil from a processor on the island of Malekula.  This processor in turn buys nuts (from raw to part cured) from rural communities (in the main, it is women who evidently trade the nuts).  The review team did not visit Malekula, and so cannot comment in detail on the relations and dynamics of this supply chain.  However, one would have expected more detail on this to have been provided (or demanded) in the application.  For example, we understand that Volcanic Earth is just one small buyer of oil from the pressing facility, who we are told are regular exporters of raw oil.

On this basis one would be concerned to know more clearly about the volumes and operations of the pressing facility, to be sure that, for example, increased purchases of oil from Volcanic Earth genuinely represents increased production of oil from the press, rather than displacement of existing volumes.  If the latter was true, then there would be no additional income benefits to rural communities who supply the nuts.

The application states that around 50kg of nuts is required to produce 5 litres of oil.  It is not clear how much oil will be required to deliver on the sales targets listed in Volcanic Earth’s application.  However, such an estimation is fairly critical if one is to be clear that there are sufficient nuts, and / or labour to collect nuts, and/or space processing capacity, to deliver the volumes required.

The above represent a number of areas where the current monitoring and evaluation framework likely needs revisiting.

Systemic Change

This project is not concerned with tackling any market failure.  It is simply about financing the rapid expansion of a small, arguably life-style business into something more substantial.  This might be argued as valid on strategic grounds if the expansion offered a real and substantial impact to the lives and livelihoods of large numbers of rural people on Malekula.  However, such a case is not sufficiently made.

Level and type of innovation

Any innovation resides solely in the changed marketing practices the company is going to have to succeed with in moving from direct internet sales, to agency distribution agreements in destination markets.

As regards motivation, the company is firmly motivated by commercial business reasons.  However, time will tell whether the grant facilities them to grow, or simply encourages them to indulge in small business largesse.

Demonstration effect

At best, and if successful, this project might serve as a demonstration to show that Vanuatu can host larger and successful businesses in the international natural skin products (and/or related) market.  However, it is not clear that such a thing needs demonstrating; and as such it is not clear to whom such demonstration should be targeted, nor hence how such a lesson should be disseminated.

Replication potential

It is too early to say much on this point.  However, with such limited innovation potential, and no clear demonstration need or focus, there can be no clear gauge of replication potential.

The PDD uses the term “market failure”.  This is too absolute, and hence we prefer to talk in terms of the more relative concept of “market weakness”.

By systemic we refer to the market system within which businesses and the poor co-exist.  This equates to the Business Enabling Environment (BEE) which the preferred term of the PDD.

Taken from Page 9 of the PDD.

The PDD acknowledges that replication might well not happen spontaneously.  Rather it is more likely that the Fund Manager will need to actively facilitate replication through wider awareness raising, lesson learning and experience dissemination activities.

This is clearly articulated on Page 30 of the PDD.