|  |  |  | AusAID |
| --- | --- | --- | --- |
| Enterprise Challenge Fund – Mid-Term Review |  |  |  |
| Annex 4: Efficiency |  |  |  |
| Sarah Barlow |  |  |  |
| November 2009 |  |  |  |
|  |  | Suite One, 4 Saddler Street Durham DH1 3NP United Kingdom Tel: +44 191 383 1212 Fax: +44 191 383 1616 Email: global@ springfieldcentre.com |  |

# introduction

The efficiency of a programme is a measurement of its outputs and outcomes in relation to its inputs. Efficiency measures therefore consider whether the resources available to a programme were used in the best possible way to maximize the likelihood of achieving the programme’s strategic objectives. As the ECF project does not have a logframe, the review team has used the strategic objectives suggested in the project’s design document.

In summary the following overarching issues emerged from the assessment of ECF’s efficiency:

- Sound administration: managing a challenge fund in nine countries requires good systems and efficient administration. ECF has established efficient administrative systems, which if required will serve as a sound basis for expanding the programme.

- Clarity of strategic framework: as discussed in earlier sections of this report, there is a significant confusion and/or misunderstanding as to what the project is trying to achieve. This has had a negative impact on efficiency at several levels: from ensuring the appropriate staffing mix, to establishing project evaluation criteria which assess projects in light of the Fund’s strategic objectives, to the format and content required in project application forms. Ultimately this has directly impacted the quality of the projects.

- Ownership of vision and accountability: No person, body or organization has clear ownership of the vision for ECF, or accepts responsibility for the programme’s success or failure. In normal circumstances, this responsibility would be assumed by the Fund Manager, but as the Fund Manager has little influence over which projects are approved, it is unwilling to take on this overall responsibility. Likewise, while grant allocation decisions are made by the assessment panels, the panels have limited influence over the other aspects of the Fund. As a result there is a significant accountability gap with no-one clearly responsible for the quality and performance of ECF, and the projects it supports.

- Inflexible systems: management of the ECF, particularly as this was a pilot phase, has been fairly inflexible; the Fund Manager should have been allowed greater opportunity to try out different approaches and systems, and make better use of the pilot phase.

- Role of the Fund Manager: The Fund Manger began the pilot phase with a hands-off role. While this changed slightly during the course of the pilot phase, it is a good example of the approaches which should have been adapted, and tested, further. Increasing the involvement of the Fund Manager in the identification and development of projects, that is taking on a more facilitative role, would have been in keeping with international experience, and would probably have improved the efficiency, as well as effectiveness of the programme.

Assessing a programme’s efficiency involves assessing the use of resources, the processes followed by the programme, the timeliness of activities in relation to agreed work plans, and the management and governance arrangements. The review team assessed ECF’s efficiency by answering the following key questions, adapted from those suggested by OECD’s DAC, and by making comparisons with relevant and similar grant allocation funds as appropriate and where information is available.

# Grant fund management processes

Do the grant fund management processes maximise ECF’s impact and the likelihood that it will achieve its strategic objectives and purpose? In order to answer this question, we have assessed each of the key steps in the ECF management process, as follows:

## ECF Marketing:

### Summary of the marketing approach:

ECF’s marketing approach has two overarching objectives: a) to raise awareness of the ECF amongst key stakeholders in the private sector and Government; and b) to ensure that these stakeholders understand the key objectives of the ECF and what it is looking for in projects to support. Awareness on its own is not sufficient, as it will ensure a high level of applications, but a relatively low proportion of these will be suitable.

The Fund Manger developed a marketing strategy at the start of the programme, but in practice it was further refined and adapted during the pilot phase. Marketing of the fund was initially undertaken through country launches, limited press advertising and face to face meetings. These activities were led by the Fund Director and Country Managers, and were supported by the ECF website which provides background information on the programme as well as information on how to apply for potential applicants. Following Round 1, the launch of which was reportedly fairly rushed, most Country Managers started to market ECF more actively with presentations to private sector organisations, and mini launches at key locations within their countries. For example, the Country Manager in Vanuatu held launch meetings in at least two different locations in the country, and followed this up with a series of one to one meetings with those who expressed interest in the project after the launches.

ECF messages are relatively complex: explaining a) what the fund is aiming to achieve, beyond allocating grants for businesses; b) what it is looking for in applications; and c) the processes and how to apply, all require a fair amount of detail and explanation. As such, ECF’s increased use of face to face marketing through launches, road shows and one to one meetings, supported by minimal advertising to raise initial awareness, appears to be entirely sensible and born out by international experience with similar funds. The Fund Manager is fully aware that in the event of further Rounds, they will be able to use the existing portfolio of projects, and project recipients, to help explain what the ECF is all about. To this end they have developed initial case studies of all approved project, which can be expanded to incorporate progress and results, as and when possible.

### Impact from ECF Marketing Efforts:

The review team did not have the time to undertake a comprehensive assessment of awareness and understanding of the ECF in the target countries. Anecdotally, it appeared that awareness of ECF was generally fairly high amongst the key stakeholders interviewed by the review team. However, in some cases, for instance in Fiji, it was surprising that important organisations, such as the Investment Promotions Bureau, were not aware of the ECF.

Genuine understanding of the ECF, its objectives and modus operandi, was fairly patchy in the countries visited by the team. Stakeholders, including grantees, regional panel members and Country Managers, often struggled to explain the rationale for the ECF and what it is trying to achieve. This confusion is likely to be directly attributable to the absence of a clear strategic framework for ECF, as discussed in the main body of this report.

While awareness of the ECF is reasonably high, it seems likely that strategically important organisations and businesses are not yet fully conversant with the Fund, and that if the ECF is to continue, a greater level of pro active and targeted marketing will be required to ensure that all potential applicants are fully aware of, and genuinely understand, the Fund.

However, it’s important to note that there is some, albeit slightly mixed, evidence to suggest that the more focused marketing approach employed by ECF in the second and third Rounds, is helping to improve the overall quality of applications received, especially in the Pacific. Table 1 below records concept notes (CNs) and applications received in each of the three ECF rounds for all nine countries.  This shows: a) a significant and steady increase in the proportion of eligible PCNs received from R1 to R2 and to R3; b) a lower absolute number and proportion of PCNs were approved and invited to submit applications as Rounds progressed; and c) there was a dramatic increase in approvable applications from R1 to R2, and in the conversion rate from R1, to R2, to R3. It should be noted that comparisons/trends from R2-R3 are more meaningful as R1 was, as previously noted fairly rushed.

Table 1: Concept Notes and Applications Received and Approved in Rounds 1-3

|  | Round 1 | Round 2 | Round 3 | Totals |
| --- | --- | --- | --- | --- |
| CNs received | 217 | 181 | 125 | 532 |
| Eligible CNs | 125 | 147 | 115 | 387 |
| % of CN eligible | 58% | 81% | 86% |  |
| CNs approved | 37 | 35 | 24 | 96 |
| % of eligible CNs approved | 30% | 24% | 20% |  |
| Applications received | 29 | 30 | 22 | 81 |
| Projects approved | 2 | 10 | 11 | 23 |
| % Applications approved | 6% | 33% | 50% |  |

[Source: ECF Management Statistics]

Improvements in conversion rates from concept note to approved applications, as the Fund Manager gains experience and the marketing work starts to take hold, are to be expected for this type of programme. The more projects supported, the more stakeholders are able to believe in the programme and to understand the type of projects likely to be awarded grants. There are several possible reasons that might also explain the overall trend of improved conversion rates of initial concept notes to approved applications. These include a significant number of repeat applications in Rounds 2 and 3, from bidders who had been told to revise their applications in a specific way, and then re submit; as well as a possible increased readiness by panel members in the last Round, to approve projects which they knew could not be re submitted in later Rounds. Notwithstanding these possible contributory factors, it seems likely that the primary reason for the increase in the proportion of applications approved is applicants’ better and growing understanding of what the ECF panels are looking for in an application (even if the panels assessment criteria do not closely reflect ECF’s strategic objectives).

There is a worrying regional bias in approved applications; 74% of the projects funded, and 77% of ECF funds, have been allocated to the Pacific islands. Table 2 below summarises the projects, applications and concept notes achieved by country. The Philippines, East Timor, and Indonesia were awarded one, one and no projects respectively. This is particularly surprising as the project design team had been concerned that the Asian countries, with large populations and deeper economies, might end up with a disproportionately high number of projects compared to the Pacific. The reverse has taken place. As Table 2 demonstrates, Indonesia and the Philippines submitted a relatively high number of concept notes, which suggests that awareness of, and interest in, ECF was reasonably high.

The review team did not visit any of the three countries with particularly disappointing project approval rates, so it is not possible to be sure exactly why they have performed so poorly. Possible explanations include: a) the project wasn’t managed effectively in these countries with insufficient marketing, and support to applicants to ensure projects were of an adequate standard; b) a relatively strict regional panel covering applications from these countries (although only 44% of CNs and 34% of applications for these countries were for budgets under $200,000 and therefore assessed only by the Regional panel);  c) the fact that the International panel has more experience with the Pacific and therefore is more likely to approve risky projects in this region than in Asian countries; and d) the Fund is not sufficiently relevant for the economies and private sector in these countries. Clearly the first three possibilities are relatively simple to address, and the last is more fundamental. Before any continuation of the ECF, the reasons for the low numbers of approved projects in these countries should be explored in more detail.

Table 2: Summary of Concept Notes, Applications and Projects by Country in Rounds 1-3

|  | CNs Received | Applications Received | Projects Awarded |
| --- | --- | --- | --- |
| Cambodia | 36 | 6 | 3 |
| East Timor | 12 | 4 | 1 |
| Fiji | 59 | 12 | 3 |
| Indonesia | 59 | 9 | 0 |
| Lao PDR | 19 | 5 | 2 |
| Papua New Guinea | 71 | 16 | 4 |
| Philippines | 80 | 13 | 1 |
| Solomon Islands | 22 | 7 | 5 |
| Vanuatu | 25 | 7 | 4 |
| Multi-region | 8 | 2 | 0 |

[Source: ECF Management Statistics]

### Role of the Fund Manager in the marketing effort

The Fund Manager has adopted a fairly hands off approach to the marketing of the fund and has not been actively involved in facilitating the development of appropriate projects. For example, on the whole, Country Managers, do not perceive researching, identifying and approaching possible ECF grantees and areas of intervention as part of their remit. Although there are dangers with the Fund Manager adopting this kind of pro active role, on balance and given experiences from other Challenge Funds, it seems likely that more effective projects will emerge if the Fund Manager takes on a more facilitative role than it has, on the whole, to date.

Box1: Increasing the role of the Fund Manager in BEST-AC , Tanzania

BEST-AC is an advocacy challenge fund in Tanzania, which provided grants to private sector organisations to implement advocacy projects aimed at improving the business environment. BEST-AC was initially run as a fairly standard and formulaic challenge fund; the Fund Manager role was limited in both marketing the Fund and identifying projects, and also had little opportunity within the grant management processes to facilitate the development of sound projects. A mid term review in October 2007 recommended the role of the Fund Manager be changed dramatically to take on a much more facilitative role, involving active identification of potential projects and partner organisations, and the provision of support to applicants to help them develop sound proposals and implement those approved by the Project Board. A follow up review 18 months later found that this new approach was one of the main factors in the improvement of project proposals being presented to the Project Board for appraisal.

[Source: BEST-AC independent review reports from October 2007 and May 2009]

An expanded, and more proactive, role for the Fund Manager is a theme that runs through several sections of this discussion of efficiency. One of the dangers with a more proactive role for the Fund Manager is that it can result in perceptions of bias. In fact we heard some discussion of this issue in at least two of the countries visited. Given the small communities in many of the targeted countries, this is to be expected to some degree, but transparency and efficiency of the overall approval process is clearly very important in avoiding any real or apparent bias. If the approval process is seen to be making its decisions relatively independently from the Fund Manager and the donor, these accusations should be baseless and relatively easy to rebut.

However, it should be noted that many projects are run by ex-pats. In Vanuatu, three of the four approved projects were run by ex-pats (the 4th was run by a large Australia based company, Carnival). None of the approved projects was owned or managed by a ni Vanuatan. In addition, the Vanuatu Country Manger is an ex-pat and at least one of the panel members representing Vanuatu on its Regional Panel is an ex-pat. In Vanuatu, a letter from a local MP was published in a local newspaper complaining about the absence of locally owned projects receiving ECF funding. A common view seems to be that there are not any ni-Vanuatan businesses with the capacity to develop and implement a successful ECF project. However, in the review team’s opinion, at least one of the ex-pat run businesses in Vanuatu that received a grant, did not demonstrate a strong enough track record (financially or in terms of marketing ability) to justify the A$190,000 ECF grant it was awarded. This opens up the ECF to accusations of double standards. The review team is not questioning the potential developmental impact, in principle, of projects developed by ex-pat owned businesses, but there are two clear dangers for ECF in supporting ex-pat run businesses exclusively in one country:

- that there will be significant political fallout for AusAID and/or ECF, from the lack of locally owned projects; and

- that only supporting expat owned businesses will in effect support and possibly exacerbate the unequal capacity and resource base of expat and ni Vanuatan businesses, which could have developmental and political consequences.

## ECF Application Process:

### Summary of the application process:

The ECF follows a fairly standard Challenge Fund application process. There have been three ‘Rounds’ of applications, which, in turn, have two stages. Concept notes are submitted by applicants and initially reviewed by a regional panel and, if applying for grants of more than A$ 200,000, by an international panel. At this stage they are either rejected, invited to submit a full application, or in some instances applicants are rejected but invited to re submit with key changes in the application, in the next Round. Full applications are reviewed by the same panels and again, either rejected, approved or in some cases invited to re apply with certain changes to the application. Each step in the Round is guided by fairly strict deadlines. It takes approximately 10 months for a successful project to be approved, longer if it requires a grant over $200,000 and is forwarded to the international panel for consideration.

The two stage application process (concept note and application form) is in keeping with international good practice and is appreciated by applicants.

### CN and Application Forms & Guidance

Applicants are provided with standard formats for the concept note and applications, along with guidelines and a set of the assessment criteria. All of these are available from the Country Manager and/or can be downloaded from the ECF website.

While many applicants interviewed by the team found the application form challenging to complete, none thought it overly complex or taxing given that substantial grants were the end goal. The main areas of difficulty were the financials and the sections requiring analysis and comment on the intended poverty impact of the projects. While it is entirely appropriate for the applicant to be required to supply the former, it is questionable whether a business person will be able, or is the right person, to provide the necessary poverty related information (especially when estimating the number of poor people likely to be impacted, their level of poverty, gender and so forth). Linked to this, all applicants found the section on BEE (Business Enabling Environment) difficult to complete. None of the applicants interviewed (nor most of the panel members and Country Managers interviewed) had a clear understanding of what BEE really meant.

A further and more fundamental problem with the PCN and application forms is that they do not guide applicants to present projects which meet the ECF Purpose - that is there is no requirement for applicants to describe a) the market weakness the project aims to address, the innovation it hopes will address this weakness or the potential for replication. It is clear from the projects assessed by the review team (as detailed in the project summaries in Annex 3) that they were not conceived with these strategic issues in mind, and the majority are unlikely to contribute to the achievement of the ECF’s Purpose. This is clearly a significant weakness, which can be traced back to the absence of a strategic framework for the programme as a whole, and has been commented on in the main body of this report.

### Role of the Fund Manager in the application process

Initially the Fund Manager provided minimal support to applicants, maintaining a strictly hands off role. This was intentional and intended to ensure no bias or influence over applications. In the 2nd and 3rd Rounds, some of the Country Managers, and the Fund Director, became more involved in the application process, providing comments and guidance to selected applicants on draft submissions.

The ECF team believes that its involvement has resulted in better quality applications, both in terms of the way they are presented to the panels, and more substantively in terms of the quality of the projects themselves. This is born out by the higher approval rates for applications submitted in Rounds 2 and 3, and also by experience with international challenge funds, which suggests that a more facilitative role for the Fund Manager tends to result in improved applications and ultimately more effective projects.

Some applicants opted to hire service providers to assist with developing their applications, primarily for either the financials or with the development elements of the application form. Again, while it’s not possible to know exact numbers of those that took this route and those that didn’t, it appears that those who used the services of a consultant tended to have better chance of getting their projects approved.

### Grant Management Systems

The systems put in place by the Fund Manager for managing the grants from application to implementation appear to be extremely efficient. Most applicants and all panel members expressed satisfaction with the systems. One improvement could be to the financial components of the application forms, which currently allow applicants to provide inconsistent information, a mistake, which can result in significant delays to the project, if the application form has to be re submitted.

## Process for Assessing Project Proposals:

### Summary of the process:

Concept notes and application forms are all submitted initially to regional panels for consideration. There are three regional panels covering three regions (the Pacific, Asia, and Lao/Cambodia). Regional panels make final decisions on all proposals with budgets under A$200,000. Concept Notes and Applications with budgets higher than this are submitted to the international panel together with the recommendations from the relevant regional panel.

The two stage panel assessment process is designed to ensure adequate local as well as technical appraisal of project proposals. Regional panels each have a minimum of two country representatives from the countries they cover as well as technical expertise in relevant sectors (agriculture, agri business, investment and so forth). The international panel is made up of international expertise in investment management, commercial finance as well as some agriculture and tourism expertise. Membership includes those with experience of AusAID and the IFC and several members also have experience of working in the Pacific and to a lesser degree the Asian countries covered by the ECF.

All eligible Concept Notes and Application forms are reviewed by the panels; the Fund Manager does not screen, rank or weed out proposals, which have met the basic eligibility criteria. As such the panels have had to review a considerable number of proposals, particularly at concept note stage. Panel members are provided with the applicants’ submission (concept note or application) and a written submission by the County Manager, recommending either approval or rejection. The ECF Fund Director, or on occasion his replacement from the ECF team, sits in at all the panel meetings; he is not required to brief the panel but is sometimes asked to provide additional information or clarifications. The comments provided by the Country Managers are usually based on the written submission of the bidder, supported by personal knowledge of the bidder and the bidder’s business reputation, if he or she is known to the Country Manager.

The panels use a standard set of assessment criteria to assess, mark and rank proposals. These are summarised in Box 2. There is no weighting applied to the criteria, although many of those interviewed commented on the particular emphasis applied by the international panel to the commercial sustainability and quality of the financial information in project submissions.

Box 2: ECF Project Assessment Criteria (abbreviated)

- Description of the project – are its objectives etc clearly defined

- Commercial Sustainability – likelihood that proposed project will be sustainable within 3 years and credibility of bidder’s track record for achieving this.

- Contribution to ECF objectives – likely real improvements in incomes and livelihoods of poor people; likely positive impact on women; likely extent of social benefits in proportion to social gain; anticipated contribution to capacity building in local market; likelihood of being replicated; extent to which helps country harness its natural resources on sustainable basis; likely positive impact on conditions for doing business

- Relevance of ECF funding – bidder’s dependence on ECF funding and bidder’s contribution to the project

- Risk – adequate identification of risk and appropriate risk management strategies proposed.

- Capability to implement the project – quality of business case, credibility of bidder, appropriateness of external expertise.

- Longer term Sustainability – likelihood of project remaining commercially sustainable beyond ECF grant

- Financial assessment – sound financial projections; appropriate sharing of costs and benefits between stakeholders; level of new private sector resources mobilized

- Monitoring and Evaluation – extent to which indicators and monitoring mechanisms are clear and appropriate.

### Efficiency of the assessment process:

Most regional and international panel members attended training provided by the Fund Manager, which effectively covered the modalities of the ECF. However, the bulk of those interviewed had fairly confused perceptions of the strategic objectives of the Fund. This is not surprising given the absence of a strategic framework and the assessment criteria, which do not directly relate to the programme Purpose.

Regional and International Panels receive insufficient information with which to assess the project applications: the majority of panel members interviewed as part of the review suggested that they would have liked the opportunity to visit the bidders, see the businesses and as one regional panel member expressed it ‘see the whites of their eyes’. While this is clearly not feasible for panel members, it is a role that the Fund Manager, through its Country Managers, Fund Director, or other team members could perform, at least for those bidders invited to present applications. This would be entirely in keeping with commercial investment panels, which need to know that someone has officially and independently assessed the business and project, which is going to receive the investment. The poor level of project appraisal and commentary on project applications by the Fund Manager represents a missed opportunity to provide a more in depth assessment of the bidder’s business and project proposal on both basic due diligence criteria, and more substantive issues relevant to ECF criteria. In fact, it is clear that Country Managers do not always visit bidders and their businesses before a full application is reviewed by the panels. As it stands, panel members suggested that they make the best decisions they can, with the information available to them – but that this is not usually enough.

The rationale for regional and international panels is questionable, particularly if the local knowledge and business appraisal role were to be more adequately filled by the Fund Manager. Two panels add to the cost of the programme, and for projects with projects over $200,000, to the time it takes to assess project proposals. If the programme were to continue, an amalgamation of the international and regional panels into one assessment panel seems more appropriate.

Non payment of international panel members is counter productive: Currently the international panel members are not paid for the considerable work involved in this role in terms of preparation, travel and panel meeting attendance. Non payment of fees is one of the reasons given for the three resignations of international panel members, and is particularly an issue for those members who are not representing their organisations (and therefore not receiving their usual salaries). Not paying panel members, a practice mandated in the contract between AusAID and Coffey, runs counter to international experience; panel members involved in other Challenge Funds, e.g. the ACF, are usually paid a fee which, while often less than their normal remuneration, at least acknowledges the time and effort they are required to put into this role.

As with the application forms, the assessment criteria do not ensure approved applications contribute to the achievement of ECF’s purpose: Although one of the criteria refers to the proposed project’s contribution to ECF objectives, there is in fact very little cohesion between the objectives cited, and ECF’s overall Purpose. The application form does not describe, and the criteria do not require the assessment panels to consider, the broader market weakness the project is aiming to address, whether the grant is being used to test or stimulate an innovation to address this weakness, and if there is the potential to demonstrate a new way of working (at the firm, or sector or country/regional level) which might be replicated by other market players, and therefore achieve deeper systemic change affecting a larger number of people. There is one mention of replication in the assessment criteria, but without considering how this replication might deliver systemic change to the way markets work, and without any consideration of innovation (which was unfortunately removed from the criteria early in the pilot phase) this is not sufficient. The assessment criteria do not therefore enable the assessment panels to consider and assess the projects in the context of the overall purpose of the ECF. Add to this the fact that most of the panel members interviewed by the review team, did not consider innovation, market system change and replication, to be key considerations for the projects, and it is not surprising that the majority of the projects funded are not fully supportive of the overall ECF purpose.

The strictly delineated roles of the Fund Manager and the assessment panels have resulted in an ownership and accountability gap. The Fund Manager has adopted a hands-off role, which gives it very little influence over which projects are approved; as such it does not see itself as responsible for the quality of the projects submitted for approval, or indeed for their implementation progress and ultimate impact. The grant allocation decisions are made by the assessment panels, but the panels have limited influence over the other aspects of the Fund, and panel members interviewed do not see themselves responsible for the overall impact of the projects or the programme as a whole. As a result there is a significant accountability gap with no-one or body with clear responsibility for the quality and performance of ECF and the projects it supports. This is a fundamental problem.

## Process for monitoring and supporting project implementation

A full assessment of ECF’s approach to monitoring and evaluation is provided in Annex 5. However there are two aspects of the monitoring work, post project approval, which are specifically relevant to discussions of the efficiency of the programme. These are:

- The monitoring of basic aspects of project implementation, i.e. due diligence, to ensure that the approved grants are spent in accordance with the project agreement, equipment is used as agreed and in general the business and grantee are following the course they presented in their application.

- Beyond this basic due diligence, there is a role for the Fund Manager in providing relevant assistance and advice to the grantee to facilitate effective implementation of the project. This might involve the provision of advice, or directing the grantee towards sources of relevant technical expertise, possible partners and so forth.

Currently, the first of the above monitoring roles appears to be included in the role of the Country Managers and those the review team spoke to, see this as part of their remit. At this stage it is too early to comment on how effectively it is being enacted, as only a handful of projects have recently got underway. However, the second, and very important role, is not generally viewed as being part of the Fund Manager’s remit; as it stands, once grantees have received funding, they are left on their own in terms of effectively implementing the project. This is a missed opportunity to achieve maximum impact from the projects.

# suitability of management arrangements

## Staffing

The Fund Manager is made up of a team of three full time, and two part time Coffey staff, based in Australia, supported by one external M&E specialist, also based in Australia, and nine part time Country Managers based in each of the target countries. This is a larger staff contingent than originally envisaged, and specified in the AusAID/Coffey contract. In particular, the contract specified that the Fund Director would be a part time position (13 months during the 6 year project period) which in the review team’s assessment is unrealistic, and would be counter to the usual LoE of similar positions in international Challenge Funds, most of which have full time Directors.

While the staff interviewed by the review team all appear to be highly competent and dedicated, it is clear that all technical private sector development expertise is centered in the Fund Director, and the remaining staff appear to be focused on administration functions. In future it may be worth considering including some contracted in specialist expertise to support the Fund Director in priority areas for the ECF, particularly if the Fund Manager as a whole takes on a more facilitative role.

The ECF Fund Manager has questioned the value of having nine Country Managers, at some considerable expense, and whether it would be more beneficial to use the funds for regional managers with on average greater levels of expertise. This seems sensible.

## Team work

The review team was not able to form a comprehensive assessment of ECF team work dynamics, but it was clear that those we met worked well together. We have some concern regarding the disparate geographical location of the team (based in Sydney, Adelaide and Canberra), which is not particularly conducive to maximising productivity, especially when none of these locations is in the 9 target countries. Linked to this was a sense that this is very much a Coffey project, partly branded as such, largely located in Coffey, not ECF, offices, and that, with the exception of the Fund Director and the M&E Specialist, the staff were Coffey employees before the project started. Ideally the team should act and feel like an ECF, as opposed to a Coffey, team.

## Governance

The assessment panels have no strategic governance remit and this role is essentially provided by AusAID. AusAID and ECF management meet formally for a performance review annually and informally every quarter. There is little opportunity for input by local stakeholders in the 9 targeted countries to provide input to the strategic oversight of the programme.

## Flexibility

Despite this being a pilot project, it is clear that the Fund Manager did not feel it had much flexibility to test out and adapt different approaches during the course of the pilot phase. There were some adaptations, but not nearly as many as one would have expected, and given the Fund Manager’s recognition that some components were not working as well as they could. The AECF Fund Director has a much higher degree of flexibility and reported that they have changed things around, run special windows, changed rules etc, with a relatively high level of autonomy. The limited flexibility is in part due to the prescriptive contract between Coffey and AusAID, which specifies in a fair amount of detail, the grant management process and the activities and staffing of the Fund Manager.

# Cost effectiveness

Were programme funds used effectively to achieve ECF objectives? There are several important points to make in relation to ECF’s cost effectiveness:

The ECF budget was largely used in line with activities agreed in the Coffey/AusAID contract. However, as discussed in the main body of this report, these activities were not always the best route for achieving the overall strategic objectives and ECF Purpose.

As mentioned above, a disproportionate amount of the grant funds (77%) were allocated to projects in the Pacific at the expense of projects in Asia, particularly Indonesia, the Philippines and East Timor. The Fund Manager has attempted to assess why so few ‘good’ projects emerged from these countries, but this needs to be assessed more rigorously, including revisiting whether there is sufficient demand for the ECF, before continuing with a similar programme in these countries.

A common means for assessing the efficiency of funds used to implement a challenge fund is to assess the proportion of the total budget that is used for administering the fund/overhead costs. Comparisons with other funds are useful, but need to be treated with caution; the overall size of the fund, the number of countries covered, local costs and capabilities, and any differences in the objectives of the funds and their target audiences, all can have a significant impact on these ratios. Not withstanding these cautionary health checks, international comparisons can be useful. Table 3 compares ACF with three other large regional/international challenge funds, all funded by DFID. The comparison shows that the cost of implementing ECF is slightly higher than the other funds, but given its smaller overall size this is not unexpected.

Table 3: Comparing the Costs of Implementing Challenge Funds

| Challenge Fund | % of Budget for Implementing the Fund | Total Grant Fund** | Coverage |
| --- | --- | --- | --- |
| ECF | 27%* | 14,500,00 (Aus$) | 9 countries |
| AECF | 20% | 40,000,000 | 54 countries |
| BLCF | 20% | 16,600,000 | International |
| FDCF | 22% | 32,000,000 | Africa and South Asia |

[Sources: ECF Management Statistics; Correspondence with AECF Fund Manager; BLCF and FDCF reports (Enterplan).]

Notes:

* This figure has been calculated from the following information from the budget for the 6 year project period:

management fees:	3,832,970

reimbursables:	1,217,666

performance bonus:	350,000

Subtotal:			5,400,636

Grants				14,500,000 (of which 13,307,881 had been committed at the start of the review)

TOTAL				19,900,636

Cost of implementing the fund: 27.14%

** All figures are in US$ except when noted. The US$ to Aus$ exchange rate is currently 1: 1.12

In addition, to the above broad comparison of costs, the review team considered the budget and expenditure breakdowns to date and tried to identify if there were any particularly high costs, or expenditure for activities that in reality had not contributed much to the achievement of ECF objectives. The following budget items are worthy of mention:

- Assessment panels: these cost a total of A$466,726, which breaks down to an average cost per panel meeting of approximately A$55,000. Panel member and Fund Manager travel are particularly high proportions of this cost at approximately A$210,000 and A$140,000 respectively.

- Staff costs generally seem very high at A$3,378,089, especially given the comments above regarding the staff mix.

- In particular, Country Managers (including their travel and training costs) are budgeted and likely to cost, a full A$ 448,000. This seems high given their limited role in assessing projects, applicants and providing project implementation assistance.

- In terms of superfluous costs, the much misunderstood BEE assessments, which cost A$ 32,000 are worthy of mention. The review team was unable to find anyone who considered these useful, including within the ECF team and AusAID. However a more detailed and closer assessment of constraints and opportunities within the key sectors at country level might well have been more beneficial and a good use of this budget line.

The review team also considered the financial management of both the overall fund and the individual grants:

- Overall ECF Fund: the Review did not undertake an audit of the ECF funds, although these are undertaken regularly, and was only able to examine the files and financial management systems fairly briefly. However, from this process, it seems that the ECF financial management systems are efficient and effective. The ECF team was able to answer all our questions quickly and easily; the team undertakes useful analysis of the ECF financials and its non financial performance which has not only been useful for this review but will be useful if the fund expands.

- ECF Grants: ECF manages grant payments through a tranche payment system with payments made in arrears. There is some flexibility built in to this system to take account of the different needs of different projects. Grantees appear to understand the system. ECF, with contracted legal expertise, has developed a contractual template, which it amends slightly for each grant. This contract then governs the financial arrangement with the grantee. A true test of the validity of this arrangement will be if/when something goes wrong, such as a grantee mistakenly or willfully misusing grant funds or goods bought with grant funds. Fortunately the systems have not been put to the test in this way yet, however the review team had some concerns regarding whether the current system is as rigorous as it needs to be. For example, the contract between Coffey and MCS, a grant recipient in Vanuatu, does not stipulate how long the ship (75% of which was purchased with an ECF grant) should be used on the new route being tested by the project. In effect there is nothing to stop MCS switching the ship to a more profitable route (see Annex ? for more information on this project)

# AusAID and Coffey Management Issues

The document which provides the basis for both the management of ECF and relationship between AusAID and the managing agent, Coffey International Development, is the Contract. The review team assessed Schedules 1, the Scope of Services, and 2, the Basis of payment, of this document. In general, the Contract is very prescriptive, and covers Coffey’s activities in a great deal of detail. There are several problems with this:

- In combination with the absence of a clear strategic framework, this level of detail at the activity level has led the Fund Manger to focus on implementing activities, rather than achieving outcomes. It may also have contributed to the Fund Manager’s reluctance to be accountable for the success or otherwise of the programme and the projects it supports.

- The contracts’ prescriptive nature has contributed to the Fund’s limited flexibility, which has constrained its ability to test new approaches, and make changes as necessary.

- In some instances, when it would have been very difficult to ascertain what activities are required, the contract includes a level of detail, which with hindsight was inappropriate. Examples include:

- 2.11: ‘Assessment criteria…..need to be broad enough to allow consideration of any worthwhile pro business project.’ In fact, the ECF has, rightly, decided to focus on projects, which are clearly focused on ECF criteria.

- 2.20: ‘All panels shall remain anonymous, so members can make decisions free from undue pressure.’ In small communities in the pacific, this was an unrealistic stipulation.

The contract stipulates performance criteria, which if achieved, result in performance bonuses being paid to the managing agent. While this is an attractive management tool in theory, it is usually difficult to ensure, in practice, that the criteria provide the appropriate incentives for ensuring a high quality programme, which achieves its strategic objectives. This is particularly difficult for a programme like ECF, which lacks a strategic framework and clearly identified Purpose. Some of the criteria stipulated in the ECF Contract, such as a targeted number of concept notes submitted, and the value of grants, clearly have little to do with the quality of the ECF.

ECF’s contact and relationship with AusAID posts appears to vary country by country, largely in relation to the degree AusAID is involved with private sector development work in that country or not. ECF has generally involved the country Posts with marketing efforts and given them the opportunity to veto applications from their countries. Most AusAID Posts perceive ECF to be a useful addition to their portfolio of interventions, and it would be beneficial if they could be more involved in the project assessment process, particularly to provide background information on Government and other development partner activities. AusAID Posts expressed an interest in knowing more about the projects supported and their impact.

OECD Development Assistance Committee’s Criteria for Evaluating Development Assistance (www.oecd.org)

In the main, comparisons have been made with the DFID supported Challenge Funds: BLCF and FDCF (both of which have now closed) and the AECF. Some limited comparisons with the Advocacy Funds which have been started in Africa, supported by a range of bilateral development partners, including DFID and Danida.

www.enterprisechallengefund.org

Based on discussions with ECF Management and comments from Country Managers.

‘Eligibility’ describes concept notes that fulfil 8 basic criteria. These include: a) that the lead proposer is a for profit business; b) that the lead proposer is able to contribute 50% of the required project funds; and c) that the proposal voids social damage and does not involve tobacco, alcohol and/or gaming.

BEST-AC is the Business Environment Strengthening for Tanzania programme’s Advocacy Component, supported by DFID, Danida, SIDA and the Government of the Kingdom of the Netherlands.

It is worth noting that this hands-off role is counter to much of the ECF Contract which stipulates, for example that ‘….the Contractor shall provide facilitation services to grant applicants….’ Section 4.14 of Schedule 1: Scope of Services.

The Fund Manager tested the attendance of Country Managers at regional panel meetings in Round 3, but on the basis of disquiet expressed by some panel members, decided not to proceed with this process.

The Review Team issued a questionnaire to all AusAID Posts and received feedback from 4 of the 9 countries.