|  |  |  | AusAID |
| --- | --- | --- | --- |
| Enterprise Challenge Fund – Mid-Term Review |  |  |  |
| Annex 5: Monitoring and Evaluation |  |  |  |
| Harald Bekkers |  |  |  |
| November 2009 |  |  |  |
|  |  | Suite One, 4 Saddler Street Durham DH1 3NP United Kingdom Tel: +44 191 383 1212 Fax: +44 191 383 1616 Email: global@ springfieldcentre.com |  |

# Introduction

The Enterprise Challenge Fund (ECF) is a pilot project in more than one way. This is the first AusAID program designed to interact more directly with the private sector (instead of through multilateral channels such as IFC or ADB). This is also the first challenge fund operated by AusAID. Finally, this is the first challenge fund of its kind, with a specific Asian-Pacific focus. For all these reasons rigorous impact assessment is import. Only in this way questions about the effectiveness and efficiency of the instrument can be answered and learning for subsequent AusAID funded programs generated.

Impact assessment is often perceived to be complex process, especially in relation to private sector development. This has to do with the nature of subject, capturing socio-economic change and trying to isolate that change from all those other societal factors producing change. It also has to do the nature of the process. Often it takes years before an impact assessment can be completed. Often it also requires applying a variety of research tools at different points in time for a variety of respondents. Given this complexity it is possible to lose track of what the program initially intended to achieve and which activities were supposed to trigger what changes.

All this does not make impact assessment a 'mission impossible', but it does make it a process that needs 'careful handling'. Without sufficient care impact assessment easily results if 'shallow' stories with smiling beneficiaries and unsubstantiated claims about 'strongly improved livelihoods' or a '30% increase in income'. Such statements should always be treated with suspicion. Often they are indications of the fact that really solid and concrete information is missing due to inappropriate measurement (wrong question, wrong respondent, wrong timing, wrong research tool, et cetera).

This call for careful handling is repeated here, at the beginning of this annex on ECF Monitoring and Evaluation, because there are reasons to be concerned about how the ECF M&E process is currently handled. Below follow a number of key guidelines to keep an M&E process on track. In all cases the current ECF M&E process deviates from these guidelines (except for the last one, which does not apply yet).

Formulate a clear results framework, with a clear and logical hierarchy of objectives and suitable indicators against which performance can be measured.

Such results framework keeps a program on course; it gives strategic direction to activities and defines the logic and purpose of the program. Without it, confusion can arise about what the program intends to achieve and how it intends to achieve it.

Logical frameworks and impact logic models are useful tools to enforce that a single hierarchy of objectives is articulated (instead of using woolly descriptions or 'shopping lists' of objectives, which leave much room for interpretation).

Translate this logical hierarchy of objectives and matching indicators into a tidy monitoring and evaluation framework with well-defined steps spelling out who will measure what, how and when.

This ensures that the framework produces credible impact stories: credible in terms of a sufficiently rigorous methodology; credible in terms of being sufficiently coherent and detailed to allow for triangulation between different sets of figures; and credible in terms being sufficient coherent to establish plausible attribution between project activities and a variety of changes in business practices and the wider economy, without having to depend on 'leaps of faith'.

Impact assessment should not be about collecting bits and pieces of information on a variety of possibly interesting signs of change, because all these individual bits and pieces of information are very difficult to interpret if presented without sufficient context. Also their relation with program activities may be difficult to establish if it is not clear how and where they fit into the impact story. Without credibility and attribution figures are just figures.

Instead, impact assessment should be about validating (or refuting) a particular impact story and information collection should be tightly organized around this 'case'. The impact story should contain a clear impact logic, an idea of how program activities lead to changes with in turn lead to real impact, and a prediction of impact in accordance with the original rationale for funding the project. Both guide the process of information collection because they define where change will take place and in what form change is expected.

Note that in order to be able develop an accurate impact story the person in charge of M&E must be very familiar with the project and the context in which it is implemented.

Spend sufficient time in the field to be able to 'test' the impact story/logic for a project or intervention and interpret figures in their context.

Even with both frameworks in place rigorous impact assessment depends on the correct interpretation of data. This may sound rather obvious, but in most cases interpretation of data is complex because different bits and pieces of information contract each other, other bits and pieces are missing, and again other bits and pieces require careful 'handling' because they might be of an unreliable quality. This means that impact assessment can never be a desk job. Data needs to be interpreted in its context: what is credible and what is not.

Feed the findings back to the project or intervention's initial objectives to make impact assessment a real management and learning tool.

This annex will discuss the M&E system in place for the ECF based on this four-step logic and point out weaknesses and suggests changes where necessary. Note that point 4 will not be discussed, as the results from the field are not mature enough yet.

# What to measure: the Results Framework

The ECF Project Design Document (PDD) does not provide a logical framework, which 'forces' the ideas behind the ECF into a clear hierarchy of objectives. This was a conscious choice at the time of the design, perhaps given in by the fact that the ECF was likely to fund a wide variety project, which might be problematic to fit into the 'straightjacket' of a logical framework. However, with hindsight one can conclude that this might have been a mistake and the opposite holds true: because the projects funded will vary so much it is essential to have a clear framework to assess them against, first during the application stage and later while monitoring their performance.

During the review process it became clear that there was confusion about the purpose of the ECF program. This seems to have been caused by:

- A 'shopping list' of development goals, which the ECF is expected to 'serve', such as innovation, pro-poorness, improving the Business Enabling Environment (BEE) and triggering systemic change;

- A lack of clarity about the exact meaning and interrelated nature of concepts such as innovation, BEE, systemic change and pro-poor growth.

This confusion is reflected in the ECF Program Results Framework. In an attempt to create clarity, for writing this M&E annex documents were revisited to see how the objectives were formulated originally. This helps to interpret the current ECF Program Results Framework and recommend an alternative framework.

## Review of a 'shopping list' of objectives and concepts

### Project Design Document

Starting point is the PDD. As mentioned, the PDD does not contain a logical framework for the ECF. Instead it gives a list of objectives (see par. 42, p. 9):

- Poverty alleviation;

- Raising awareness among the private sector in Asia and the Pacific that there are profit making opportunities in poor markets;

- Catalyzing commercial investment in those markets, bring about sustainable change in corporate behaviour - an increasing proportion of private sector resources is allocated for investment in poor markets;

- Improvise conditions for profitable business in poor markets - in terms of more enabling rules, business to business services, improved infrastructure, and so forth;

- Leveraging the activities of business for to help advance broader improvements in the enabling environment.

This list of 'objectives' is actually more a program activity list: to alleviate poverty one first wants to create awareness among business that there are profitable opportunities in pro-poor markets (e.g., with the help of studies), then trigger investment in these (by co-investing), which results in better functioning pro-poor markets (through better rules, services and infrastructure), which the program in turn wants to leverage out to broaden the scope of pro-poor market expansion and improvement.

Translating this into a hierarchy of objectives, the output level relates to 'pro-poor business models established' (by co-investing), the purpose level is about 'pro-poor market expansion' (when these business models start to deliver), which through increased income and employment for the final beneficiaries should contribute to 'poverty alleviation', the goal level.

One particular comment needs to be made here. Improvements in the conditions for doing business (BEE) relate here to the conditions for the beneficiaries, i.e. poor households, not the business models supported. Thus the logic followed is 'invest in business models to improve the BEE for poor households' and not 'create a conducive BEE to support specific business model to develop pro-poor markets'. This is not how the term is most conventionally used. However, it is consistent with how the Making Markets Work 4 the Poor (M4P) approach is introduced in the PDD, namely as a complementary, more proactive tool for channelling investments into a particular business environment and in this manner reinforce or prepare the ground for less direct, further removed, regulatory-based BEE reform.

Further down in the PDD a list of anticipated direct and indirect impacts is given (par 76-79, p. 39-40). Direct impact is defined as jobs and income for poor people. Indirect impact is defined as:

- Systemic impact - improvements brought about by the project in terms of transport and distribution, business enabling environment (BEE) - enabling increased pro-poor commercial activity;

- Replication: having seen what has been achieved by the ECF project approach other businesses imitate the project approach (in same/different sectors/territories);

- Crowding in: having seen what has been the achieved by the ECF project approach other businesses follow in the servicing of particular markets;

- Scaling up: because business are commercially sustainable they continue beyond the live of the grant;

- Behavioural change in the business community towards investing in pro-poor markets.

Two more comments need to be made here.

Firstly, the distinction between direct and indirect impact is incorrect. Direct impact seems to relate to an increase jobs and income for poor persons within the funded business, and indirect impact to jobs and income for beneficiaries reached around the business through an improved BEE (rules, services, infrastructure). However, given the fact that ECF projects are funded on the premises of representing business models that generate wider developmental benefits, this outreach to beneficiaries should be considered as direct impact.

Secondly, the distinction between systemic impact on the one hand and replication, crowding in and behavioural change on the other is incorrect. The inclusion of beneficiaries in better functioning markets through ECF funded projects represents systemic change (presuming that these markets did not function well before), but so does the fact that the market system is able to capitalize on this and starts copying the ECF funded model or at least tries to crowd into the same new profitable market. The difference between the two is that the first form of systemic change is a form of direct impact because directly related to program activities, whereas the second one is a form is indirect impact because replication and crowding in are beyond the influence of the program.

It is useful to repeat these lists here, because they help to explain the ensuing confusion when putting together the results framework. It is clear that whereas the first list puts most emphasis on direct impact, inclusive growth through an improved BEE for beneficiaries, the second list puts more emphasis on indirect impact in the form of replication, crowding in and changing mindsets. However, it should also be noted that the different emphasis aside, there is no direct contradiction between the two: the basic hierarchy of objectives formulated above fits both.

### Request for Tender

However, the Request For Tender (RFT), which is based on the PDD, defines a very different goal and purpose level from what was mentioned above. Here the goal of the ECF program is translated not as 'poverty alleviation' but as 'private sector led growth in poorer regions of Asia and the Pacific'. The purpose level is defined not as pro-poor market expansion, but as 'increased access by the poor to sustainable jobs and services'.

This seems to be an incorrect translation of the spirit of the PDD. Private sector led growth, stimulated by the ECF, should result in income earning opportunities for the poor (through an improved BEE), not the other way around. And it is unlikely that inclusive market development reaching poor households immediately translates into an increase in GDP or the share of the private sector in the GDP (the two indicators chosen for the goal level). Nevertheless, this goal and purpose level was consequently copied into the ECF Program results framework.

The RFT also seems to deviate from the PDD in two other ways.

- It refers to the need for ECF projects to be 'innovative'. The term makes sense in the context of the ECF, because there is a demonstration effect embedded in the rationale for the ECF (opening the eyes of businesses for doing business in pro-poor markets), but the term as such does not feature very prominently in the PDD.

- Whereas pro-poor benefits and BEE more or less meant the same in the PDD, in the RFT they seem to be taken apart again. Impact on the BEE is expected aside from direct employment, income earning opportunities and access to services for the poor. Changes in the BEE should benefit all private sector activity. Thus here BEE is used again in a more conventional manner.

Recommendation

Considering the fact that there is some 'fluctuation' in how key concepts such as BEE and systemic change are interpreted - not only in key documents but also by the various persons involved in implementing the ECF - it might be useful to develop a list of operational definitions for these key concepts. This list can be attached to the reworked results framework (see Paragraph 1.2) to help steer and understand the ECF. Together with reworked measurement frameworks with clear impact stories (see Section 2), these documents could provide a concise overview or summary of the ECF.

## The results framework reworked

The ECF Program Results Framework is the product of a collaborative effort between the Fund Manager (FM) and the Independent Monitoring Team (IMT). The initial version produced by the FM (Monitoring and Evaluation Framework, version 2) focused strongly on the direct outcomes of the projects funded, feeding directly into jobs, income and services for poor people (the purpose level designated in the RFT). BEE is mentioned, but not as an outcome of the activities of the projects funded. (Wider) systemic change is not mentioned.

In revision 4 of what is by now called the Program Monitoring and Evaluation Plan the FM and the IMT pulled together the following ECF Program Results Framework (see Figure 1 below). On the behest of the IMT BEE and systemic change were included here.

The easiest way to read Figure 1 is to move from outcome 1, the direct impact generated within the project funded, to outcome 2, the inclusive, enabling effect of the project on business environment for poor people (the beneficiaries), to outcome 3, the reach of project, to the purpose level, the result of that inclusive, enabling reach, to the goal level (follow the  arrows).

Figure 1: The ECF Program Results Framework

There are three problems with this results framework:

Firstly, the hierarchy of objectives, the causal logic of how one change, starting with program activities and leading up to the goal level, is weak and fragmented.

The clearest indication is the need to give reading instructions to spell out the impact story that the framework does not tell by itself. BEE is not a standalone outcome, but is again a consequence of the business growth in outcome 1 one and hence should be at a higher level. Outcome 3 again is not a standalone outcome, but relates to the effectiveness outcome 2 and should again be at a higher level.

Another indication is that references to indicators like jobs or services each are mentioned in three different boxes at two different levels.

In other words, this results framework does not sufficiently articulate how the different 'ingredients' of the ECF design  (innovation, BEE, systemic change, pro-poor growth are related and feed into each other - perhaps a direct result of the 'loose' manner in which the different ingredients were dealt with in the various documents. There was never a clear 'recipe'.

The consequence of this is that when translating this results framework into a measurement framework (see Section 2), the connections between the different levels and indicators might not clear and coherent. This in turn might lead to gaps in measurement or measurements might be not sufficiently specific.

Secondly, the purpose level should be defined in a more strategic, more systemic manner.

Access to jobs, services and income earning opportunities are the result of a systemic change triggered by the 'transformative' business models, in which the ECF invests, and which in turn which might trigger 'wider systemic change' in the form of scaling up, replication and crowding in.

The purpose level must be about markets, opened up by innovative business models, breaking down access frontiers and improving the BEE for poor people in the sense that they have better access to income earning opportunities, jobs and services. In other words, Systemic change here is about market inclusion and market expansion, fuelled by innovative business models, for which the ECF fund acts like a catalyst.

Systemic change is more than BEE and should not placed at the outcome level.

Thirdly, the goal level is ill defined and with the current set of indicators impossible to measure.

The most pressing concern in relation to beneficiaries would be their poverty status, not their contribution to GDP. The additional income they might earn from having better access to income earning opportunities, jobs and services could make a substantial contribution to their household income level, but is not likely to influence regional GDP levels.

Conversely, any changes in GDP levels will not be attributable to the program.

Recommendation

The following results framework is proposed to address the issues of logic, purpose and goal mentioned above.

Figure 2: Proposed ECF Program Results Framework

About this results framework the following explanatory comments need to be made:

- BEE is not specifically mentioned here. Instead indicators are listed at purpose level, which imply a change in BEE, such as access to services, skill development, changes in productivity and savings, changes in the volume and value of commercial transactions.

- Systemic change is not specifically mentioned here. Instead indicators are listed, which imply systemic change. One list of indicators was listed under the previous bullet point: the inclusive nature of innovative business models opening up markets in which the poor can participate as entrepreneurs, labourers and consumers. Wider, indirect systemic change relates to copying and crowding in.

- The term 'innovation' has been highlighted here. Innovation refers to the forms of systemic change just described: breaking down barriers and find way to open up a market in which the poor can participate, and in doing so setting an example for others to follow.

- A difference is made between direct impact and indirect impact. Direct impact covers a pro-poor market expansion directly related to the innovative business model supported. Indirect impact relates to pro-poor market expansion triggered by other businesses copying the innovative business model supported by ECF or trying to crowd into the same pro-poor market. The FM will stimulate this by disseminating the impact story and learning from ECF projects to relevant audiences.

- Hence there are two sets of activities identified, creating two outputs (putting innovative business models in the market, and making sure people get interested in those), triggering two outcomes (the business models demonstrate their viability and this viability (further) triggers copying and crowding in). Outputs are defined as changes over which the ECF program still has a reasonable amount of control (providing sufficient support and oversight so that the entrepreneurs can implement their business plans). Outcomes are beyond the program's control: they depend on how the market reacts to the business models put into place.

- As mentioned, the purpose level is about expanding pro-poor markets. The indicators listed capture the qualitative and quantitative aspects of this expansion.

- The goal level has been changed to poverty alleviation for reasons mentioned earlier. The goal level indicators, increase in GDP and the share of the private sector in GDP, will not yield changes attributable to the ECF projects. For this the influence of 23 projects on the GDP of nine countries is simply far too small. Also, both indicators will be influenced by many other factors. An indicator on poverty alleviation on the other hand, operationalised by matching the additional income earned by beneficiaries with their poverty level will yield an impact that can be calculated and is attributable.

- It is important to note that the indicators listed are not obligatory. They should be generally useful, but if the impact story requires different indicators then there should be room to use those. For reason of comparison and aggregation it would be useful to use the following key indicators for all 23 projects:

- At outcome level: volume, value and profit of transactions with pro-poor markets;

- At purpose level: outreach and additional employment and income generated.

- From the outcome level upwards, key indicators can be measured for a number of years, especially if a significant expansion of business is expected (thus capturing the 'scaling up' effect). Also, with the help of these key indicators a basic cost-benefit calculation or return on investment calculation can be made for each project. If you know the total additional income and employment, based on a certain outreach (direct and indirect), based on increased transactions with pro-poor markets one can compare this with the ECF investments to quantify the effectiveness of the program.

# How to measure: the M&E Framework

The ECF Program Results Framework is translated into a Monitoring and Evaluation Framework. The Monitoring and Evaluation Framework makes the results framework operational: it provides operational definitions for the indicators listed in the results framework; it identifies tools for measuring against these indicators; and it allocates responsibilities in terms of who will apply these tools. In other words, this framework provides a system for conducting the monitoring and evaluation for the ECF program.

For the 23 individual projects funded this system is laid down in individual Monitoring and Evaluation Frameworks (MEFs). MEFs list the indicators to be measured, baseline information, changes in indicators across years, targets and assumptions.  Having these individual MEFs and being able to use them as a road map for measurement represents good practice. As mentioned earlier, monitoring and evaluation depends on a systematic, organized and continuous approach to measurement. MEFs provide the foundation for that.

However, despite the fact that this foundation is in place, there are concerns about the interpretation and interconnectedness of indicators, the availability of suitable baseline data, and the oversight over the M&E process and field presence.

## Indicators

Indicators define the points of change, which will be measured with the aim to demonstrate impact. Which indicators are chosen and how in turn they are translated in to measurable units strongly influences the effectiveness of an M&E system in terms of capturing impact.

The following comments can be made about the choice of indicators and the way in which they are made operational in the Monitoring and Evaluation Framework (see Program Monitoring and Evaluation Plan p. 8-14). First two technical points need to be raised:

- The goal level indicators are not suitable for measuring impact, as already discussed.

- Crowding in is defined as "number of non ECF funded businesses providing other products/services on the supply chain to support ECF funded initiatives..." It is not clear why this particular formulation was chosen, but crowding in has little to do with supporting ECF funded initiatives. Instead, what one hopes to see is 'other businesses crowd in to the market opened up by the ECF funded innovative business model'.

Next, the following two comments touch on the functioning of the MEFs as a whole and relate back to the problems mentioned above in relation to the current results framework, namely the lack of connection and coherence between indicators and levels. If one faithfully measures the indicators in the MEFs, one should get a reasonably clear impact story. However this is not the case. There are two issues that influence this.

The Monitoring and Evaluation Framework asks for percentages but should work only with absolute figures. Working with absolute figures has two advantages:

- Absolute figures can be aggregated across projects to produce figures for the ECF program.

- Absolute figures can be used for impact calculations relating change at one level to change at the next level hence ensuring triangulation and attribution.

For example: if the business supported by the ECF reports a 500 MT increase in purchasing a certain crop from farmers, and if you know that on average farmers produce 0.1 MT then it is likely that the outreach is around 5,000 farmers. If you know that the profit (not the sales figure!) per MT should be around 100,000 units, then each farmer earns an additional income of 10,000 units. If you know that the average household income in this region is 50,000 units and the poverty line is drawn at 55,000 units, you can also say something about the relevance of these additional 10,000 units per household for poverty alleviation.

The example demonstrates how changes at one level directly feed into and inform changes at the next level. This ensures attribution. And because this relation is so clear, changes can be checked from both sides: the business reports an increased purchase of 500 MT, but can farmers confirm this, did they see their sales increase by around 0.1 MT? This ensures triangulation.

As also noted earlier, the credibility of figures and attribution of change go hand in hand. If one works with percentages making these connections and calculations is simply not possible (unless percentages are reworked again into absolute figures: farmers report a 10% increase in sales, which means X MT).

The Monitoring and Evaluation Framework is currently set up as an inventory list, and asks, e.g., for 'the number of new products and services developed by ECF projects', the 'number of new income earning opportunities', the 'number and types of change in the BEE for beneficiaries', 'number and type of change in factors that influence productivity', 'number and type of change influencing access to finance', 'number and type of change in business linkages', the 'number of new skills acquired', 'percentage of services provided to poor people', 'number of new jobs created', and the 'percentage increase in income for poor people'. This checklist produces 'signs of change', but not necessarily a comprehensive impact story.

For example: let's assume a transformative business model in which a company wants to purchase vulnerable yet high-value flowers from smallholders. The company provides hands on advice on flower cultivation (to increase quality) and crates (to ship the delicate flowers safely to the city). Flower cultivation and packaging is labor intensive and profitable. With this information we can give values for the indicators asked for, and in the way they are asked for.

- Number of new services developed: 2 (advice on cultivation and packaging/transport);

- Number and types of change in BEE: 2, the same ones as above: the advice helps small holders to grow flowers that sell better; the crates help to bridge the distance between the cultivation area to the market);

- Number and type of change in factors influencing productivity: 1, advice increases quality which, if quality is rewarded in the market, increases the value of output compared to the value of input;

- Number and type of new business linkage: 1, the ECF supported business;

- Number of new skills acquired: 1, better cultivation;

- Jobs created: 10;

- Percentage increase in smallholder's income: 22%.

Based on this information it is not really possible to understand what happened, whether for instance both the advice and the supply of crates were successful and contributed to the 22% increase in income. For this it would have been necessary to have information on the price for the old quality of flowers and on losses due to bad packaging. Also it is not possible to check the accuracy of the 22% increase in income. This would have be possible if there would be information on the (increase in the) number of flowers sold, (the decrease in) losses, and the (increase in) profit per flower. In other words, vital information is missing to tell the story, check the credibility of figures and attribute change to program activities.

At the same time, different indicators basically duplicate each other asking about the same change: the service developed by the ECF funded business is the improved in the BEE for the beneficiary is the new skill the beneficiary acquires, etcetera.

This could have been avoided by working the other way around and starting by telling the impact story. Based on such a story it is possible to identify very precisely what information is needed and indicators for these can be inserted in the MEF. The MEF would have made use of most of the indicators given in Figure 2, but would have added specific indicators, for instance to operationalise the 'volume and value of commercial transactions' (by identifying grades of flowers and profit margins per grade).

Recommendation

To rework MEFs in accordance with the recommended results framework (Figure 2) and in such manner that they are no longer checklists of change, but are able to tell unique impact stories so as to ensure the measurement of all indicators needed to prop up those stories. A cover page could be added to the MEFs where this story is written down, including the anticipated impact, so that there is clarity among all involved about the expectations with regard to the different projects.

## Baselines and anticipated impact

The next step, after identifying indicators, is to establish baselines for these indicators to get an idea of change in time. Before discussing the baselines established for the ECF program, first three comments needs to be made about the functionality of baselines and the importance of calculating 'anticipated impact':

There are two types of baselines, generic baselines, often intended to cover a whole program, and specific baselines, tailor-made to capture a particular program activity or intervention.

Traditionally most energy is invested in the generic baselines, often involving large surveys or big studies. They can be very insightful, but for the purpose of impact assessment they often remain too general: for most of the specific changes brought about by a program activity there tends to be no baseline value in the big report.

In contrast, the specific baselines are often much more in informal in nature, based on observation or a few interviews, and sometimes do not exist at all. However, for the purpose of impact assessment this type of baseline tends to be more useful, because if done well can record 'baseline scenarios or practices', which the program aims to influence. These baseline scenarios and practices can be part of the impact story.

Baselines are established to show change in time, between 'before' and 'after'. This works well in an environment in which there is no change if not triggered by the program. Whatever is different 'after' as compared to 'before' must be caused by the program. However, economic environments change all the time; economies are always growing or shrinking. This means that proper impact assessment should be based on at least three measurement points and not two (before, after). One needs to assess not whether there is change, but whether is change in the pace and/or direction of change (trends). Description of trends (and anticipated changes in trends) can again be part of the impact story.

Aside from defining baseline practices and baseline values it is also important to formulate what impact is the expected impact from a certain program activity. As mentioned, defining anticipated impact helps to focus on what needs to be measured to capture that impact.

### BEE baseline reports

One set of baselines for the ECF are the BEE baseline reports. These fall in the 'generic' category and are basically country studies covering:

- Economic review and performance;

- Business environment;

- Key sectors;

- Donor activity;

- ECF strategy focus areas.

These studies, prepared for all nine ECF countries, were supposed to serve a double purpose: to give strategic direction to the ECF grant allocation process by identifying areas to focus on, and to serve as an ECF baseline, so that the effect of ECF funded projects on the BEE could be compared against the baseline scenario. The outcome is a very generic set of studies without sufficient strategic dept to give direction to the ECF grant allocation process and without sufficient detail on various aspects of the business environment to really serve as a baseline.

For example: the BEE baseline for Vanuatu speaks in such generalities as "neither state nor private provision of infrastructure provides for low cost or effective service...", "inadequate infrastructure continues to be a major obstacle to economic growth...", "Vanuatu's legal and regulatory framework for business is outdated and inadequate...", and "Vanuatu's underdeveloped onshore financial sector provides a minimal range of banking services, which have just started to reach beyond the main urban centres..." All these points may be valid, but do not carry enough detail to be really useful here.

To build on the Vanuatu example: the innovation that Marine Consultancy Services (MCS) introduced is the concept of 'timetable driven', regular shipping connections between islands. Four key baseline scenarios are relevant in this context:

- How many regular 'timetable driven' shipping lines existed in Vanuatu before MCs entered the scene?

- How often particular islands where visited before MCS introduced its regular shipping line?

- How much cargo (volume, value) and people were transported from these islands before MCS introduced its shipping line?

- Survey of economic activity and household income and expenditure patterns on the islands before MCS introduced its shipping line.

All this information cannot be found in the generic BEE baseline. Thus, all this information needs to be collected and inserted in the MEFs. This does not mean that the BEE baseline studies are badly executed. It is simply impossible to expect such generic studies to serve as a baseline; for that the studies should have focused in much greater detail on specific sectors relevant to the targeted beneficiaries, poor households, or in much greater detail on all aspects of the business environment as faced by the same beneficiaries.

Thus, it is doubtful that the BEE baseline studies will be of much use when trying to understand the real 'before' picture. This makes the baselines in the MEFs of the individual projects all the more important.

### Project specific Monitoring and Evaluation Frameworks

The second set of baseline figures (as well as indications of anticipated impact) can be found in the MEFs for the individual projects. However, these MEFs are nearly all still in a draft format and not complete. One issue with the MEFs is that in most cases baseline data and target (anticipated impact) data are copied from the application form of the particular project. This raises the following issues:

- The financial data in the applications is not always correct. To meet the criteria of 'commercial sustainability within three years' figures appear to have been tweaked in that direction. However, for a real life impact assessment, making use of realistic figures is more appropriate; otherwise projects might fall short of meeting expectations only because they had to impress the panel. In other words, the applications are not the best source of business related information and efforts needs to be undertaken to arrive at realistic figures.

- Also, applications are typically weak on estimating the development impact of the innovative business model promoted: the outreach of new markets being opened up and the benefits for poor households such as additional sales, additional income and additional employment. Again, the applications are not the best source of information and efforts needs to be undertaken to arrive at realistic figures.

This copying of figures from applications is given in by the fact that in the ECF M&E process there is overreliance on the grantees for providing impact data, combined with a weak 'field presence' of program staff with research affinity and capabilities. Both will be discussed in more detail below. However, it is important that this situation changes. The way the M&E process is moving it is unlikely that it will generate robust impact stories.

Incomplete baselines and copying application figures (instead of accurately recording baseline scenarios and practices) means that at this point in time there is a lack of clarity about the different projects funded, the exact working of the business model and the exact nature of the potential benefits for the designated beneficiaries. This is related to the lack of clarity about the results framework, the exact meaning of BEE, the exact purpose of the program and how to define systemic change. Nevertheless, a translation from paper-driven applications to real-life projects needs to guide the monitoring and evaluation effort. Visiting the project, understanding how things will work, checking the assumptions in the application, visiting the intended beneficiaries are all part of this. It should not be up to an evaluation mission to try and dig all this out as happened this time; it task should be to validate what was dug out before.

Recommendation

To get realistic baselines and anticipated impact, each project needs to be visited in person so that for each project the impact story can to be 'sorted out' (what is most likely to happen based on the investments triggered by approval of the application) and realistic figures can be to be attached to it, both for the baseline and for the anticipated impact. Where these figures are not available additional groundwork needs to be done to fill in the gaps.

The question is: who is responsible for this?

## Oversight over M&E process and field presence

It should have become clear from what has been written so far that for impact assessment oversight is important. Someone needs to be familiar with, in this case, the 23 ECF funded projects and needs to understand how they will bring about systemic change and generate impact. That same person should think about how to capture these changes and impact. And that same person should also be in the position to direct the various impact measurements needed to capture the change process. M&E roles should never be divorced from implementation roles, because only with implementation comes the insight that is so useful when thinking about how to capture impact.

So far much emphasis is given to the need to be able to tell an impact story in which 'everything' - old scenarios and practices, trends, systemic changes, anticipated impact - can be brought together in a clearly articulated, fluid, coherent story of systemic change. In this manner one can move beyond a series of changes with unclear connections to a logical flow in which it is clear how activities led to systemic changes and these changes generated impact. Being able to tell this story means being clear about the impact logic of the project means having overview of what needs to be done to capture all this. This clarity and overview needs to be embodied in a person.

However, at present the responsibility for the M&E process appears to be scattered over a large number of persons. The ECF program enjoys a double monitoring and evaluation structure. The Fund Manager is responsible for monitoring and evaluation, but there is also the Independent Monitoring Team, contracted to validate specific aspects of the FM's reporting and to add value to the M&E process. The FM involves four 'levels': an M&E specialist, project staff to maintain the MEF database (but who rarely visit the field), the country managers and the 23 grantees. The FM also considers hiring NGOs for specific studies. The IMT employs at least two more persons for different studies, one engaged in validating direct and indirect impact as reported by the FM, the other engaged in making Cost Benefit Analyses (CBA) for a limited number of projects.

The M&E process around the ECF might appear robust and 'happening', but it is a robustness and energy around an empty core: the person with oversight in the middle, able to direct the process, is missing. On the FM's side the person who has seen most of the field and who is most familiar with the projects is the ECF program director, but he does not have the time to be more involved in M&E. The M&E specialist has a limited number of days, most of them used to set up the M&E process together with the IMT. FM staff, full-time on the program, could have a much larger role effectively running the M&E process, but so far have had far too little exposure to the field. The country managers do not always have an affinity with doing research and lack a sufficient number of days for doing so (20 days per year for the last three years of their contract). Finally there is the grantee who is expected to carry the bulk of the M&E burden.

This set up creates a number of problems as outlined below.

Impact assessment depends too heavily on the grantees that are basically expected to report on 'everything' except the two goal-level indicators.

This is unrealistic and unwanted. Grantees should run their innovative, transformative, risky projects, not engage in studies on household income levels. Also, grantees might not be the most suitable persons to handle such research assignments.

Thus, by design the grantees were the supposed to be persons with oversight, with the FM mainly in an administrative role, managing the database. Where the grantee leaves a gap immediately the question arises who can step in.

The FM is aware of this 'grantee gap' is thinking of solutions. Country manager might chip in (but in some cases country managers made it clear not to be ready for such tasks). NGOs might be useful be contracted for this purpose. See more on this below.

A consequence of this 'grantee gap' is that impact stories and MEFs are not properly sorted out. What is being kept in the FM's database are MEFs with inappropriate indicators and boxes filled with not always accurate figures from applications.

Too many different persons visit the same project for different research efforts (but basically repeating many of the same basic questions).

Equipped with incomplete MEFs it can happen that up to four persons visit the same project for different research requirements: the country manager who needs to collect some figures for the FM's reporting, the FM's M&E specialist who wants develops a case study, an IMT person who needs to check inputs in the FM's reporting, and another IMT person doing a CBA.

Each of them will struggle with the same basic issue: how to make a proper assessment of the project's probably impact in the absence of reliable figures. In other words, each person has to reinvent the same wheel and the outcomes of their efforts might not be very reliable, because most of that remains based on the same quick assessments (instead of proper measurements).

Of course, as solutions for the 'grantee gap' are found (some) MEF's will improve, but the point is that sound MEFs should be the cornerstone on which to build with other research efforts, not the by-product of those research efforts.

Whereas some projects might benefit from various research efforts, there is a reasonable chance that others will remain virtually unvisited (perhaps once of twice), which under the current circumstances means that whatever impact data emerge from those projects is questionable (unless real solutions are found to fill gaps).

Overall, there is a lack of clarity about the division of labour between FM and IMT.

The IMT's role was originally as follows:

- Provide an annual assessment of the FM's performance (which depends on the annual activity plan and varies with the stage the program is in);

- Validate the findings of the FM's performance assessment of the direct and indirect impact of the ECF projects and the entire ECF portfolio (which is based on a combination of desk review of the FM's reporting and field visits);

- Conduct a detailed cost-benefit analysis of a sample of ECF funded projects (a standalone activity which does not involve the FM).

- Perform the analysis for the two goal level indicators (which in the way the results framework has been set up has little bearing on the projects - another standalone activity).

In time, however, the IMT's role has expanded beyond the original scope of work, especially in relation to the design of the results framework, the design of BEE baselines and the design project MEFs.

The fact that the IMT has been insisting on using more complex frameworks seems justified. Also, the fact that the IMT 'duplicates' work by visiting the same projects as the FM might be difficult for the FM - given the fact that the FM struggles to fill the 'grantee gap' - but is justified in the light of the role that the IMT has to play. The IMT can never substitute for the FM in terms of the overall responsibility for the M&E process. It is the FM's responsibility to run this process and, if the original idea putting much of this on the grantee's plate have proven to be too optimistic, to come up with another solution within the FM's organization.

While writing this review report the FM and IMT agreed on the following division of labor to further clarify roles and responsibilities. The solution that has been found to fill the grantee's gap is to first look at the country (CM) to do more and, if that does not work, to hand over the responsibility to the FM's M&E advisor.

Figure 3: Roles and responsibilities in the ECF M&E process

Recommendation

It would be good if this latest agreement on how to manage the ECF M&E process in the field is able to fill the grantee gap. However, this solution still does not put a person firmly in charge of the overall process. This is still recommended. There needs to be someone who is so familiar with all projects that that is able to judge whether the changes and impact reported make sense.

# Quality of measurement

In the previous section it was already mentioned that around the ECF various research efforts are ongoing, but that these efforts struggle because the basis, solid impact stories and MEFs, is missing. In this last section of this M&E annex two examples will be given that help to illustrate this, a case study developed by the FM and CBAs developed by the IMT.

The key difference between M&E and proper academic research is that an M&E process is not likely to produce a 'definitive' answer. For that time is too short and resources too limited. The aim of M&E is not to 'proof'; it is to generate 'plausible' impact stories. But also plausible impact stories need grounding. The examples given below demonstrate that the current understanding of the ECF projects is too weak, which makes this grounding weak, which makes it easy to arrive incorrect conclusions about the projects at hand.

The Nature's Way case developed by the FM

Nature's Way represents an interesting yet complicated project. ECF's funding feeds into a larger strategic expansion plan. Whether or not this plan will become reality depends on a variety of factors. Quarantine protocols and market research will influence market expansion. Packaging (crates), a grading machine and, perhaps in the future, a value chain study on losses will reduce wastage. Seeds, extension services and, perhaps, irrigation will influence yields. All this factors influences the potential for impact. These factors will influence how much will be exported through Nature's Way (and hence the volume that farmers need to cultivate), how much margin there is to be divided (quality, loss), and how much yield increases farmers can experience. The picture gets even more complicated when new crops are exported (perhaps with a different profit margin) and new farmers switch to producing high-value export crops (experiencing increases in income that will be substantially higher than farmers already in export crops).

The case developed by the FM is thorough and tried to look at Nature's Way from all angles as specified by the MEF. This was a useful exercise. It made clear, for instance, that the amount of additional employment as mentioned by Nature's Way in the application is far too optimistic.  Similar adjustments are likely to be needed in other projects. Nature' Way MEF was substantially adjusted after the case study and again this is something likely to happen with other projects as well.

The key point to make here is in relation to a particular conclusion of in the case study, namely that Nature's Way additional export volume will be absorbed by existing export farmers, all of whom are not poor. This would make Nature's Way somewhat of a failure from an ECF perspective:  a project derived of any pro-poor relevance. The case study brings the potentially very rich and complex scenario described above down to a few already rich farmers earning a bit more.

Indeed existing export farmers are probably not poor, but the conclusion that there is no room for new farmers when export starts to expand is too radical and something that Nature's Way does not agree to. If one reasons from the amount land existing export farmers have available to expand production, no new farmers are required. However, if one reasons from the average amount of land farmers have under cultivation with a particular crop and that there are good reasons (irrigation, labour, soil quality) why this cannot be expanded easily, there is room for up to 650 new farmers. If a percentage of those farmers would be former sugarcane farmer and hence poor, a case that seemed without pro-poor relevance all of a sudden becomes very relevant again: poor farmers being able to diversify away from a dying sector to a sector with future that offers a livelihood above the poverty line.

This is not the time or the place to decide who is wrong and who is right. The point is that there should not be so much confusion about something so essential to the project. The uncertainty with Nature's Way is whether or not new export markets will open up. To what extent existing farmers will expand production and/or new farmers will enter (and if so from where), is something about which it should be possible to reach some agreement. One can study farmer behaviour, the availability of suitable land, etcetera. One can work with conservative and optimistic scenarios, or scenarios for different crops if necessary.

The fact that there is so much confusion about the fundamentals of the project illustrates the point made above, that at this point in time there not sufficient clarity about how the projects work (the business model) and what they can deliver (in terms of growth, BEE and impact). This affects the case study. When real impacts can be recorded a case study on Nature's Way should get 'lost' in changing cropping pattern, different cultivation cost and fluctuating profit margins in order to try to establish the additional income for farmers. But long before that the basics of how many farmers are approximately involved should be clear.

The Cost Benefit Analyses conducted by the IMT

Similar problems arise with the CBAs conducted by the IMT. A CBA can be a sophisticated tool to assess the effectiveness of a project. However, the relevance and quality of the calculation depends on the quality of the information feeding into the calculation and the assumptions made. Because of this it is a tool that is particularly useful at the end of the project life cycle, when there is clarity on what worked and what did not and relevant impact data has been collected.

In this light the CBAs conducted by the IMT are conducted very early and it is questionable how much value should be attached to their outcomes. The early timing of the CBAs, and hence the need to work with assumptions rather than real data, is compounded by the quality of the assumptions made. As in the case of the Nature's Way case, these assumptions tend to be rather 'radical'.

The following examples illustrate this:

Marine Consultancy Services: As mentioned above, the innovative business model introduced by MCS is the timetable driven, regular shipping line. Other ships in the Vanuatu waters do not follow this principle. The owner of MCS claims that by following a regular schedule he can kick start economic activity on the islands on route, which in turn makes his regular schedule viable. Thus in his scenario there are substantial pro-poor gains: economic activity on isolated island made possible only because of MCS's innovation in shipping.

The CBA is much more negative. The CBA relies heavily on a shipping study, which concludes that there is overcapacity in shipping and that most of the islands on MCS' new route are serviced frequently enough. Thus in this scenario no pro-poor gains, but instead ECF subsidising one ship owner to push others out of business.

Again, the aim here is not to pass a final judgment. On the contrary, the conclusion is again that too little is known about the fundamentals underpinning the project and that the radically different opinions about the project illustrate this. There is nothing wrong with the fact that MCS' innovative shipping schedule crowds other ships out of the market, if it really offers a better service. Proof of this better service would be the increase in economic activity on the islands serviced.

In the absence of this proof fieldwork is needed to assess the demand for a regular shipping service and/or to study the economic effects of MCS's first regular shipping service between the two main cities. Both could shed light on when a regular shipping service starts to add value to the local economy and how much this added value could be. A CBA would make sense only once this picture is clear.

Carnival. Whereas the MCS CBA is very negative, the Carnival CBA is very positive. ECF supported Carnival in developing facilities so that cruise ship passengers can go ashore on isolated islands. This in turn generates income for the local economy. For the CBA it is assumed that with the new facilities the number of visitors will increase by 7% per year for 20 consecutive years! It is also assumed that without investments the number of visitors will decrease by 7% per year until the visitors stop coming altogether!

Obviously, based on this scenario the project has good impact, but the validity of the assumptions is questionable. One cannot assume that a business continues to grow for 20 years. There is no reference to a Carnival growth projection to help support this claim. Likewise, the assumption that nothing will be done to prevent the total collapse of tourism is also unlikely. Again, a CBA would make more sense once these fundamentals are clarified.

Recommendation

This final recommendation can be brief. There is a lot of energy going into the M&E process around the ECF funded projects, but not enough of that energy is focused there where it matters most, in travelling to the field to understand the projects and their impact potential in detail and trying to find answers to difficult yet fundamental questions. One thorough 'sorting out' would create more clarity and produce more reliable figures than an array of short exercises. The way to achieve this 'sorting out' has been indicated: articulate the impact story, identify what needs to be known to validate that story, insert this into a MEF, and put someone in charge with sufficient time and resources to direct research efforts. If this is done the ECF M&E system will fall together and out of it will emerge undoubtedly very interesting impact stories.