|  | Cambodia Community Justice Assistance Partnership (CCJAP) Department of Foreign Affairs and Trade 30-Oct-2015 Doc No. SMPR |  |
| --- | --- | --- |
| Six-Monthly Progress Report |  |  |
| April to September 2015 |  |  |

Six-Monthly Progress Report

April to September 2015

Client:	Department of Foreign Affairs and Trade

ABN: 47 065 634 525

Prepared by

AECOM Australia Pty Ltd

Level 28, 91 King William Street, Adelaide SA 5000, Australia

T +61 8 7223 5400  F +61 8 7223 5499  www.aecom.com

ABN 20 093 846 925

30-Oct-2015

Job No.: 42444174

AECOM in Australia and New Zealand is certified to the latest version of ISO9001, ISO14001, AS/NZS4801 and OHSAS18001.

© AECOM Australia Pty Ltd (AECOM). All rights reserved.

AECOM has prepared this document for the sole use of the Client and for a specific purpose, each as expressly stated in the document. No other party should rely on this document without the prior written consent of AECOM. AECOM undertakes no duty, nor accepts any responsibility, to any third party who may rely upon or use this document. This document has been prepared based on the Client’s description of its requirements and AECOM’s experience, having regard to assumptions that AECOM can reasonably be expected to make in accordance with sound professional principles. AECOM may also have relied upon information provided by the Client and other third parties to prepare this document, some of which may not have been verified. Subject to the above conditions, this document may be transmitted, reproduced or disseminated only in its entirety.

Quality Information

| Document | Six-Monthly Progress Report |
| --- | --- |
| Ref | 42444174 |
| Date | 30-Oct-2015 |
| Prepared by | John Rennie, Team Leader |
| Reviewed by | Dee Hartvigsen, Project Manager |

Revision History

| Revision | Revision Date | Details | Authorised |  |
| --- | --- | --- | --- | --- |
|  |  |  | Name/Position | Signature |
| 1.0 | 30-Oct-2015 |  | Frank Maiolo Project Director |  |

Table of Contents

Executive Summary	i

1.0	Introduction	1

1.1	Project Description	1

1.2	Structure of Six-monthly Progress Report	1

2.0	Progress of Project Implementation	2

2.1	End of Program Outcome 1: The Justice System is Managed for More Effective Pre-trial Arrangements, Use of Non-custodial Sentencing and Improved Prisons	2

2.1.1	Intermediate Outcome 1a: Community Understands and Begins to Support Non-custodial Sentencing	2

2.1.2	Intermediate Outcome 1b: Courts and Police Pilot More Effective Pre-trial Options and Non-custodial Sentencing	2

2.1.3	Intermediate Outcome 1c: Improved Custody for Prison Detainees	2

2.2	End of Program Outcome 2: Women, Youth and Children are Safer and Communities have Less Crime	2

2.2.1	Intermediate Outcome 2a: Community Works Better Together to Demand and Deliver Safety	2

2.2.2	Intermediate Outcome 2b: Police Engage with Community and Respond to their Safety Needs	3

2.2.3	Intermediate Outcome 2c: Cambodians have Greater Awareness of the Law, and their Legal Rights and Responsibilities	4

2.3	End of Program Outcome 3: Communities, Police, Courts and Prisons Use Evidence to Support Policy and the Management of Justice	4

2.3.1	Intermediate Outcome 3: Justice Sector uses Strengthened Systems for Evidence-based Management	4

3.0	Capital Works	5

4.0	Management	7

4.1	Exit Strategy – Closure Plan	7

4.2	Staff Reductions – Civil Action under the Cambodian Labour Law	7

5.0	Budget and Expenditure	8

6.0	Monitoring and Evaluation	9

Appendix A

Resource and Implementation Schedule from July 2015 to June 2016	A

Appendix B

CPCS Project List from April to September 2015	B

Appendix C

CPCS Project Assessment Data, Apr–Sept 2015	C

Appendix D

Assets Handed Over to Government Agencies	D

Appendix E

Actual Expenditure against Total Contract	E

List of Tables

Table 1	Breakdown of end-of-partnership outcomes into intermediate outcomes	1

Table 2	Capital works projects (Phase I)	5

Table 3	Capital works (Phase II)	5

Table 4	Summary of CCJAP expenditure vs budget	E-1

List of Figures

Figure 1	CPCS projects financed during April–September 2015	3

Figure 2	CPCS PIAs during April–September 2015	3

Figure 3	Beneficiaries' perception of the CPCS awareness sessions	4

Figure 4	Actual expenditure July–September 2015 against Annual Plan budget (July 2015 – June 2016)	8

Figure 5	Level of CPCS project beneficiaries’ awareness improvement	9

Figure 6	Average number of crimes per person per year	10

Figure 7	Outcome of all crimes reported	11

Figure 8	Fear of crime happening in village	11

Figure 9	Overall satisfaction with police	12

Figure 10	Contract Budget vs Actual Expenditure April 2013 – September 2015	E-2

Abbreviations

| Abbreviation | Description |
| --- | --- |
| APPA | Administrative Police Post Affairs |
| AUD | Australian dollar |
| BAT | Battambang province |
| BMC | Banteay Mean Chey |
| CCJAP | Cambodia Community Justice Assistance Partnership |
| CNP | Cambodian National Police |
| CPCS | Crime Prevention and Community Safety |
| DAPPA | Department of Administrative Police Post Affairs |
| DFAT | Department of Foreign Affairs and Trade |
| DID | Difference in deference |
| GBV | Gender-based violence |
| Ind | Indicator |
| KCH | Kampong Chhnang province |
| KDL | Kandal province |
| KPC | Kampong Cham province |
| KPT | Kampong Thom province |
| KRT | Kratie province |
| NMB | National Management Board |
| PIA | Project Implementing Agency |
| PNP | Phnom Penh City |
| PVG | Prey Veng province |
| RGC | Royal Government of Cambodia |
| SRP | Siem Reap province |
| UPS | Uninterruptible power supply |
| USD | United States dollar |
| WCCC | Women and Children’s Consultative Committees |

Executive Summary

The Cambodia Community Justice Assistance Partnership (CCJAP) has now entered its final year of operations as part of an ongoing and unbroken period of support to the Cambodian law and justice sector that began in 1997. CCJAP, which began on 1 April 2013, represents the final phase in this support, and will conclude on 30 June 2016. CCJAP is distinct from previous phases due to its narrower focus and concentration on crime prevention, community safety, reduced prison populations and improved conditions, and improved management through more effective use of information and information systems.

Progress during the first two and a half years of CCJAP has been mixed, with good progress identified under Component 2 (‘Women, youth and children are safer and communities have less crime’), but little identifiable progress noted under Component 1 (‘The justice system is managed for more effective pre-trial arrangements, use of non-custodial sentencing and improved prisons’) and Component 3 (‘Communities, police, courts and prisons use evidence to support policy and management of justice’). The lack of progress in Components 1 and 3 led the National Management Board (NMB) to approve in June 2015 the removal of activity expenditure to both of these component areas in the CCJAP cost and implementation schedule for the final year, other than funding to complete capital works commenced within the Cambodian prison system and the construction of police posts to support crime prevention and community safety.

In December 2014, the NMB also approved an exit strategy for the cessation of the Crime Prevention and Community Safety (CPCS) support activities at the commune level under Component 2, which previously provided annual funding of AUD800 per commune for approved CPCS activities. Following this decision, support to the nine partner provinces was progressively ceased, beginning with the closure of activities in the first three provinces in April 2015, a further three provinces in June 2015 and the final three provinces at the end of September 2015. Component 2 will continue with a focus on supporting community policing.

In this report, CCJAP will provide details of the outcomes of its support to the partnership against the NMB-approved reduced activity areas. Details will therefore be provided only relating to capital works under Component 1 and Component 2. There were no activities supported under Component 3 during this reporting period after discussions with counterparts and the NMB in late 2014 and the approval of the final year’s cost and implementation schedule by the NMB in June 2015, removing all funding support for this component.

Component 1 Results – Capital Works

All capital work sub-projects in Phase I (Table 2) have been completed and handed over to counterpart organisations and are now being utilised operationally. Ninety five percent of the contract cost has been released to the engaged contractor, with five percent retained for the contracted defect liability period of six months, which is due to expire in mid-November 2015. Although CCJAP is not able to directly measure the extent of impact attributable to these capital work projects, the nature of the works (prison health post buildings, security fencing to allow greater time outside of cells, water storage and water pumping improvement) suggest that they will have a significant impact on the quality of life for persons incarcerated within the prisons.

The Capital Work Phase II (Table 3) has made steady progress, with some delays due to unforeseen issues such as land conflicts with local authorities (Projects No. 6, No. 10, and No. 19), failure of admission to prison (Project No. 3) and poor road accessibility due to seasonal flooding. These issues have largely been overcome and progress is on track to allow completion of all activities by the planned dates.

Component 2 Results – Crime Prevention and Community Safety

During this reporting period, six CCJAP partner provinces implemented CPCS projects. Kandal, Siem Reap and Kratie had been phased out in April 2015; three more were concluded in July and the final three closed at the end of September. During this reporting period, a total of 390 CPCS projects (USD81,360) were supported by CPCS funding, with topics including awareness-raising on law preventing domestic violence (38%), drug abuse, gambling and human trafficking, as well as safe migration, the penal code, the traffic law, education for persons engaged in gang activity, and the Village-Commune Safety Policy (the Royal Government of Cambodia policy related to community safety). The most frequently requested CPCS project type funded by CCJAP during the reporting period continued to be for activities related to the reduction of domestic violence (148 of 390 projects) followed by drug business/use prevention projects (54 of 390 projects) and other lesser priorities such as Village-Commune Safety Policy dissemination, and the traffic law and public order (Figure 1).

Internal CCJAP monitoring and evaluation of the CPCS activities conducted during the period identified that a total of 22,694 community members (of which 13,472 were female and 2,200 youth) benefited from these CPCS projects. Internal evaluations completed by participants revealed that after having attended CPCS dissemination meeting, 39% and 61% of 57 respondents rated improvement of their awareness as “Excellent” and “Good”, respectively. Approximately 98% of the respondents expressed that the awareness sessions were “Important” and “Very Important” (Figure 3).

Cumulatively, CCJAP’s work in the area of CPCS has achieved measurable results, not only from a quantitative perspective, but also qualitatively. Quantitatively, CCJAP has achieved the following results since the commencement of the CPCS activities in 2013:

- 2060 separate activities were conducted across nine provinces

- 134,681 persons attended CPCS activities at the commune level

- 31% of all commune requested activities related to reducing gender-based violence (GBV)

- 72,785 participants were female

- USD498,474.92 in program funds were expended in this activity.

Qualitatively, CCJAP achieved the following:

- 77% of participants reported their level of awareness improvement as either good or excellent (CCJAP internal evaluation data)

- 98% of participants reported the importance of the programs as either important or very important (CCJAP internal evaluation data)

- 84% of communes reported that they had begun to use their own funding in 2015 to continue the programs initiated by CCJAP (CCJAP rapid assessment of 115 communes supported by CCJAP)

- 93% of respondents surveyed by Angkor Research to assess the impact of the CPCS reported that the attitude of police had improved during the period of the CPCS activities (Angkor Research 2015)

- 77.8% of respondents surveyed by Angkor Research reported that they had noticed a change in accessibility of police services over the period, with 95% reporting improved accessibility (Angkor Research 2015)

- 98% of respondents surveyed by Angkor Research reported that police visibility had become improved during the previous 2 years (Angkor Research 2015)

- 87% of respondents surveyed by Angkor Research reported either slight (63%) or much improved (34%) police responsiveness.

Component 2 Results – Support to the Development of Community Policing

CCJAP has continued to provide support to strengthen the capacity of the Cambodian National Police (CNP) Department of Administrative Police Post Affairs (DAPPA), which is the CNP department responsible for implementing reform to the way in which police services are delivered at the commune level. In late 2014, CCJAP embarked on a program of engagement with DAPPA to develop and implement community policing within the country. During this reporting period, CCJAP has provided financial and technical assistances to CNP in organising 2 four-day trainings on the roles and responsibilities of Police Posts to a total of 180 participants (of which 3 were female) in Koh Kong and Pursat. CCJAP also co-financed, with the United Nations Office of the High Commissioner for Human Rights in Cambodia, a three-day training program (2–4 June 2015) on community policing to 35 CNP police officers from DAPPA and three provincial commissariats (Kandal, Kratie, Prey Veng). Following this training, CCJAP organised a four-day Training of Trainers on Community Policing Concepts and Crime Prevention for 24 DAPPA Officers (of which 3 were female) from 24 to 27 August 2015.

# Introduction

## Project Description

The Cambodia Community Justice Assistance Partnership (CCJAP) is an Australian-funded 3.5-year project operating from 2013 to 2016 to support the Royal Government of Cambodia (RGC) and its legal and judicial reform. Since 1997, Australia has provided financial and technical support to RGC in its legal and judicial reform efforts, with a focus on improving access to justice, with a particular emphasis on vulnerable groups such as women and juveniles. For this phase of the program, the focus is narrower and deeper, with a program goal of “Contributing to building safer communities, as well as sentencing and prison reform”. To achieve this purpose, the project has three main project strategic outcomes: 1) The justice system is managed for more effective pre-trial arrangements, use of non-custodial sentencing and improved prisons; 2) Women, youth and children are safer and communities have less crime; and 3) Communities, police, courts and prisons use evidence to support policy and management of justice. The key strategies to be implemented to support these outcomes are based on a partnership approach with RGC.

## Structure of Six-monthly Progress Report

CCJAP has three thematic end-of-partnership outcomes and a management component. The three thematic outcomes have been broken-down into seven intermediate outcomes (Table 1).

Table 1	Breakdown of end-of-partnership outcomes into intermediate outcomes

| End-of- partnership outcomes | Intermediate outcomes |
| --- | --- |
| The justice system is managed for more effective pre-trial arrangements, use of non-custodial sentencing and improved prisons | 1a. Community understands and begins to support non-custodial sentencing 1b. Courts and police pilot more effective pre-trial options and non-custodial sentencing 1c. Improved custody for prison detainees |
| Women, youth and children are safer and communities have less crime | 2a. Community works better together to demand and deliver safety 2b. Police engage with community and respond to their safety needs 2c. Cambodians have greater awareness of the law, and their legal rights and responsibilities |
| Communities, police, courts and prisons use evidence to support policy and management of justice | 3. Justice sector uses strengthened systems for evidence-based management |

This report is structured to provide information related to progress against budget and annual plan as well as towards each intermediate outcome. During this reporting period, Component 1 activities were phased out and funding for phase 3 was removed, on the direction of the National Management Board (NMB) (other than capital works under Component 1) and CCJAP redirected its support over thematic area 2 with a primary focus on supporting the Cambodian National Police (CNP) to develop its community policing initiative. This report, therefore, provides detail relating to Component 2 and the capital works conducted under Component 1 only.

# Progress of Project Implementation

The progress reported below is made partly against the third CCJAP annual work plan, covering the period from July 2015 to June 2016, and the second CCJAP annual work plan and budget, covering the period from July 2014 to June 2015. The two work plans were approved by the NMB. It should be noted that during this reporting period, CCJAP has ceased its support to the two thematic areas (thematic area 1: pre-trial detention options and prison management, and thematic area 3: evidence to support policy and management of justice). The focus remains only on thematic area 2 (Women and children are safer and communities have less crime) and has been further narrowed down to supporting crime prevention through the development of the CNP and its Department of Administrative Police Post Affairs (DAPPA) led community policing approach.

The goal of CCJAP is: Prosperous, safe and secure communities in Cambodia.

The purpose of CCJAP is: Contribute to building safer communities and reducing overcrowding in prisons.

## End of Program Outcome 1: The Justice System is Managed for More Effective Pre-trial Arrangements, Use of Non-custodial Sentencing and Improved Prisons

### Intermediate Outcome 1a: Community Understands and Begins to Support Non-custodial Sentencing

During this reporting period (Apr–Sep 2015), no activities were undertaken under this area.

### Intermediate Outcome 1b: Courts and Police Pilot More Effective Pre-trial Options and Non-custodial Sentencing

During this reporting period (Apr–Sep 2015), no activities were undertaken under this area.

### Intermediate Outcome 1c: Improved Custody for Prison Detainees

Although CCJAP has not supported any direct capacity development activities to improve prison conditions for detainees under this component, the impact of CCJAP’s capital works program in prisons (Capital work Phase II) includes the construction of buildings for juveniles and female prisoners in Uddor Meanchey and Pailin prisons and the construction of family visit and lawyer room in Correctional Centre 1, which all have the potential to contribute to the improvement of prison conditions for juvenile and female prisoners, as well as their human rights.

The 15 sub-projects commenced under Phase I of the capital works program have all been completed and handed over to the General Department of Prisons, and are now all under management of the respective prison authorities. (Please refer to chapter 3.0 of this report for detailed information related to capital work).

## End of Program Outcome 2: Women, Youth and Children are Safer and Communities have Less Crime

### Intermediate Outcome 2a: Community Works Better Together to Demand and Deliver Safety

The final six Crime Prevention and Community Safety (CPCS) partner provinces were concluded during this reporting period. From April to September 2015, a total of 390 CPCS projects (USD81,360) were selected for CPCS funding through the CPCS partnership support fund. CPCS projects were selected through a process that involved CCJAP provincial program officers providing support to target commune authorities to assist them to identify, screen, and select CPCS priority project proposals from Commune Investment Programs (the government-led, local participatory planning process applied by all commune councils across the country).

CPCS projects selected for this partnership support fund included: projects addressing the laws on preventing domestic violence; drug abuse; gambling; human trafficking; safe migration; the penal code; the traffic law; education for persons engaged in gang activity; and the Village-Commune Safety Policy (the RGC policy related to community safety). The most frequent CPCS project type funded by CCJAP during the reporting period was for domestic violence education (148 of 390 projects), followed by drug business/use prevention projects (54 of 390 projects) and other lower priorities such as Village-Commune Safety Policy dissemination, and the traffic law and public order (Figure 1).

Figure 1	CPCS projects financed during April–September 2015

Source: CCJAP Evaluation and Monitoring System

### Intermediate Outcome 2b: Police Engage with Community and Respond to their Safety Needs

CCJAP delivered its CPCS program by engaging directly with community located agencies and individuals who were contracted locally to provide inputs. The use of these Project Implementing Agencies (PIAs) allowed CCJAP to revise the way in which funds were managed provincially and reduce previous costs attributed to provincial overheads from 42% under the previous phase to an average of 15% under CCJAP. During this reporting period, there were nine PIAs involved in delivering CPCS projects to the communities in the six CCJAP partner provinces. Police agencies remained the highest PIA representation (around 46%) in terms of project value in delivering CPCS projects, with Women’s Affairs Agencies second at 39%.

Figure 2	CPCS PIAs during April–September 2015

Source: CCJAP Evaluation and Monitoring System

A total of 22,694 community members (of which 13,472 were female and 2,200 youth) benefited from the CPCS projects.

CCJAP has continued to provide support to strengthen the capacity of DAPPA/CNP. During this reporting period, CCJAP has provided financial and technical assistance to CNP to:

- Deliver 2 four-day trainings on the roles and responsibilities of Police Posts to a total of 180 participants (of which 3 were female): the first in Koh Kong in late April 2015 and the second in Pursat in early June 2015. The key participants for these trainings were chiefs and deputy chiefs of police posts from those respective provinces

- Conduct a workshop in May 2015 to introduce the concepts of Community Policing. A total of 76 participants (of which 9 were female) attended from the CNP DAPPA in Kandal and Kratie provinces, along with CCJAP thematic advisers

- Co-fund and facilitate, with the United Nations Office of the High Commissioner for Human Rights in Cambodia, a three-day training program (2–4 June 2015) on community policing to 35 CNP police officers (of which 4 were women) from DAPPA and three provincial commissariats (Kandal, Kratie, Prey Veng)

- Organise a four-day Training of Trainers on Community Policing Concept and Crime Prevention for 24 DAPPA Officers (of which 3 were female) from 24 to 27 August 2015.

Following the above four-day training, CCJAP advisers worked with DAPPA counterparts to discuss and refine the training materials relating to Community Policing and Crime Prevention that will be used by DAPPA/CNP to conduct this type of training for the three agreed CCJAP partner provinces at the police post level. The training for the police posts is scheduled to commence in October 2015 and CCJAP has supported the CNP to develop a series of simple tools to facilitate the implementation of community policing processes at the commune level. All trainers are based at DAPPA and have attended the above training and will be supported by CCJAP Advisers who have adopted adult learning techniques, mentoring, role modelling and coaching to advance the capacity of these new CNP trainers as they deploy to the commune level.

### Intermediate Outcome 2c: Cambodians have Greater Awareness of the Law, and their Legal Rights and Responsibilities

Among the 390 CPCS projects implemented during the period, 57 projects were selected for assessment through CCJAP’s internal monitoring and evaluation system. The assessment results revealed that after having attended a CPCS dissemination meeting, 39% and 61% of 57 respondents rated improvement of their awareness as “Excellent” and “Good” respectively. Approximately 98% of the respondents expressed that the awareness sessions were “Important” and “Very Important” (Figure 3).

Figure 3	Beneficiaries' perception of the CPCS awareness sessions

Source: CCJAP Evaluation and Monitoring System

## End of Program Outcome 3: Communities, Police, Courts and Prisons Use Evidence to Support Policy and the Management of Justice

### Intermediate Outcome 3: Justice Sector uses Strengthened Systems for Evidence-based Management

During this reporting period (Apr–Sep 2015), no activities were undertaken under this area.

# Capital Works

All capital work sub-projects in Phase I (Table 2) were completed and handed over to the management prison authorities. CCJAP has released payment of 95% of the contract cost to the engaged contractor, with another 5% retained for the Defect Liability Period of six months, which will expire in Mid-November 2015. If there are no defects identified or complaints raised from the counterparts, this final amount will be released to the contractors.

Table 2	Capital works projects (Phase I)

| No. | Prison | Project | Contracted Costs (USD) | Progress |
| --- | --- | --- | --- | --- |
| 1. | Preah Vihear | Improved prison sewage system | 6,692.00 | Completed |
| 2. |  | Family visiting shelter and lawyer room | 32,734.90 | Completed |
| 3. |  | Public toilets building |  | Completed |
| 4. | Svay Rieng | Family visiting shelter and lawyer room | 23,771.48 | Completed |
| 5. |  | Health post building construction | 34,878.87 | Completed |
| 6. |  | Security fence inside the prison | 13,206.00 | Completed |
| 7. | Battambang | Security fence inside the prison | 5,338.80 | Completed |
| 8. | Siem Reap | Water storing tank, water pumping motor and solar power set up | 8,124.00 | Completed |
| 9. | Kampong Speu | Public toilets building | 5,111.75 | Completed |
| 10. |  | Security fence inside the prison | 18,236.00 | Completed |
| 11. | Ratanakiri | Public toilets building | 5,042.01 | Completed |
| 12. |  | Health post building construction | 47,561.60 | Completed |
| 13. | Mondulkiri | Public toilets building | 5,020.05 | Completed |
| 14. |  | Health post building construction | 40,932.67 | Completed |
| 15. | Kampong Cham | Public toilets building | 4,934.28 | Completed |

The procurement committees established to select bidders for the Phase II capital works (Table 3) selected two winning contractors (Vistanukar and Reaksmei Keomeas), who signed contracts in July 2015 and commenced works shortly after.

During this report period, the Phase II capital works have made steady progress by overcoming minor delays due to land conflicts with local authorities (Projects No. 6, No. 10, and No. 19), failure of admission to prison (Project No. 3) and poor road accessibility due to seasonal flooding. Table 3 below reflects the actual progress to-date against its original schedule.

Table 3	Capital works (Phase II)

| No. | Location | Project | Project schedule | Actual Work Progress |
| --- | --- | --- | --- | --- |
| 1. | Uddor Mean Chey (Prison) | Accommodation building for juveniles and female prisoners | 70% | 80% |
| 2. | Pailin (Prison) | Accommodation building for juveniles and female prisoners | 70% | 80% |
| 3. | Correctional Centre 1 | Family visit and lawyer room | 70% | 65% |
| 4. | Kandal Province | Administrative Police Post building | 70% | 75% |
| 5. | Kandal Province | Administrative Police Post building | 70% | 75% |
| 6. | Kampong Chhnang Province | Administrative Police Post building | 70% | 75% |
| 7. | Kampong Chhnang Province | Administrative Police Post building | 70% | 65% |
| 8. | Battambang Province | Administrative Police Post building | 85% | 75% |
| 9. | Battambang Province | Administrative Police Post building | 85% | 75% |
| 10. | Kampong Thom Province | Administrative Police Post building | 85% | 70% |
| 11. | Siem Reap Province | Administrative Police Post building | 85% | 90% |
| 12. | Prey Veng Province | Administrative Police Post building | 85% | 80% |
| 13. | Prey Veng Province | Administrative Police Post building | 85% | 90% |
| 14. | Prey Veng Province | Administrative Police Post building | 85% | 90% |
| 15. | Prey Veng Province | Administrative Police Post building | 85% | 90% |
| 16. | Prey Veng Province | Administrative Police Post building | 85% | 90% |
| 17. | Prey Veng Province | Administrative Police Post building | 85% | 90% |
| 18. | Prey Veng Province | Administrative Police Post building | 85% | 90% |
| 19. | Prey Veng Province | Administrative Police Post building | 85% | 90% |

At the current rate of progress, it is expected that some projects will be completed in mid-October 2015 and all projects will be completed by early November 2015, thereby allowing sufficient time for the expiration of the six-month defect period and final payment before the completion of CCJAP.

# Management

CCJAP acted as NMB Secretariat to support the organisation of the fifth NMB Meeting on 22 June 2015 and provided updates to all NMB members regarding the progress of project activities, challenges and the new project direction. The NMB approved all recommendations and also discussed and approved the final CCJAP Cost and Implementation Schedule for July 2015 to June 2016 (Appendix A).

CCJAP also joined in and facilitated the discussion with Secretariat co-chair and DFAT in identifying a list of vehicles and office equipment to be handed over to the government agencies following the closure of the CPCS provincial offices. On 23 September 2015, a formal ceremony of asset handover to CNP was organised with participation from CNP senior officers, DFAT representatives, Australian Federal Police representatives and CCJAP staff members. The handed over assets include vehicles, laptops, LCD monitors etc. (Appendix D).

Two 3-month reports (Apr–June) in URS (now AECOM) and NMB formats were prepared and submitted to DFAT and NMB respectively. These two reports only emphasised the progress on activity to output level.

## Exit Strategy – Closure Plan

During the period, URS (now AECOM) submitted a formal Exit Strategy – Closure Plan to DFAT. This was accepted and approved on 28 September 2015. This plan will form the basis for the final nine months of operations of CCJAP and will guide each step of the closure process. The Risk Management Plan was also updated as part of the annual planning process and revised as part of the drafting of the Exit Strategy. No additional risks have been identified; however, the risk to the budget from the ongoing fall in the USD/AUD rate has been noted and factored into program budget planning.

## Staff Reductions – Civil Action under the Cambodian Labour Law

CCJAP initiated a process of staff reductions following the completion of the CPCS program and the re-focusing of the program on Component 2 and the withdrawal of support for Components 1 and 3. Three program officers were retrenched after legal advice identified that their contracts could be concluded early under the unspecified duration contract provisions in the Labour Law, after payment of a specified amount based on the number of years’ service. One officer has commenced legal action following this retrenchment and AECOM has engaged local legal representation to defend the case. The other two retrenched officers have not commenced legal action; however, they may do so depending on the outcome of the first retrenched officer’s case. DFAT has been kept advised of the process of this action and at the present time the case has been adjourned for legal argument.

# Budget and Expenditure

Figure 4 below reflects actual expenditure to the end of the quarter (July–September 2015) against Annual Plan budget (July 2015 – June 2016).

See Appendix E for detail of actual expenditure against contract value.

There are discussions underway to shift the focus of CCJAP, which will result in significant savings across the Contract. These discussions are taking place separately to this Report.

Figure 4	Actual expenditure July–September 2015 against Annual Plan budget (July 2015 – June 2016)

# Monitoring and Evaluation

During the reporting period, CCJAP focused on the monitoring of CPCS project implementation and managed the CPCS end line survey through Angkor Research and Consulting Ltd, a private research company contracted to undertake an independent review of the impact of the CPCS program activities.

CCJAP’s monitoring and evaluation process includes regular tracking of activities and their impact. In the case of the CPCS project implementation, all CPCS project proposals were sent to CCJAP head office in Phnom Penh, where all the CPCS project-related data (see Appendix B) was entered and regularly updated by the Managing for Development Results Officer. This monitoring data was also important for supporting and following up the progress of the CPCS project implementation, as well as for monitoring payments made against its schedule of costs.

In terms of monitoring CPCS project progress and performance in the field, all CCJAP provincial officers and their counterparts were directly responsible to monitor and assess the CPCS implemented projects through direct observation and interviews with project direct beneficiaries and other project stakeholders. The completed assessment forms were sent to the CCJAP Phnom Penh office, where the assessment data was entered (Appendix C), summarised and analysed and used to support management oversight and feedback to the NMB and counterparts.

During this reporting period, 57 out of 390 CPCS project implemented were selected for performance assessment through the CCJAP internal monitoring and evaluation system. The assessment results revealed that after having attended the CPCS dissemination meeting, 39% and 61% of 57 respondents rated improvement of their awareness as “Excellent” and “Good” respectively (Figure 5).

Figure 5	Level of CPCS project beneficiaries’ awareness improvement

Source: CCJAP Evaluation and Monitoring System

In June 2015, a CCJAP internal ‘rapid assessment’ was conducted of 116 out of 387 CCJAP-targeted communes that had been supported during the period, in order to find out whether any CCJAP targeted communes were using their own commune fund to support CPCS-related projects. This question is highly relevant to understanding if the CPCS-funded activities have established a sustainable platform from which commune leaders will support community safety reform in the future. The key respondents to this assessment were the commune chiefs, commune vice chiefs or clerks who have good knowledge of the use of each assessed commune’s 2015 commune fund. One of the 116 communes was not able to provide a response due to a schedule conflict; however, CCJAP provincial officers were able to interview all other identified respondents and forward the data to CCJAP’s Managing for Development Results team, who entered and analysed the data received. The findings from the assessment include:

- Among 115 communes interviewed, 84% of them used commune funds to finance social projects in 2015

- 84 out of 115 communes interviewed (accounting for 73% of the responding communes) used their commune funds to support CPCS-related activities in 2015. The amount of commune funds used to finance CPCS-related activities ranged from USD25 to USD2,375

- Only 1.2% of the allocated commune funds was used to finance the CPCS-related projects in 2015

- Upon asking why the communes had not allocated Community Safety funds to finance CPCS-related activities, we received the following responses:

  - 35% said “No idea”

  - 26% said “CCJAP already supported the activities”

  - 19% said “Infrastructure activities are the higher priority”

  - 10% said “No instruction from national level”

  - 10% said “CPCS activities require complicated procurement process”.

In early 2015, CCJAP engaged Angkor Research and Consulting Ltd. to conduct a study to measure the effectiveness of the CPCS project during the fourth phase of CCJAP in CPCS-targeted communes. The effectiveness of the project was measured in relation to: the safety of women, youth and children; changes in community crime rates; sustainability of the program; and changes in community behaviours. This survey included:

- A cross-sectional, quantitative survey of 756 households in three provinces (504 households in 12 communes that have received CPCS support, along with 252 households in 6 similar communes without CPCS interventions)

- A qualitative survey of 18 in-depth interviews with relevant local authorities (including commune police and commune council members) and community members (those that have participated in CPCS activities, and/or have the strongest perceptions of safety)

- Three focus group discussions with community members who had completed the quantitative survey already.

Summary of the results of the survey:

- The average rate of crimes per person was lower for the treatment group than the control group. Additionally, a decrease in rate of crime was observed in the treatment group, while the control group remained steady. While this suggests impacts of CPCS, the difference-in-deference (DID) analysis here did not prove this change to be statistically significant.

Figure 6	Average number of crimes per person per year

- There is a noticeable difference in the outcome of reporting, with the treatment group having a larger percentage of crimes solved than the control group. This frequency was also increasing through the timeline surveyed for treatment group, while the control group remained steady.

Figure 7	Outcome of all crimes reported

- In relation to how afraid of crimes respondents felt, the treatment group, overall and on specific measures, felt less afraid then the control group. The control group has a higher level of fear of various crime types than CPCS treatment respondents. In both groups, the fear has decreased in the past three years; however, the treatment group is declining at a faster rate than the control group. While these are encouraging for respondents’ perceptions of crime, the DID analysis showed that it cannot be a definitive result of CPCS activities, as a statistical significance was not observed.

Figure 8	Fear of crime happening in village

- The treatment group was observed to have higher perceptions of safety than the control group in their homes, villages and various situations in the community. This is also mentioned anecdotally in the qualitative section of the survey report, due to increased police presence and education of beneficiaries about safety at these events.

- For overall satisfaction with local police, the mean satisfaction scores rose throughout the treatment period. This was true for the treatment group and the control group alike. While increasing at a similar rate, the treatment group was higher than the control group; however. because of the similar increase of the control group, the result of the DID analysis was not significant.

Figure 9	Overall satisfaction with police

In regards to specific measure of police behaviour change, the largest change occurred in relation to the accessibility of police (defined as how easy it is to locate and contact police via telephone or in person). Here a significantly lower proportion of treatment respondents felt that it had become worse, and a larger percentage indicated that they felt it had improved either somewhat or much.

Appendix A

Resource and Implementation Schedule from July 2015 to June 2016

Appendix A	Resource and Implementation Schedule from July 2015 to June 2016

| Result Code | Activities |  | Resource and Implementation Schedule |  |  |  |  |  |  |  |  |  |  |  | Total in USD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 2015 |  |  |  |  |  | Year 2016 |  |  |  |  |  |  |
|  |  |  | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June |  |
|  | Component 1 – The Justice system is managed for more effective pre-trial arrangements, use of non-custodial sentencing and improved prisons |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Intermediate outcome 1c: improved custody for prison detainees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity – small scale infrastructure for prisons and police posts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INF | 1 | Small scale infrastructure construction Phase I |  |  |  |  | $12,579 |  |  |  |  |  |  |  | $12,579 |
| INF | 2 | Small scale infrastructure construction in three prisons | $56,012 | $56,012 | $56,012 | $10,373 |  |  |  |  |  | $10,373 |  |  | $188,780 |
| INF | 3 | Construction of Police posts in selected provinces | $160,867 | $160,867 | $160,867 | $29,790 |  |  |  |  |  | $29,790 |  |  | $542,181 |
| INF | 4 | Equipment | $8,150 |  |  |  |  |  |  |  |  |  |  |  | $8,150 |
|  |  | Sub-total for Component 1 | $225,029 | $216,879 | $216,879 | $40,163 | $12,579 | $0 | $0 | $0 | $0 | $40,163 | $0 | $0 | $751,690 |
|  | Component 2 – Women, youth and children are safer and communities have less crime |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Intermediate Outcome 2b: Police engage with their community and respond to their safety needs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity – Support the Capacity Development of the CNP, DAPPA through technical training programs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OCM2b | 1 | Ongoing technical support to DAPPA including continual coaching and mentoring to members of the six working groups |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OCM2b | 2 | One-day workshop on the outcomes of the study and survey on Administrative Police Post Affairs (APPA) functioning and gender-based violence (GBV), and an Introduction of Community Policing organised for 300 participants from national and sub-national Police of 25 provinces | $3,500 |  |  |  |  |  |  |  |  |  |  |  | $3,500 |
| OCM2b | 3 | Conduct four partner/donor group meetings to outline the Community Policing and GBV strategy to June 2016 | $500 |  |  | $500 |  |  | $500 |  |  | $500 |  |  | $2,000 |
| OCM2b | 4 | A half-day workshop for staff of DAPPA on: (i) Roles and Responsibilities of DAPPA; and (ii) Role and Responsibilities of Provincial Office of APPA and District Police Inspectors in charge of APPA |  |  | $1,000 |  |  |  |  |  |  |  |  |  | $1,000 |
| OCM2b | 5 | DAPPA Crime Prevention Working Group to obtain and review Commune Investment Plans in Prey Veng and develop action plans for future pilot activities |  | $1,000 |  |  |  |  |  |  |  |  |  |  | $1,000 |
| OCM2b | 6 | Undertake a review of the effectiveness of existing roles, relationships and communications between DAPPA staff and their CNP counterparts at provincial, district and commune levels in Prey Veng |  | $1,000 |  |  |  |  |  |  |  |  |  |  | $1,000 |
| OCM2b | 7 | 6 x workshop – Crime Prevention, GBV, the role of police in Cambodia (2 days) Phnom Penh, Kratie, Kandal, and Prey Veng | $5,000 | $2,500 |  |  |  |  |  |  |  |  |  |  | $7,500 |
| OCM2b | 8 | 1 x workshop – Understanding role of Governance and DAPPA’s role in ensuring governance is maintained at police posts (2 days) |  | $1,000 |  |  |  |  |  |  |  |  |  |  | $1,000 |
| OCM2b | 9 | 1 x workshop – Effective Administration Skills (1 day) |  |  | $1,000 |  |  |  |  |  |  |  |  |  | $1,000 |
| OCM2b | 10 | 1 x Training of Trainer for 20 DAPPA staff (3 days) |  |  | $3,300 |  |  |  | $3,300 |  |  |  |  |  | $6,600 |
| OCM2b | 11 | Building the management capacity of DAPPA through conduct of trainings, including skills on management and leadership, planning, report writing, monitoring and evaluation, communication, and objective orientated project planning (LogFrame) |  |  | $2,500 | $3,000 | $1,500 |  | $4,000 |  |  |  |  |  | $11,000 |
|  | Intermediate Outcome 2a: Community works better together to demand and deliver safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity – Support the implementation of community policing activities in three provinces: Prey Veng, Kratie, and Kandal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OCM2a | 12 | Implement Community Policing in target provinces (supporting, coordinating and implementing various activities at provincial, district and commune levels) |  |  |  |  | $7,500 | $7,500 | $7,500 | $7,500 | $2,000 | $2,000 | $2,000 |  | $36,000 |
| OCM2a | 13 | 3 x workshops in preparation for the pilot programs in Kandal and Kratie and Prey Veng. Participants will be the main stakeholders and include senior community leaders and police from Provincial, District and Commune levels. Outcomes to include: i) agreed plan of action; ii) letters of authority; iii) activities; iv) identification of thematic problems; and v) agreed implementation model (1 day each = 3 days) |  |  |  | $4,500 |  |  |  |  |  |  |  |  | $4,500 |
| OCM2a | 14 | 3 x provincial workshops on professional roles and responsibilities to lead the undertaking of Community Policing (Crime Prevention, Community Relations, GBV, Monitoring and Evaluation) Office of APPA participants from the three target provinces (1 day each = 3 days) |  |  |  | $4,500 |  |  |  |  |  |  |  |  | $4,500 |
| OCM2a | 15 | 9 x 1 day foundation training for police post staff introducing their roles and responsibilities under the Community Policing model (22 communes @ 3 communes per session = 9 workshops) |  |  |  |  | $5,000 |  |  |  |  |  |  |  | $5,000 |
| OCM2a | 16 | 9 x half day Commune Leader / Chief of Police Posts workshop to establish parameters of activities throughout the pilot program (22 communes @ 3 communes per session = 9 workshops) |  |  |  |  | $5,000 |  |  |  |  |  |  |  | $5,000 |
| OCM2a | 17 | 9 x 1 day follow up training of Police Post staff and members from the respective Commune Councils. This training builds upon initial training and focuses on the importance of police/commune council partnerships, implementation of Commune Investment Plan activities and the way GBV is managed (22 communes @ 3 workshops for session = 9 workshops) |  |  |  |  | $5,000 |  |  |  |  |  |  |  | $5,000 |
|  | Intermediate Outcome 2c: Cambodians have greater awareness of the law, their legal rights and responsibilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity – CPCS activities are funded at the commune level (AUD800 per commune) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OCM2c | 18 | CPCS projects identified, selected and implemented in communes in the three CCJAP partner provinces: Battambang, Kampong Cham, and Prey Veng | $9,300 | $9,300 | $9,300 |  |  |  |  |  |  |  |  |  | $27,900 |
| OCM2c | 19 | Payment to CCJAP provincial and district output-based contract coordination officials to support CCJAP project activities in three provinces. | $1,800 | $1,800 | $1,800 |  |  |  |  |  |  |  |  |  | $5,400 |
|  |  | Sub-total for Component 2 | $20,100 | $16,600 | $18,900 | $12,500 | $24,000 | $7,500 | $15,300 | $7,500 | $2,000 | $2,500 | $2,000 | $0 | $128,900 |
|  | Component 4: CCJAP Partnership is managed for mutual accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OCM4 | 1 | Base Line survey conducted by DAPPA and CCJAP on 15 random Police Posts in target provinces |  | $2,500 |  |  |  |  |  |  |  |  |  |  | $2,500 |
| OCM4 | 2 | End Line surveys conducted by DAPPA and CCJAP on 15 random Police Posts in target provinces |  |  |  |  |  |  |  |  |  | $2,500 |  |  | $2,500 |
|  |  | Sub-total for Component 4 | $0 | $2,500 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $2,500 | $0 | $0 | $5,000 |
|  |  | Grand Total | $245,129 | $235,979 | $235,779 | $52,663 | $36,579 | $7,500 | $15,300 | $7,500 | $2,000 | $45,163 | $2,000 | $0 | $885,590 |
|  |  | Cumulative | $245,129 | $481,107 | $716,886 | $769,548 | $806,128 | $813,628 | $828,928 | $836,428 | $838,428 | $883,590 | $885,590 | $885,590 |  |

Appendix B

CPCS Project List from April to September 2015

Appendix B	CPCS Project List from April to September 2015

| Province | District | Commune Name | Fiscal Year | Project Standard Name | Categories | Contract Code | # of Project | # of Beneficiaries |  |  |  |  | Contract Cost | Contract Date |  | Contractor/Suppliers | Name of PIA representative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | M | F | <18 Yrs Male | <18 Yrs Female | Total |  | Starting | Ending |  |  |
| Kampong Chhnang | Rolea B'ier | Rolea B'ier | 2015 | Law against Domestic Violence | Community Awareness | KCH/041/15 | 1 | 27 | 51 | 0 | 2 | 78 | $205.65 | 1-Apr-15 | 1-Apr-15 | District Office of Women’s Affairs | You Sokreth |
| Kampong Chhnang | Kampong Chhnang | Kampong Chhnang | 2015 | Law against Domestic Violence | Community Awareness | KCH/040/15 | 1 | 31 | 41 | 2 | 1 | 72 | $203.75 | 2-Apr-15 | 2-Apr-15 | District Office of Women’s Affairs | Mey Sinat |
| Prey Veng | Svay Antor | Svay Antor | 2015 | Law against Domestic Violence | Community Awareness | PVG/047/15 | 1 | 23 | 33 | 0 | 1 | 56 | $210.00 | 2-Apr-15 | 2-Apr-15 | District Office of Women’s Affairs | Chhim Chankhantey |
| Kampong Cham | Prey Chhor | Baray | 2015 | Drug business/use prevention | Community Awareness | KPC/036/15 | 1 | 45 | 20 | 2 | 0 | 65 | $215.00 | 6-Apr-15 | 6-Apr-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Chhnang | Kampong Tralach | Chhuk Sa | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/042/15 | 1 | 25 | 52 | 7 | 0 | 77 | $200.00 | 6-Apr-15 | 6-Apr-15 | District Office of Women’s Affairs | Kim Sopheap |
| Banteay Meanchey | Preah Netr Preah | Phnum Lieb | 2015 | Drug business/use prevention | Community Awareness | BMC/029/15 | 1 | 50 | 50 | 10 | 16 | 100 | $364.00 | 7-Apr-15 | 7-Apr-15 | Commune/Sangkat Police Post | Chhinh Buntthoeurn |
| Kampong Cham | Stueng Trang | Areaks Tnot | 2015 | Village and Commune Safety Policy | Community Awareness | KPC/038/15 | 1 | 67 | 16 | 1 | 0 | 83 | $215.00 | 7-Apr-15 | 7-Apr-15 | District Police Inspectorate | Soeun Tit |
| Kampong Chhnang | Kampong Leaeng | Kampong Hau | 2015 | Law against Domestic Violence | Community Awareness | KCH/044/15 | 1 | 38 | 32 | 0 | 0 | 70 | $215.00 | 7-Apr-15 | 7-Apr-15 | District Office of Women’s Affairs | Sorn Sarum |
| Kampong Chhnang | Baribour | Melum | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/043/15 | 1 | 27 | 44 | 0 | 0 | 71 | $205.00 | 7-Apr-15 | 7-Apr-15 | District Police Inspectorate | Cheang Sovanarith |
| Kampong Thom | Stoung | Banteay Stoung | 2015 | Village and Commune Safety Policy | Community Awareness | KPT/048/15 | 1 | 75 | 2 | 0 | 0 | 77 | $198.00 | 7-Apr-15 | 7-Apr-15 | District Police Inspectorate | Chhiv Sarim |
| Prey Veng | Kamchay Mear | Cheach | 2015 | Law against Domestic Violence | Community Awareness | PVG/050/15 | 1 | 13 | 44 | 0 | 6 | 57 | $191.90 | 7-Apr-15 | 7-Apr-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Kanhchriech | Kanhchriech | 2015 | Law on Suppression of Sexual Exploitation | Community Awareness | PVG/052/15 | 1 | 19 | 27 | 0 | 0 | 46 | $192.60 | 7-Apr-15 | 7-Apr-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Svay Antor | Svay Antor | 2015 | Village and Commune Safety Policy | Community Awareness | PVG/048/15 | 1 | 22 | 28 | 1 | 4 | 50 | $210.00 | 7-Apr-15 | 7-Apr-15 | District Police Inspectorate | Theoun Chanthol |
| Banteay Meanchey | Svay Chek | Phkoam | 2015 | Law on Migration | Community Awareness | BMC/030/15 | 1 | 22 | 45 | 1 | 8 | 67 | $310.00 | 8-Apr-15 | 8-Apr-15 | District Office of Social Affairs | Chan Cheko |
| Banteay Meanchey | Mongkol Borei | Bat Trang | 2015 | Law against Domestic Violence | Community Awareness | BMC/031/15 | 1 | 22 | 50 | 0 | 6 | 72 | $311.00 | 8-Apr-15 | 8-Apr-15 | District Office of Women’s Affairs | Duch San |
| Kampong Chhnang | Rolea B'ier | Rolea B'ier | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/045/15 | 1 | 30 | 57 | 0 | 4 | 87 | $216.50 | 8-Apr-15 | 8-Apr-15 | Provincial Department of Social Affairs | Chheang Chanthy |
| Kampong Thom | Baray | Bak Sna | 2015 | Traffic Law and Public Order | Community Awareness | KPT/049/15 | 1 | 43 | 15 | 1 | 0 | 58 | $214.00 | 8-Apr-15 | 8-Apr-15 | District Police Inspectorate | Chin Vicheth |
| Prey Veng | Kamchay Mear | Cheach | 2015 | Law against Domestic Violence | Community Awareness | PVG/051/15 | 1 | 7 | 42 | 1 | 2 | 49 | $178.10 | 8-Apr-15 | 8-Apr-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Kanhchriech | Kanhchriech | 2015 | Law against Domestic Violence | Community Awareness | PVG/053/15 | 1 | 11 | 36 | 1 | 0 | 47 | $192.60 | 8-Apr-15 | 8-Apr-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Svay Antor | Svay Antor | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | PVG/049/15 | 1 | 26 | 19 | 0 | 0 | 45 | $204.00 | 8-Apr-15 | 8-Apr-15 | District Police Inspectorate | Theoun Chanthol |
| Banteay Meanchey | Thma Puok | Kumru | 2015 | Traffic Law and Public Order | Community Awareness | BMC/033/15 | 1 | 47 | 33 | 2 | 0 | 80 | $344.00 | 9-Apr-15 | 9-Apr-15 | Commune/Sangkat Police Post | Khut Sorphorn |
| Battambang | Moung Ruessei | Chrey | 2015 | Law against Women and children rape | Community Awareness | BAT/048/15 | 1 | 22 | 36 | 0 | 0 | 58 | $210.62 | 9-Apr-15 | 9-Apr-15 | District Administration/Council | Ou Bopha Champa |
| Battambang | Bavel | Boeung Pram | 2015 | Law against Domestic Violence | Community Awareness | BAT/046/15 | 1 | 16 | 26 | 0 | 0 | 42 | $207.00 | 9-Apr-15 | 9-Apr-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Koas Krala | Doun Ba | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/047/15 | 1 | 17 | 15 | 5 | 11 | 32 | $197.00 | 9-Apr-15 | 9-Apr-15 | District Police Inspectorate | Siek Phea |
| Kampong Cham | Prey Chhor | Baray | 2015 | Law on Migration | Community Awareness | KPC/040/15 | 1 | 33 | 20 | 2 | 2 | 53 | $195.00 | 9-Apr-15 | 9-Apr-15 | District Women and Children’s Consultative Committees (WCCC) | Touch Vath |
| Kampong Chhnang | Kampong Chhnang | Kampong Chhnang | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/047/15 | 1 | 24 | 48 | 3 | 0 | 72 | $203.75 | 9-Apr-15 | 9-Apr-15 | District Police Inspectorate | Chai Khemrath |
| Kampong Chhnang | Kampong Leaeng | Kampong Hau | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/046/15 | 1 | 35 | 32 | 0 | 0 | 67 | $204.50 | 9-Apr-15 | 9-Apr-15 | Provincial Department of Social Affairs | Chheang Chanthy |
| Kampong Thom | Stoung | Chamna Kraom | 2015 | Law against Domestic Violence | Community Awareness | KPT/050/15 | 1 | 48 | 13 | 0 | 0 | 61 | $193.00 | 9-Apr-15 | 9-Apr-15 | District Office of Women’s Affairs | Pa Bopha |
| Prey Veng | Ba Phnum | Boeng Preah | 2015 | Traffic Law and Public Order | Community Awareness | PVG/054/15 | 1 | 9 | 33 | 0 | 0 | 42 | $197.60 | 9-Apr-15 | 9-Apr-15 | District Police Inspectorate | Lay Sakun |
| Prey Veng | Kanhchriech | Kanhchriech | 2015 | Public Forum/Community Forum | Community Awareness | PVG/055/15 | 1 | 15 | 69 | 0 | 0 | 84 | $239.00 | 9-Apr-15 | 9-Apr-15 | District Police Inspectorate | Yim Sarim |
| Banteay Meanchey | Mongkol Borei | Ruessei Kraok | 2015 | Law against Domestic Violence | Community Awareness | BMC/032/15 | 1 | 35 | 59 | 3 | 9 | 94 | $311.00 | 10-Apr-15 | 10-Apr-15 | District Office of Women’s Affairs | Duch San |
| Banteay Meanchey | Thma Puok | Kumru | 2015 | Law against Domestic Violence | Community Awareness | BMC/034/15 | 1 | 31 | 21 | 0 | 0 | 52 | $260.50 | 10-Apr-15 | 10-Apr-15 | District WCCC | Loeum Sokha |
| Battambang | Sangkae | Ou Dambang Pir | 2015 | Law against Domestic Violence | Community Awareness | BAT/049/15 | 1 | 19 | 15 | 0 | 0 | 34 | $200.00 | 10-Apr-15 | 10-Apr-15 | Commune/Sangkat Police Post | Soeng Dieb |
| Battambang | Banan | Kantueu Pir | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | BAT/050/15 | 1 | 6 | 34 | 0 | 1 | 40 | $202.00 | 10-Apr-15 | 10-Apr-15 | District Administration/Council | Theam Chantho |
| Kampong Cham | Chamkar Leu | Bos Khnor | 2015 | Drug business/use prevention | Community Awareness | KPC/037/15 | 1 | 32 | 23 | 0 | 2 | 55 | $193.00 | 10-Apr-15 | 10-Apr-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Chhnang | Kampong Tralach | Chhuk Sa | 2015 | Law against Domestic Violence | Community Awareness | KCH/042/15 | 1 | 37 | 39 | 3 | 5 | 76 | $210.50 | 20-Apr-15 | 20-Apr-15 | District Office of Women’s Affairs | Kim Sopheap |
| Kampong Thom | Stoung | Banteay Stoung | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPT/054/15 | 1 | 20 | 52 | 0 | 0 | 72 | $196.00 | 20-Apr-15 | 20-Apr-15 | District Police Inspectorate | Chhiv Sarim |
| Prey Veng | Ba Phnum | Boeng Preah | 2015 | Law against Domestic Violence | Community Awareness | PVG/059/15 | 1 | 13 | 37 | 0 | 0 | 50 | $220.00 | 20-Apr-15 | 20-Apr-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Kamchay Mear | Cheach | 2015 | Traffic Law and Public Order | Community Awareness | PVG/058/15 | 1 | 52 | 28 | 0 | 1 | 80 | $254.00 | 20-Apr-15 | 20-Apr-15 | District Police Inspectorate | Uy Noeun |
| Banteay Meanchey | Thma Puok | Pkoam | 2015 | Law against Domestic Violence | Community Awareness | BMC/035/15 | 1 | 16 | 61 | 0 | 0 | 77 | $310.00 | 21-Apr-15 | 21-Apr-15 | District Office of Social Affairs | Net Sophorn |
| Battambang | Koas Krala | Doun Ba | 2015 | Law against Domestic Violence | Community Awareness | BAT/053/15 | 1 | 17 | 17 | 2 | 0 | 34 | $212.00 | 21-Apr-15 | 21-Apr-15 | District Office of Women’s Affairs | Khhourn Saory |
| Kampong Cham | Chamkar Leu | Bos Khnor | 2015 | Law against Domestic Violence | Community Awareness | KPC/039/15 | 1 | 32 | 33 | 0 | 0 | 65 | $215.00 | 21-Apr-15 | 21-Apr-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Prey Chhor | Lvea | 2015 | Drug business/use prevention | Community Awareness | KPC/041/15 | 1 | 27 | 29 | 4 | 18 | 56 | $195.00 | 21-Apr-15 | 21-Apr-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Chhnang | Baribour | Melum | 2015 | Law against Domestic Violence | Community Awareness | KCH/048/15 | 1 | 29 | 38 | 2 | 3 | 67 | $205.00 | 21-Apr-15 | 21-Apr-15 | District Office of Women’s Affairs | Duong Sokhom |
| Kampong Thom | Baray | Bak Sna | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPT/054/15 | 1 | 25 | 33 | 0 | 0 | 58 | $210.00 | 21-Apr-15 | 21-Apr-15 | District Police Inspectorate | Chin Vicheth |
| Prey Veng | Preah Sdach | Preah Sdach | 2015 | Law against Domestic Violence | Community Awareness | PVG/056/15 | 1 | 25 | 36 | 0 | 0 | 61 | $217.00 | 21-Apr-15 | 21-Apr-15 | District Office of Women’s Affairs | Khiev Saphean |
| Prey Veng | Ba Phnum | Boeng Preah | 2015 | Law against Domestic Violence | Community Awareness | PVG/060/15 | 1 | 10 | 35 | 0 | 0 | 45 | $206.00 | 21-Apr-15 | 21-Apr-15 | District Office of Women’s Affairs | Prach Saroeun |
| Banteay Meanchey | Mongkol Borei | Bat Trang | 2015 | Village and Commune Safety Policy | Community Awareness | BMC/036/15 | 1 | 19 | 51 | 1 | 0 | 70 | $306.00 | 22-Apr-15 | 22-Apr-15 | Commune/Sangkat Police Post | Krai Soeng |
| Battambang | Sangkae | Kantueu Pir | 2015 | Law against Women and children rape | Community Awareness | BAT/051/15 | 1 | 15 | 12 | 1 | 1 | 27 | $205.50 | 22-Apr-15 | 22-Apr-15 | Commune/Sangkat Police Post | Soeng Dieb |
| Battambang | Moung Ruessei | Chrey | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | BAT/054/15 | 1 | 17 | 17 | 0 | 2 | 34 | $203.44 | 22-Apr-15 | 22-Apr-15 | District Administration/Council | Chea Daravuth |
| Battambang | Banan | Kantueu Pir | 2015 | Law against Domestic Violence | Community Awareness | BAT/055/15 | 1 | 10 | 28 | 1 | 1 | 38 | $204.00 | 22-Apr-15 | 22-Apr-15 | District Administration/Council | Theam Chantho |
| Battambang | Bavel | Boeung Pram | 2015 | Law against Women and children rape | Community Awareness | BAT/056/15 | 1 | 16 | 30 | 0 | 4 | 46 | $203.00 | 22-Apr-15 | 22-Apr-15 | District Office of Women’s Affairs | Sem Pov |
| Kampong Cham | Prey Chhor | Lvea | 2015 | Law against Domestic Violence | Community Awareness | KPC/045/15 | 1 | 33 | 32 | 0 | 0 | 65 | $215.00 | 22-Apr-15 | 22-Apr-15 | District WCCC | Touch Vath |
| Kampong Chhnang | Kampong Chhnang | Kampong Chhnang | 2015 | Drug business/use prevention | Community Awareness | KCH/047/15 | 1 | 43 | 39 | 37 | 36 | 82 | $216.00 | 22-Apr-15 | 22-Apr-15 | District Police Inspectorate | Chhai Khemrath |
| Prey Veng | Preah Sdach | Preah Sdach | 2015 | Penal and Civil Law | Community Awareness | PVG/061/15 | 1 | 24 | 26 | 0 | 0 | 50 | $190.00 | 22-Apr-15 | 22-Apr-15 | District Police Inspectorate | Nuon Sakhorn |
| Banteay Meanchey | Preah Netr Preah | Phnom Leap | 2015 | Law on Migration | Community Awareness | BMC/037/15 | 1 | 39 | 17 | 0 | 0 | 56 | $259.00 | 23-Apr-15 | 24-Apr-15 | District Office of Social Affairs | Sun Sokchea |
| Battambang | Sangkae | Ou Dambang Pir | 2015 | Drug business/use prevention | Community Awareness | BAT/052/15 | 1 | 12 | 21 | 7 | 19 | 33 | $212.00 | 23-Apr-15 | 23-Apr-15 | Commune/Sangkat Police Post | Soeng Dieb |
| Kampong Cham | Stueng Trang | Areaks Tnot | 2015 | Law against Domestic Violence | Community Awareness | KPC/047/15 | 1 | 26 | 53 | 0 | 0 | 79 | $195.00 | 23-Apr-15 | 23-Apr-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Chamkar Leu | Svay Teab | 2015 | Law on Migration | Community Awareness | KPC/050/15 | 1 | 12 | 44 | 0 | 0 | 56 | $195.00 | 23-Apr-15 | 23-Apr-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Thom | Stoung | Chamna Kraom | 2015 | Village and Commune Safety Policy | Community Awareness | KPT/052/15 | 1 | 53 | 7 | 0 | 0 | 60 | $187.00 | 23-Apr-15 | 23-Apr-15 | District Police Inspectorate | Chhiv Sarim |
| Prey Veng | Preah Sdach | Preah Sdach | 2015 | Law against Domestic Violence | Community Awareness | PVG/057/15 | 1 | 11 | 44 | 0 | 0 | 55 | $217.00 | 23-Apr-15 | 23-Apr-15 | District Office of Women’s Affairs | Khiev Saphean |
| Banteay Meanchey | Mongkol Borei | Ruessei Kraok | 2015 | Village and Commune Safety Policy | Community Awareness | BMC/038/15 | 1 | 34 | 45 | 0 | 0 | 79 | $311.00 | 24-Apr-15 | 24-Apr-15 | Commune/Sangkat Police Post | Ouk Bunthon |
| Battambang | Banan | Kantueu Pir | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/058/15 | 1 | 16 | 19 | 0 | 0 | 35 | $204.00 | 24-Apr-15 | 24-Apr-15 | Commune/Sangkat Police Post | Duong Phen |
| Kampong Cham | Prey Chhor | Baray | 2015 | Law against Domestic Violence | Community Awareness | KPC/046/15 | 1 | 14 | 41 | 0 | 0 | 55 | $200.00 | 24-Apr-15 | 24-Apr-15 | District WCCC | Touch Vath |
| Kampong Chhnang | Kampong Leaeng | Kampong Hau | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/049/15 | 1 | 44 | 26 | 43 | 26 | 70 | $204.50 | 24-Apr-15 | 24-Apr-15 | District Police Inspectorate | Seng Chenda |
| Kampong Thom | Baray | Bak Sna | 2015 | Law against Domestic Violence | Community Awareness | KPT/055/15 | 1 | 26 | 30 | 0 | 0 | 56 | $197.00 | 24-Apr-15 | 24-Apr-15 | District Office of Women’s Affairs | Man Chantrea |
| Battambang | Moung Ruessei | Chrey | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/059/15 | 1 | 38 | 23 | 0 | 0 | 61 | $213.80 | 27-Apr-15 | 27-Apr-15 | Commune/Sangkat Police Post | Lay Chham |
| Battambang | Bavel | Boeung Pram | 2015 | Law against Women and children rape | Community Awareness | BAT/057/15 | 1 | 11 | 32 | 2 | 12 | 43 | $198.00 | 27-Apr-15 | 27-Apr-15 | District Office of Women’s Affairs | Sem Pov |
| Kampong Cham | Chamkar Leu | Svay Teab | 2015 | Law against Domestic Violence | Community Awareness | KPC/049/15 | 1 | 6 | 53 | 0 | 0 | 59 | $195.00 | 27-Apr-15 | 27-Apr-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Prey Chhor | Lvea | 2015 | Traffic Law and Public Order | Community Awareness | KPC/042/15 | 1 | 29 | 26 | 13 | 7 | 55 | $194.00 | 27-Apr-15 | 27-Apr-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Chhnang | Kampong Tralach | Chhuk Sa | 2015 | Drug business/use prevention | Community Awareness | KCH/051/15 | 1 | 43 | 24 | 12 | 7 | 67 | $213.10 | 27-Apr-15 | 27-Apr-15 | District Police Inspectorate | Hul Veasna |
| Kampong Thom | Stoung | Chamna Kraom | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPT/053/15 | 1 | 30 | 30 | 0 | 0 | 60 | $187.00 | 27-Apr-15 | 27-Apr-15 | District Police Inspectorate | Chhiv Sarim |
| Battambang | Koas Krala | Doun Ba | 2015 | Drug business/use prevention | Community Awareness | BAT/060/15 | 1 | 9 | 25 | 0 | 1 | 34 | $212.00 | 28-Apr-15 | 28-Apr-15 | District Police Inspectorate | Siek Phea |
| Kampong Cham | Stueng Trang | Areaks Tnot | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/048/15 | 1 | 79 | 23 | 0 | 0 | 102 | $200.00 | 28-Apr-15 | 28-Apr-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Chamkar Leu | Bos Khnor | 2015 | Drug business/use prevention | Community Awareness | KPC/043/15 | 1 | 23 | 30 | 7 | 9 | 53 | $195.00 | 28-Apr-15 | 28-Apr-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Chhnang | Baribour | Melum | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/048/15 | 1 | 11 | 60 | 0 | 0 | 71 | $214.00 | 28-Apr-15 | 28-Apr-15 | District Office of Women’s Affairs | Duong Sokhom |
| Kampong Thom | Stoung | Banteay Stoung | 2015 | Law against Domestic Violence | Community Awareness | KPT/056/15 | 1 | 51 | 19 | 0 | 0 | 70 | $205.00 | 28-Apr-15 | 28-Apr-15 | District Office of Women’s Affairs | Pa Bopha |
| Kampong Cham | Chamkar Leu | Svay Teab | 2015 | Traffic Law and Public Order | Community Awareness | KPC/044/15 | 1 | 33 | 35 | 3 | 4 | 68 | $214.00 | 29-Apr-15 | 29-Apr-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Chhnang | Rolea B'ier | Rolea B'ier | 2015 | Drug business/use prevention | Community Awareness | KCH/050/15 | 1 | 32 | 40 | 25 | 30 | 72 | $201.75 | 29-Apr-15 | 29-Apr-15 | District Police Inspectorate | Yin Saly |
| Kampong Chhnang | Kampong Chhnang | B'er | 2015 | Drug business/use prevention | Community Awareness | KCH/052/15 | 1 | 27 | 51 | 17 | 1 | 78 | $225.50 | 1-May-15 | 1-May-15 | District Police Inspectorate | Chhai Khemrath |
| Kampong Cham | Chamkar Leu | Chamkar Andoung | 2015 | Traffic Law and Public Order | Community Awareness | KPC/051/15 | 1 | 14 | 51 | 0 | 0 | 65 | $195.00 | 5-May-15 | 5-May-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Thom | Stueng Saen | Kampong Roteh | 2015 | Law against Domestic Violence | Community Awareness | KPT/057/15 | 1 | 22 | 43 | 0 | 0 | 65 | $204.00 | 5-May-15 | 5-May-15 | District Office of Women’s Affairs | Chum Kesasophea |
| Prey Veng | Svay Antor | Me Bon | 2015 | Law against Domestic Violence | Community Awareness | PVG/062/15 | 1 | 10 | 37 | 0 | 0 | 47 | $209.90 | 5-May-15 | 5-May-15 | District Office of Women’s Affairs | Chhim Chankhantey |
| Kampong Cham | Prey Chhor | Kor | 2015 | Law against Domestic Violence | Community Awareness | KPC/053/15 | 1 | 8 | 50 | 0 | 3 | 58 | $200.00 | 6-May-15 | 6-May-15 | District WCCC | Touch Vath |
| Banteay Meanchey | Preah Netr Preah | Bos Sbov | 2015 | Traffic Law and Public Order | Community Awareness | BMC/039/15 | 1 | 30 | 33 | 0 | 0 | 63 | $308.50 | 7-May-15 | 7-May-15 | Commune/Sangkat Police Post | Bear Chov |
| Kampong Chhnang | Kampong Tralach | Saeb | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/054/15 | 1 | 40 | 28 | 5 | 0 | 68 | $202.00 | 7-May-15 | 7-May-15 | District Police Inspectorate | Hul Veasna |
| Kampong Chhnang | Baribour | Chak | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/055/15 | 1 | 18 | 54 | 0 | 0 | 72 | $200.00 | 7-May-15 | 7-May-15 | District Police Inspectorate | Cheang Sovanarith |
| Kampong Thom | Kampong Svay | Kampong Svay | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPT/058/15 | 1 | 15 | 38 | 0 | 0 | 53 | $200.00 | 7-May-15 | 7-May-15 | District Police Inspectorate | Ke Kanchna |
| Prey Veng | Kanhchriech | Tnaot | 2015 | Law against Domestic Violence | Community Awareness | PVG/064/15 | 1 | 12 | 36 | 0 | 0 | 48 | $212.00 | 7-May-15 | 7-May-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Svay Antor | Me Bon | 2015 | Village and Commune Safety Policy | Community Awareness | PVG/063/15 | 1 | 32 | 9 | 0 | 0 | 41 | $200.00 | 7-May-15 | 7-May-15 | District Police Inspectorate | Theoun Chanthol |
| Banteay Meanchey | Svay Chek | Sarongk | 2015 | Law on Migration | Community Awareness | BMC/042/15 | 1 | 16 | 27 | 0 | 0 | 43 | $183.00 | 8-May-15 | 8-May-15 | District Office of Social Affairs | Chan Cheko |
| Banteay Meanchey | Mongkol Borei | Banteay Neang | 2015 | Law against Domestic Violence | Community Awareness | BMC/041/15 | 1 | 4 | 41 |  |  | 45 | $185.90 | 8-May-15 | 8-May-15 | District Office of Women’s Affairs | Duch San |
| Battambang | Bavel | Prey Khpos | 2015 | Law against Domestic Violence | Community Awareness | BAT/061/15 | 1 | 29 | 14 | 7 | 2 | 43 | $199.00 | 8-May-15 | 8-May-15 | District Office of Women’s Affairs | Sem Pov |
| Kampong Cham | Stueng Trang | Preaek Bak | 2015 | Law against Domestic Violence | Community Awareness | KPC/055/15 | 1 | 14 | 50 | 0 | 0 | 64 | $195.00 | 8-May-15 | 8-May-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Chhnang | Rolea B'ier | Krang Leav | 2015 | Law against Domestic Violence | Community Awareness | KCH/053/15 | 1 | 30 | 50 | 0 | 2 | 80 | $201.75 | 8-May-15 | 8-May-15 | District Office of Women’s Affairs | You Sokreth |
| Kampong Chhnang | Kampong Leaeng | Pou | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/056/15 | 1 | 29 | 39 | 0 | 0 | 68 | $203.00 | 8-May-15 | 8-May-15 | Provincial Department of Social Affairs | Chheang Chanthy |
| Kampong Thom | Stoung | Popok | 2015 | Law against Domestic Violence | Community Awareness | KPT/059/15 | 1 | 41 | 24 | 0 | 0 | 65 | $212.00 | 8-May-15 | 8-May-15 | District Office of Women’s Affairs | Pa Bopha |
| Prey Veng | Ba Phnum | Cheung Phnum | 2015 | Traffic Law and Public Order | Community Awareness | PVG/066/15 | 1 | 8 | 42 | 0 | 0 | 50 | $220.00 | 8-May-15 | 8-May-15 | District Police Inspectorate | Lay Sakun |
| Banteay Meanchey | Svay Chek | Roluos | 2015 | Law against Domestic Violence | Community Awareness | BMC/040/15 | 1 | 16 | 56 | 0 | 1 | 72 | $310.00 | 11-May-15 | 11-May-15 | District Office of Women’s Affairs | Nith Sophaon |
| Battambang | Sangkae | Anlong Vil | 2015 | Drug business/use prevention | Community Awareness | BAT/062/15 | 1 | 21 | 25 | 19 | 23 | 46 | $219.00 | 11-May-15 | 11-May-15 | Commune/Sangkat Police Post | Chea Vandy |
| Kampong Cham | Chamkar Leu | Chamkar Andoung | 2015 | Drug business/use prevention | Community Awareness | KPC/052/15 | 1 | 21 | 35 | 6 | 5 | 56 | $200.00 | 11-May-15 | 11-May-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Chhnang | Kampong Chhnang | B'er | 2015 | Law against Domestic Violence | Community Awareness | KCH/058/15 | 1 | 29 | 38 | 0 | 4 | 67 | $192.00 | 11-May-15 | 11-May-15 | District Office of Women’s Affairs | Mey Sinat |
| Kampong Chhnang | Baribour | Chak | 2015 | Law against Domestic Violence | Community Awareness | KCH/059/15 | 1 | 17 | 53 | 2 | 2 | 70 | $204.00 | 11-May-15 | 11-May-15 | District Office of Women’s Affairs | Duong Sokhom |
| Kampong Thom | Baray | Ballangk | 2015 | Drug business/use prevention | Community Awareness | KPT/061/15 | 1 | 30 | 30 | 6 | 10 | 60 | $203.00 | 11-May-15 | 11-May-15 | District Police Inspectorate | Heang Buntha |
| Prey Veng | Kamchay Mear | Krabau | 2015 | Law against Domestic Violence | Community Awareness | PVG/067/15 | 1 | 9 | 41 | 0 | 5 | 50 | $185.00 | 11-May-15 | 11-May-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Preah Sdach | Sena Reach Otdam | 2015 | Law against Domestic Violence | Community Awareness | PVG/069/15 | 1 | 7 | 48 | 0 | 1 | 55 | $217.00 | 11-May-15 | 11-May-15 | District Office of Women’s Affairs | Khiev Saphean |
| Banteay Meanchey | Mongkol Borei | Banteay Neang | 2015 | Law against Domestic Violence | Community Awareness | BMC/041/15 | 1 | 5 | 54 | 0 | 0 | 59 | $205.90 | 12-May-15 | 12-May-15 | District Office of Women’s Affairs | Duch San |
| Banteay Meanchey | Thma Puok | Kouk Romiet | 2015 | Law against Domestic Violence | Community Awareness | BMC/043/15 | 1 | 8 | 37 | 0 | 0 | 45 | $191.00 | 12-May-15 | 12-May-15 | District WCCC | Loeum Sokha |
| Battambang | Moung Ruessei | Ruessei Krang | 2015 | Law against Domestic Violence | Community Awareness | BAT/063/15 | 1 | 40 | 35 | 0 | 0 | 75 | $212.00 | 12-May-15 | 12-May-15 | District Administration/Council | Ou Bopha Champa |
| Battambang | Koas Krala | Preah Phos | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/064/15 | 1 | 21 | 22 | 0 | 0 | 43 | $204.80 | 12-May-15 | 12-May-15 | District Police Inspectorate | Siek Phea |
| Kampong Cham | Prey Chhor | Kor | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/054/15 | 1 | 29 | 32 | 0 | 0 | 61 | $200.00 | 12-May-15 | 12-May-15 | District WCCC | Touch Vath |
| Kampong Chhnang | Kampong Leaeng | Pou | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/060/15 | 1 | 33 | 35 | 0 | 0 | 68 | $202.00 | 12-May-15 | 12-May-15 | District Police Inspectorate | Seng Chenda |
| Kampong Chhnang | Rolea B'ier | Krang Leav | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/057/15 | 1 | 14 | 58 | 2 | 3 | 72 | $205.65 | 12-May-15 | 12-May-15 | Provincial Department of Social Affairs | Chheang Chanthy |
| Kampong Thom | Kampong Svay | Kampong Svay | 2015 | Law against Domestic Violence | Community Awareness | KPT/062/15 | 1 | 12 | 69 | 0 | 0 | 81 | $210.00 | 12-May-15 | 12-May-15 | District Office of Women’s Affairs | Dep Chenda |
| Kampong Thom | Stoung | Popok | 2015 | Village and Commune Safety Policy | Community Awareness | KPT/060/15 | 1 | 64 | 1 | 0 | 0 | 65 | $206.00 | 12-May-15 | 12-May-15 | District Police Inspectorate | Chhiv Sarim |
| Prey Veng | Kanhchriech | Tnaot | 2015 | Law against Women and children rape | Community Awareness | PVG/065/15 | 1 | 10 | 43 | 0 | 0 | 53 | $190.50 | 12-May-15 | 12-May-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Kamchay Mear | Krabau | 2015 | Law against Domestic Violence | Community Awareness | PVG/068/15 | 1 | 12 | 34 | 2 | 7 | 46 | $168.90 | 12-May-15 | 12-May-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Preah Sdach | Sena Reach Otdam | 2015 | Law against Domestic Violence | Community Awareness | PVG/070/15 | 1 | 2 | 64 | 0 | 0 | 66 | $205.00 | 12-May-15 | 12-May-15 | District Office of Women’s Affairs | Khiev Saphean |
| Kampong Chhnang | Kampong Tralach | Saeb | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/061/15 | 1 | 35 | 36 | 1 | 4 | 71 | $202.00 | 13-May-15 | 13-May-15 | District Office of Women’s Affairs | Kim Sopheap |
| Kampong Thom | Stueng Saen | Kampong Roteh | 2015 | Village and Commune Safety Policy | Community Awareness | KPT/063/15 | 1 | 40 | 25 | 0 | 0 | 65 | $196.00 | 13-May-15 | 13-May-15 | District Police Inspectorate | Heng Sinath |
| Kampong Cham | Chamkar Leu | Lvea Leu | 2015 | Law against Domestic Violence | Community Awareness | KPC/056/15 | 1 | 15 | 52 | 8 | 21 | 67 | $195.00 | 18-May-15 | 18-May-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Chhnang | Baribour | Chak | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/059/15 | 1 | 18 | 54 | 2 | 2 | 72 | $205.00 | 18-May-15 | 18-May-15 | District Office of Women’s Affairs | Duong Sokhom |
| Kampong Thom | Stueng Saen | Ou Kanthor | 2015 | Drug business/use prevention | Community Awareness | KPT/064/15 | 1 | 63 | 66 | 39 | 38 | 129 | $206.00 | 18-May-15 | 18-May-15 | District Police Inspectorate | Heng Sinath |
| Prey Veng | Kamchay Mear | Krabau | 2015 | Traffic Law and Public Order | Community Awareness | PVG/071/15 | 1 | 45 | 35 | 0 | 0 | 80 | $254.00 | 18-May-15 | 18-May-15 | District Police Inspectorate | Uy Noeun |
| Banteay Meanchey | Mongkol Borei | Banteay Neang | 2015 | Village and Commune Safety Policy | Community Awareness | BMC/045/15 | 1 | 38 | 70 | 1 | 1 | 108 | $207.60 | 19-May-15 | 19-May-15 | Commune/Sangkat Police Post | So Sophal |
| Banteay Meanchey | Thma Puok | Kouk Romiet | 2015 | Traffic Law and Public Order | Community Awareness | BMC/046/15 | 1 | 31 | 36 | 26 | 33 | 67 | $231.00 | 19-May-15 | 19-May-15 | Commune/Sangkat Police Post | Nith Meat |
| Kampong Cham | Chamkar Leu | Lvea Leu | 2015 | Law against Domestic Violence | Community Awareness | KPC/056/15 | 1 | 19 | 42 | 0 | 0 | 61 | $195.00 | 19-May-15 | 19-May-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Stueng Trang | Preak Kak | 2015 | Village and Commune Safety Policy | Community Awareness | KPC/058/15 | 1 | 31 | 52 | 0 | 0 | 83 | $215.00 | 19-May-15 | 19-May-15 | District Police Inspectorate | Soeun Tit |
| Kampong Chhnang | Kampong Chhnang | B'er | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/058/15 | 1 | 20 | 42 | 0 | 0 | 62 | $192.00 | 19-May-15 | 19-May-15 | District Office of Women’s Affairs | Mey Sinat |
| Prey Veng | Ba Phnum | Cheung Phnum | 2015 | Law against Domestic Violence | Community Awareness | PVG/072/15 | 1 | 13 | 29 | 0 | 0 | 42 | $197.60 | 19-May-15 | 19-May-15 | District Office of Women’s Affairs | Prach Saroeun |
| Banteay Meanchey | Mongkol Borei | Rohat Tuek | 2015 | Village and Commune Safety Policy | Community Awareness | BMC/044/15 | 1 | 44 | 24 | 1 | 0 | 68 | $207.60 | 20-May-15 | 20-May-15 | Commune/Sangkat Police Post | Yat Hiek |
| Banteay Meanchey | Svay Chek | Treas | 2015 | Law on Migration | Community Awareness | BMC/047/15 | 1 | 34 | 33 | 0 | 2 | 67 | $307.00 | 20-May-15 | 20-May-15 | District Office of Women’s Affairs | Chan Cheko |
| Battambang | Sangkae | Anlong Vil | 2015 | Education for Gangs | Community Awareness | BAT/065/15 | 1 | 15 | 21 | 15 | 21 | 36 | $194.30 | 20-May-15 | 20-May-15 | Commune/Sangkat Police Post | Chea Vandy |
| Battambang | Bavel | Prey Khpos | 2015 | Law against Women and children rape | Community Awareness | BAT/069/15 | 1 | 18 | 28 | 5 | 3 | 46 | $203.00 | 20-May-15 | 20-May-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Koas Krala | Preah Phos | 2015 | Law against Domestic Violence | Community Awareness | BAT/070/15 | 1 | 14 | 20 | 0 | 0 | 34 | $204.80 | 20-May-15 | 20-May-15 | District Office of Women’s Affairs | Khhourn Saory |
| Kampong Cham | Prey Chhor | Kor | 2015 | Drug business/use prevention | Community Awareness | KPC/059/15 | 1 | 32 | 31 | 2 | 5 | 63 | $204.00 | 20-May-15 | 20-May-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Thom | Stoung | Popok | 2015 | Traffic Law and Public Order | Community Awareness | KPT/067/15 | 1 | 44 | 21 | 3 | 19 | 65 | $206.00 | 20-May-15 | 20-May-15 | District Police Inspectorate | Chhiv Sarim |
| Prey Veng | Ba Phnum | Cheung Phnum | 2015 | Law against Domestic Violence | Community Awareness | PVG/075/15 | 1 | 16 | 24 | 0 | 0 | 40 | $192.00 | 20-May-15 | 20-May-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Svay Antor | Me Bon | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | PVG/073/15 | 1 | 19 | 22 | 0 | 0 | 41 | $200.00 | 20-May-15 | 20-May-15 | District Police Inspectorate | Theoun Chanthol |
| Prey Veng | Kanhchriech | Tnaot | 2015 | Public Forum/Community Forum | Community Awareness | PVG/074/15 | 1 | 17 | 57 | 0 | 0 | 74 | $206.60 | 20-May-15 | 20-May-15 | District Police Inspectorate | Yim Sarim |
| Banteay Meanchey | Thma Puok | Kouk Romiet | 2015 | Law against Domestic Violence | Community Awareness | BMC/048/15 | 1 | 23 | 24 | 0 | 0 | 47 | $191.00 | 21-May-15 | 21-May-15 | District WCCC | Loeum Sokha |
| Battambang | Banan | Chheu Teal | 2015 | Law against Women and children rape | Community Awareness | BAT/068/15 | 1 | 12 | 33 | 0 | 2 | 45 | $202.00 | 21-May-15 | 21-May-15 | District Administration/Council | Theam Chantho |
| Kampong Chhnang | Kampong Leaeng | Pou | 2015 | Law against Domestic Violence | Community Awareness | KCH/062/15 | 1 | 8 | 57 | 0 | 0 | 65 | $204.00 | 21-May-15 | 21-May-15 | District Office of Women’s Affairs | Sorn Sarum |
| Kampong Thom | Stueng Saen | Ou Kanthor | 2015 | Law against Domestic Violence | Community Awareness | KPT/068/15 | 1 | 6 | 59 | 0 | 1 | 65 | $194.00 | 21-May-15 | 21-May-15 | District Office of Women’s Affairs | Dum Kesasophea |
| Banteay Meanchey | Mongkol Borei | Rohat Tuek | 2015 | Law against Domestic Violence | Community Awareness | BMC/049/15 | 1 | 11 | 37 | 0 | 0 | 48 | $205.90 | 22-May-15 | 22-May-15 | District Office of Women’s Affairs | Duch San |
| Banteay Meanchey | Preah Netr Preah | Bos Sbov | 2015 | Law against Domestic Violence | Community Awareness | BMC/050/15 | 1 | 16 | 52 | 0 | 1 | 68 | $304.50 | 22-May-15 | 22-May-15 | District Office of Women’s Affairs | Sun Sokchea |
| Battambang | Sangkae | Anlong Vil | 2015 | Law against Women and children rape | Community Awareness | BAT/066/15 | 1 | 13 | 21 | 11 | 21 | 34 | $196.00 | 22-May-15 | 22-May-15 | Commune/Sangkat Police Post | Chea Vandy |
| Battambang | Moung Ruessei | Ruessei Krang | 2015 | Law against Women and children rape | Community Awareness | BAT/071/15 | 1 | 22 | 39 | 0 | 0 | 61 | $200.50 | 22-May-15 | 22-May-15 | District Administration/Council | Chea Daravuth |
| Kampong Cham | Chamkar Leu | Chamkar Andoung | 2015 | Law against Domestic Violence | Community Awareness | KPC/057/15 | 1 | 18 | 37 | 15 | 13 | 55 | $205.00 | 22-May-15 | 22-May-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Chhnang | Rolea B'ier | Krang Leav | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/063/15 | 1 | 22 | 63 | 2 | 11 | 85 | $201.75 | 22-May-15 | 22-May-15 | District Police Inspectorate | Yin Saly |
| Kampong Thom | Kampong Svay | Kampong Svay | 2015 | Gambling Prevention | Community Awareness | KPT/066/15 | 1 | 37 | 52 | 0 | 0 | 89 | $210.00 | 22-May-15 | 22-May-15 | District Police Inspectorate | Ke Kanchna |
| Kampong Thom | Baray | Ballangk | 2015 | Law against Domestic Violence | Community Awareness | KPT/070/15 | 1 | 44 | 16 | 1 | 0 | 60 | $203.00 | 22-May-15 | 22-May-15 | District Office of Women’s Affairs | Man Chantrea |
| Prey Veng | Preah Sdach | Sena Reach Otdam | 2015 | Public Forum/Community Forum | Community Awareness | PVG/076/15 | 1 | 22 | 43 | 0 | 0 | 65 | $187.00 | 22-May-15 | 22-May-15 | District Police Inspectorate | Nuon Sakhorn |
| Banteay Meanchey | Mongkol Borei | Rohat Tuek | 2015 | Law against Domestic Violence | Community Awareness | BMC/049/15 | 1 | 23 | 29 | 0 | 0 | 52 | $205.90 | 25-May-15 | 25-May-15 | District Office of Women’s Affairs | Duch San |
| Battambang | Banan | Chheu Teal | 2015 | Law against Domestic Violence | Community Awareness | BAT/067/15 | 1 | 9 | 27 | 0 | 1 | 36 | $204.00 | 25-May-15 | 25-May-15 | District Administration/Council | Theam Chantho |
| Battambang | Bavel | Prey Khpos | 2015 | Drug business/use prevention | Community Awareness | BAT/072/15 | 1 | 21 | 20 | 3 | 10 | 41 | $207.00 | 25-May-15 | 25-May-15 | Commune/Sangkat Police Post | Pat Sitha |
| Kampong Cham | Prey Chhor | Sour Saen | 2015 | Drug business/use prevention | Community Awareness | KPC/060/15 | 1 | 22 | 38 | 0 | 0 | 60 | $195.00 | 25-May-15 | 25-May-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Thom | Stueng Saen | Kampong Roteh | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPT/069/15 | 1 | 14 | 51 | 0 | 0 | 65 | $204.00 | 25-May-15 | 25-May-15 | District Office of Women’s Affairs | Dum Kesasophea |
| Battambang | Koas Krala | Preah Phos | 2015 | Drug business/use prevention | Community Awareness | BAT/073/15 | 1 | 14 | 20 | 0 | 0 | 34 | $204.80 | 26-May-15 | 26-May-15 | District Police Inspectorate | Siek Phea |
| Kampong Cham | Chamkar Leu | Lvea Leu | 2015 | Drug business/use prevention | Community Awareness | KPC/061/15 | 1 | 30 | 29 | 7 | 11 | 59 | $205.00 | 26-May-15 | 26-May-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Stueng Trang | Preak Kak | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/063/15 | 1 | 25 | 54 | 0 | 0 | 79 | $200.00 | 26-May-15 | 26-May-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Chhnang | Kampong Tralach | Saeb | 2015 | Law against Domestic Violence | Community Awareness | KCH/061/15 | 1 | 24 | 45 | 0 | 0 | 69 | $205.00 | 26-May-15 | 26-May-15 | District Office of Women’s Affairs | Kim Sopheap |
| Kampong Thom | Stueng Saen | Ou Kanthor | 2015 | Traffic Law and Public Order | Community Awareness | KPT/065/15 | 1 | 28 | 43 | 0 | 0 | 71 | $206.00 | 26-May-15 | 26-May-15 | District Police Inspectorate | Heng Sinath |
| Battambang | Moung Ruessei | Ruessei Krang | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/074/15 | 1 | 56 | 29 | 0 | 0 | 85 | $199.00 | 27-May-15 | 27-May-15 | Commune/Sangkat Police Post | Sun Ra |
| Battambang | Banan | Chheu Teal | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/075/15 | 1 | 11 | 28 | 0 | 0 | 39 | $204.00 | 27-May-15 | 27-May-15 | Commune/Sangkat Police Post | Chea Vann |
| Kampong Cham | Chamkar Leu | Lvea Leu | 2015 | Traffic Law and Public Order | Community Awareness | KPC/062/15 | 1 | 28 | 29 | 26 | 27 | 57 | $194.00 | 27-May-15 | 27-May-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Thom | Baray | Ballangk | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPT/071/15 | 1 | 40 | 20 | 0 | 0 | 60 | $203.00 | 27-May-15 | 27-May-15 | District Police Inspectorate | Heang Buntha |
| Kampong Cham | Prey Chhor | Sour Saen | 2015 | Law against Domestic Violence | Community Awareness | KPC/064/15 | 1 | 31 | 29 | 0 | 0 | 60 | $205.00 | 28-May-15 | 28-May-15 | District WCCC | Touch Vath |
| Banteay Meanchey | Svay Chek | Ta Phou | 2015 | Law against Domestic Violence | Community Awareness | BMC/051/15 | 1 | 17 | 51 | 0 | 1 | 68 | $310.00 | 8-Jun-15 | 8-Jun-15 | District Office of Women’s Affairs | Nith Sophaon |
| Banteay Meanchey | Thma Puok | Banteay Chhmar | 2015 | Traffic Law and Public Order | Community Awareness | BMC/052/15 | 1 | 24 | 25 | 0 | 0 | 49 | $197.00 | 9-Jun-15 | 9-Jun-15 | Commune/Sangkat Police Post | Phae Savith |
| Banteay Meanchey | Svay Chek | Sla Kram | 2015 | Law on Migration | Community Awareness | BMC/053/15 | 1 | 20 | 42 | 0 | 1 | 62 | $310.00 | 11-Jun-15 | 11-Jun-15 | District Office of Social Affairs | Chan Cheko |
| Banteay Meanchey | Preah Netr Preah | Prasat | 2015 | Traffic Law and Public Order | Community Awareness | BMC/054/15 | 1 | 46 | 54 | 46 | 54 | 100 | $372.00 | 10-Jun-15 | 10-Jun-15 | Commune/Sangkat Police Post | Prok Lae |
| Banteay Meanchey | Thma Puok | Banteay Chhmar | 2015 | Law against Domestic Violence | Community Awareness | BMC/055/15 | 1 | 26 | 35 | 0 | 0 | 61 | $197.00 | 11-Jun-15 | 11-Jun-15 | District WCCC | Loeum Sokha |
| Banteay Meanchey | Mongkol Borei | Koy Maeng | 2015 | Law against Domestic Violence | Community Awareness | BMC/056/15 | 1 | 14 | 44 | 0 | 0 | 58 | $200.50 | 12-Jun-15 | 12-Jun-15 | District Office of Women’s Affairs | Duch San |
| Battambang | Bavel | Ampil Pram Daeum | 2015 | Law against Women and children rape | Community Awareness | BAT/076/15 | 1 | 9 | 35 | 4 | 13 | 44 | $207.00 | 9-Jun-15 | 9-Jun-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Moung Ruessei | Kah Kos | 2015 | Law against Domestic Violence | Community Awareness | BAT/077/15 | 1 | 35 | 45 | 0 | 0 | 80 | $217.50 | 10-Jun-15 | 10-Jun-15 | District Administration/Council | Ou Bopha Champa |
| Battambang | Koas Krala | Chhnal Moan | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/078/15 | 1 | 17 | 16 | 0 | 0 | 33 | $212.00 | 11-Jun-15 | 11-Jun-15 | District Police Inspectorate | Siek Phea |
| Battambang | Sangkae | Ta Pon | 2015 | Law against Domestic Violence | Community Awareness | BAT/079/15 | 1 | 14 | 35 | 0 | 0 | 49 | $210.50 | 12-Jun-15 | 12-Jun-15 | Commune/Sangkat Police Post | Neth Kring |
| Battambang | Banan | Chaeng Mean Chey | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/080/15 | 1 | 8 | 35 | 0 | 0 | 43 | $202.00 | 16-Jun-15 | 16-Jun-15 | Commune/Sangkat Police Post | Tiv Chanrith |
| Prey Veng | Svay Antor | Popueus | 2015 | Law against Domestic Violence | Community Awareness | PVG/077/15 | 1 | 24 | 36 | 0 | 0 | 60 | $210.00 | 4-Jun-15 | 4-Jun-15 | District Office of Women’s Affairs | Chhim Chankhantey |
| Prey Veng | Kanhchriech | Kdoeang Reay | 2015 | Law against Domestic Violence | Community Awareness | PVG/078/15 | 1 | 14 | 34 | 0 | 0 | 48 | $211.00 | 9-Jun-15 | 9-Jun-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Kanhchriech | Kdoeang Reay | 2015 | Law against Women and children rape | Community Awareness | PVG/079/15 | 1 | 8 | 41 | 0 | 0 | 49 | $188.50 | 10-Jun-15 | 10-Jun-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Ba Phnum | Chheu Kach | 2015 | Law against Domestic Violence | Community Awareness | PVG/080/15 | 1 | 7 | 39 | 0 | 0 | 46 | $208.80 | 9-Jun-15 | 9-Jun-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Ba Phnum | Chheu Kach | 2015 | Law against Domestic Violence | Community Awareness | PVG/081/15 | 1 | 12 | 38 | 0 | 3 | 50 | $212.00 | 10-Jun-15 | 10-Jun-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Svay Antor | Popueus | 2015 | Village and Commune Safety Policy | Community Awareness | PVG/082/15 | 1 | 7 | 78 | 0 | 0 | 85 | $210.00 | 10-Jun-15 | 10-Jun-15 | District Police Inspectorate | Theoun Chanthol |
| Prey Veng | Svay Antor | Popueus | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | PVG/083/15 | 1 | 19 | 41 | 0 | 1 | 60 | $207.00 | 11-Jun-15 | 11-Jun-15 | District Police Inspectorate | Theoun Chanthol |
| Prey Veng | Kamchay Mear | Kranhung | 2015 | Law against Domestic Violence | Community Awareness | PVG/084/15 | 1 | 13 | 37 | 0 | 0 | 50 | $180.40 | 10-Jun-15 | 10-Jun-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Kamchay Mear | Kranhung | 2015 | Law against Domestic Violence | Community Awareness | PVG/085/15 | 1 | 7 | 43 | 0 | 0 | 50 | $192.90 | 11-Jun-15 | 11-Jun-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Preah Sdach | Krang Svay | 2015 | Law against Domestic Violence | Community Awareness | PVG/086/15 | 1 | 16 | 43 | 1 | 2 | 59 | $217.00 | 10-Jun-15 | 10-Jun-15 | District Office of Women’s Affairs | Khiev Saphean |
| Prey Veng | Preah Sdach | Krang Svay | 2015 | Law against Domestic Violence | Community Awareness | PVG/087/15 | 1 | 8 | 53 | 0 | 0 | 61 | $217.00 | 11-Jun-15 | 11-Jun-15 | District Office of Women’s Affairs | Khiev Saphean |
| Prey Veng | Kanhchriech | Kdoeang Reay | 2015 | Traffic Law and Public Order | Community Awareness | PVG/088/15 | 1 | 42 | 9 | 0 | 0 | 51 | $227.00 | 12-Jun-15 | 12-Jun-15 | District Police Inspectorate | Yim Sarim |
| Kampong Chhnang | Kampong Chhnang | Phsar Chhnang | 2015 | Drug business/use prevention | Community Awareness | KCH/064/15 | 1 | 43 | 30 | 0 | 0 | 73 | $211.50 | 3-Jun-15 | 3-Jun-15 | District Police Inspectorate | Chhai Khemrath |
| Kampong Chhnang | Kampong Chhnang | Phsar Chhnang | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/064/15 | 1 | 23 | 44 | 0 | 3 | 67 | $207.75 | 10-Jun-15 | 10-Jun-15 | District Police Inspectorate | Chhai Khemrath |
| Kampong Chhnang | Rolea B ier | Kouk Banteay | 2015 | Law against Domestic Violence | Community Awareness | KCH/065/15 | 1 | 33 | 38 | 0 | 1 | 71 | $207.65 | 3-Jun-15 | 3-Jun-15 | District Office of Women’s Affairs | You Sokreth |
| Kampong Chhnang | Baribour | Khon Rang | 2015 | Drug business/use prevention | Community Awareness | KCH/066/15 | 1 | 39 | 39 | 25 | 35 | 78 | $227.00 | 5-Jun-15 | 5-Jun-15 | District Police Inspectorate | Cheang Sovanarith |
| Kampong Chhnang | Baribour | Khon Rang | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/066/15 | 1 | 28 | 40 | 1 | 2 | 68 | $200.00 | 8-Jun-15 | 8-Jun-15 | District Police Inspectorate | Cheang Sovanarith |
| Kampong Chhnang | Kampong Leaeng | Svay Rumpear | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/067/15 | 1 | 25 | 45 | 0 | 0 | 70 | $215.00 | 9-Jun-15 | 9-Jun-15 | Provincial Department of Social Affairs | Chheang Chanthy |
| Kampong Chhnang | Rolea B ier | Kouk Banteay | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/068/15 | 1 | 19 | 56 | 1 | 2 | 75 | $216.50 | 15-Jun-15 | 15-Jun-15 | Provincial Department of Social Affairs | Chheang Chanthy |
| Kampong Chhnang | Kampong Tralach | Longveaek | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/069/15 | 1 | 45 | 31 | 0 | 0 | 76 | $219.50 | 9-Jun-15 | 9-Jun-15 | District Police Inspectorate | Hul Veasna |
| Kampong Chhnang | Kampong Leaeng | Svay Rumpear | 2015 | Law against Domestic Violence | Community Awareness | KCH/070/15 | 1 | 11 | 54 | 0 | 0 | 65 | $205.00 | 11-Jun-15 | 11-Jun-15 | District Office of Women’s Affairs | Sorn Sarum |
| Kampong Cham | Stueng Trang | Preaek Bak | 2015 | Law against Domestic Violence | Community Awareness | KPC/065/15 | 1 | 22 | 61 | 0 | 0 | 83 | $200.00 | 8-Jun-15 | 8-Jun-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Prey Chhor | Samraong | 2015 | Traffic Law and Public Order | Community Awareness | KPC/067/15 | 1 | 37 | 26 | 0 | 0 | 63 | $195.00 | 11-Jun-15 | 11-Jun-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Lvea Leu | 2015 | Law on Migration | Community Awareness | KPC/070/15 | 1 | 31 | 44 | 0 | 0 | 75 | $194.00 | 11-Jun-15 | 11-Jun-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Prey Chhor | Samraong | 2015 | Drug business/use prevention | Community Awareness | KPC/066/15 | 1 | 23 | 36 | 0 | 0 | 59 | $200.00 | 8-Jun-15 | 8-Jun-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Prey Chhor | Samraong | 2015 | Law against Domestic Violence | Community Awareness | KPC/068/15 | 1 | 38 | 32 | 0 | 0 | 70 | $230.00 | 9-Jun-15 | 9-Jun-15 | District WCCC | Touch Vath |
| Kampong Cham | Prey Chhor | Sragnae | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/069/15 | 1 | 26 | 29 | 2 | 1 | 55 | $200.00 | 10-Jun-15 | 10-Jun-15 | District WCCC | Touch Vath |
| Kampong Thom | Stueng Saen | Kampong Krabau | 2015 | Law against Domestic Violence | Community Awareness | KPT/072/15 | 1 | 23 | 49 | 9 | 5 | 72 | $208.00 | 9-Jun-15 | 9-Jun-15 | District Office of Women’s Affairs | Dum Kesasophea |
| Kampong Thom | Stueng Saen | Kampong Thum | 2015 | Law against Domestic Violence | Community Awareness | KPT/073/15 | 1 | 13 | 59 | 0 | 1 | 72 | $208.00 | 12-Jun-15 | 12-Jun-15 | District Office of Women’s Affairs | Dum Kesasophea |
| Kampong Thom | Kampong Svay | Chey | 2015 | Education for Gangs | Community Awareness | KPT/074/15 | 1 | 14 | 78 | 0 | 0 | 92 | $203.00 | 5-Jun-15 | 5-Jun-15 | District Police Inspectorate | Ke Kanchna |
| Kampong Thom | Kampong Svay | Chey | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPT/075/15 | 1 | 20 | 59 | 1 | 0 | 79 | $203.00 | 16-Jun-15 | 16-Jun-15 | District Police Inspectorate | Ke Kanchna |
| Kampong Thom | Stueng Saen | Kampong Krabau | 2015 | Drug business/use prevention | Community Awareness | KPT/076/15 | 1 | 41 | 34 | 38 | 34 | 75 | $213.00 | 8-Jun-15 | 8-Jun-15 | Commune/Sangkat Police Post | Huy Vath |
| Kampong Thom | Stoung | Pralay | 2015 | Traffic Law and Public Order | Community Awareness | KPT/077/15 | 1 | 43 | 15 | 1 | 9 | 58 | $209.00 | 10-Jun-15 | 10-Jun-15 | Commune/Sangkat Police Post | Kim Chanrith |
| Kampong Thom | Kampong Svay | Chey | 2015 | Law against Domestic Violence | Community Awareness | KPT/078/15 | 1 | 16 | 55 | 0 | 0 | 71 | $203.00 | 10-Jun-15 | 10-Jun-15 | District Office of Women’s Affairs | Dep Chenda |
| Kampong Thom | Baray | Chong Doung | 2015 | Penal and Civil Law | Community Awareness | KPT/078/15 | 1 | 28 | 2 | 10 | 10 | 30 | $203.00 | 10-Jun-15 | 10-Jun-15 | District Police Inspectorate | Chin Vicheth |
| Kampong Chhnang | Baribour | Khon Rang | 2015 | Law against Domestic Violence | Community Awareness | KCH/071/15 | 1 | 26 | 51 | 0 | 2 | 77 | $200.00 | 16-Jun-15 | 16-Jun-15 | District Office of Women’s Affairs | Duong Sokhom |
| Kampong Chhnang | Kampong Tralach | Longveaek | 2015 | Law against Domestic Violence | Community Awareness | KCH/072/15 | 1 | 16 | 49 | 0 | 1 | 65 | $200.00 | 16-Jun-15 | 16-Jun-15 | District Office of Women’s Affairs | Kim Sopheap |
| Kampong Chhnang | Kampong Tralach | Longveaek | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KCH/072/15 | 1 | 32 | 40 | 0 | 0 | 72 | $207.50 | 23-Jun-15 | 23-Jun-15 | District Office of Women’s Affairs | Kim Sopheap |
| Kampong Chhnang | Kampong Chhnang | Kampong Chhnang | 2015 | Law against Domestic Violence | Community Awareness | KCH/073/15 | 1 | 23 | 54 | 0 | 0 | 77 | $207.75 | 17-Jun-15 | 17-Jun-15 | District Office of Women’s Affairs | Mey Sinath |
| Kampong Chhnang | Rolea B ier | Kouk Banteay | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/074/15 | 1 | 28 | 43 | 2 | 3 | 71 | $202.75 | 22-Jun-15 | 22-Jun-15 | District Police Inspectorate | Yin Saly |
| Kampong Chhnang | Kampong Leaeng | Svay Rumpear | 2015 | Village and Commune Safety Policy | Community Awareness | KCH/075/15 | 1 | 11 | 54 | 0 | 0 | 65 | $207.00 | 19-Jun-15 | 19-Jun-15 | District Police Inspectorate | Seng Chenda |
| Prey Veng | Ba Phnum | Chheu Kach | 2015 | Traffic Law and Public Order | Community Awareness | PVG/089/15 | 1 | 23 | 22 | 0 | 0 | 45 | $206.00 | 16-Jun-15 | 16-Jun-15 | District Police Inspectorate | Lay Sakun |
| Prey Veng | Kamchay Mear | Kranhung | 2015 | Traffic Law and Public Order | Community Awareness | PVG/090/15 | 1 | 33 | 47 | 3 | 3 | 80 | $254.00 | 22-Jun-15 | 22-Jun-15 | District Police Inspectorate | Uy Noeun |
| Prey Veng | Preah Sdach | Krang Svay | 2015 | Village and Commune Safety Policy | Community Awareness | PVG/091/15 | 1 | 21 | 50 | 0 | 0 | 71 | $193.00 | 23-Jun-15 | 23-Jun-15 | District Police Inspectorate | Nuon Sakhorn |
| Kampong Thom | Stoung | Pralay | 2015 | Law against Domestic Violence | Community Awareness | KPT/080/15 | 1 | 26 | 32 | 0 | 0 | 58 | $209.00 | 19-Jun-15 | 19-Jun-15 | District Office of Women’s Affairs | Pa Bopha |
| Kampong Thom | Stueng Saen | Kampong Krabau | 2015 | Village and Commune Safety Policy | Community Awareness | KPT/081/15 | 1 | 53 | 22 | 0 | 0 | 75 | $213.00 | 17-Jun-15 | 17-Jun-15 | Commune/Sangkat Police Post | Huy Vath |
| Kampong Thom | Stueng Saen | Kampong Thum | 2015 | Drug business/use prevention | Community Awareness | KPT/082/15 | 1 | 20 | 55 | 20 | 12 | 75 | $213.00 | 16-Jun-15 | 16-Jun-15 | Commune/Sangkat Police Post | Van Vibol |
| Kampong Thom | Stueng Saen | Kampong Thum | 2015 | Village and Commune Safety Policy | Community Awareness | KPT/083/15 | 1 | 35 | 41 | 0 | 1 | 76 | $213.00 | 22-Jun-15 | 22-Jun-15 | Commune/Sangkat Police Post | Van Vibol |
| Kampong Thom | Baray | Chong Doung | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPT/084/15 | 1 | 33 | 27 | 3 | 21 | 60 | $203.00 | 19-Jun-15 | 19-Jun-15 | District Police Inspectorate | Chin Vicheth |
| Kampong Thom | Baray | Chong Doung | 2015 | Law against Domestic Violence | Community Awareness | KPT/085/15 | 1 | 22 | 44 | 0 | 1 | 66 | $203.00 | 22-Jun-15 | 22-Jun-15 | District Office of Women’s Affairs | Man Chantrea |
| Kampong Thom | Stoung | Pralay | 2015 | Penal and Civil Law | Community Awareness | KPT/086/15 | 1 | 35 | 23 | 2 | 2 | 58 | $209.00 | 23-Jun-15 | 23-Jun-15 | Commune/Sangkat Police Post | Kim Chanrith |
| Kampong Cham | Prey Chhor | Sragnae | 2015 | Law against Domestic Violence | Community Awareness | KPC/071/15 | 1 | 18 | 37 | 0 | 0 | 55 | $200.00 | 17-Jun-15 | 17-Jun-15 | District WCCC | Touch Vath |
| Kampong Cham | Stueng Trang | Preaek Bak | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/072/15 | 1 | 17 | 60 | 0 | 0 | 77 | $205.00 | 17-Jun-15 | 17-Jun-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Chamkar Leu | Cheyyou | 2015 | Traffic Law and Public Order | Community Awareness | KPC/077/15 | 1 | 51 | 6 | 4 | 1 | 57 | $200.00 | 23-Jun-15 | 23-Jun-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Spueu | 2015 | Drug business/use prevention | Community Awareness | KPC/078/15 | 1 | 57 | 15 | 6 | 6 | 72 | $230.00 | 24-Jun-15 | 24-Jun-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Cheyyou | 2015 | Drug business/use prevention | Community Awareness | KPC/079/15 | 1 | 14 | 50 | 0 | 0 | 64 | $200.00 | 25-Jun-15 | 25-Jun-15 | Provincial Police Commissariat | Chun Chamnap |
| Battambang | Sangkae | Ta Pon | 2015 | Drug business/use prevention | Community Awareness | BAT/081/15 | 1 | 17 | 20 | 10 | 19 | 37 | $214.00 | 17-Jun-15 | 15-Jun-15 | Commune/Sangkat Police Post | Net Kroeng |
| Battambang | Sangkae | Ta Pon | 2015 | Gambling Prevention | Community Awareness | BAT/082/15 | 1 | 9 | 29 | 0 | 0 | 38 | $199.00 | 26-Jun-15 | 26-Jun-15 | Commune/Sangkat Police Post | Net Kroeng |
| Battambang | Koas Krala | Chhnal Moan | 2015 | Law against Domestic Violence | Community Awareness | BAT/083/15 | 1 | 14 | 20 | 0 | 0 | 34 | $199.00 | 17-Jun-15 | 17-Jun-15 | District Office of Women’s Affairs | Khhourn Saory |
| Battambang | Moung Ruessei | Kah Kos | 2015 | Law against Women and children rape | Community Awareness | BAT/084/15 | 1 | 10 | 65 | 0 | 0 | 75 | $205.50 | 22-Jun-15 | 22-Jun-15 | District Administration/Council | Chea Daravuth |
| Battambang | Banan | Chaeng Mean Chey | 2015 | Law against Domestic Violence | Community Awareness | BAT/085/15 | 1 | 8 | 37 | 0 | 1 | 45 | $204.00 | 24-Jun-15 | 24-Jun-15 | District Administration/Council | Theam Chantho |
| Battambang | Banan | Chaeng Mean Chey | 2015 | Law against Women and children rape | Community Awareness | BAT/086/15 | 1 | 10 | 34 | 0 | 1 | 44 | $204.00 | 26-Jun-15 | 26-Jun-15 | District Administration/Council | Theam Chantho |
| Battambang | Bavel | Ampil Pram Daeum | 2015 | Law against Domestic Violence | Community Awareness | BAT/087/15 | 1 | 24 | 19 | 4 | 9 | 43 | $207.00 | 22-Jun-15 | 22-Jun-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Koas Krala | Chhnal Moan | 2015 | Drug business/use prevention | Community Awareness | BAT/088/15 | 1 | 17 | 16 | 0 | 2 | 33 | $211.00 | 23-Jun-15 | 23-Jun-15 | District Police Inspectorate | Siek Phea |
| Battambang | Moung Ruessei | Kah Kos | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/089/15 | 1 | 25 | 46 | 0 | 0 | 71 | $204.00 | 25-Jun-15 | 25-Jun-15 | Commune/Sangkat Police Post | Kin Sarang |
| Battambang | Bavel | Ampil Pram Daeum | 2015 | Drug business/use prevention | Community Awareness | BAT/090/15 | 1 | 25 | 30 | 25 | 30 | 55 | $193.00 | 25-Jun-15 | 25-Jun-15 | Commune/Sangkat Police Post | Ol Chich |
| Kampong Cham | Chamkar Leu | Spueu | 2015 | Law against Domestic Violence | Community Awareness | KPC/073/15 | 1 | 18 | 37 | 12 | 14 | 55 | $195.00 | 22-Jun-15 | 22-Jun-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Chamkar Leu | Cheyyou | 2015 | Law against Domestic Violence | Community Awareness | KPC/074/15 | 1 | 20 | 50 | 0 | 0 | 70 | $225.00 | 29-Jun-15 | 29-Jun-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Stueng Trang | Preaek Bak | 2015 | Village and Commune Safety Policy | Community Awareness | KPC/075/15 | 1 | 25 | 50 | 0 | 0 | 75 | $215.00 | 22-Jun-15 | 22-Jun-15 | District Police Inspectorate | Soeun Tit |
| Kampong Cham | Prey Chhor | Sragnae | 2015 | Drug business/use prevention | Community Awareness | KPC/076/15 | 1 | 28 | 42 | 28 | 41 | 70 | $224.00 | 22-Jun-15 | 22-Jun-15 | Provincial Police Commissariat | Chun Chamnap |
| Banteay Meanchey | Thma Puok | Banteay Chhmar | 2015 | Traffic Law and Public Order | Community Awareness | BMC/057/15 | 1 | 20 | 34 | 6 | 7 | 54 | $223.00 | 16-Jun-15 | 16-Jun-15 | Commune/Sangkat Police Post | Phae Savith |
| Banteay Meanchey | Mongkol Borei | Koy Maeng | 2015 | Law against Domestic Violence | Community Awareness | BMC/056/15 | 1 | 41 | 36 | 0 | 0 | 77 | $200.50 | 17-Jun-15 | 17-Jun-15 | District Office of Women’s Affairs | Duch San |
| Banteay Meanchey | Svay Chek | Ta Phou | 2015 | Law on Migration | Community Awareness | BMC/058/15 | 1 | 29 | 39 | 1 | 0 | 68 | $310.00 | 17-Jun-15 | 17-Jun-15 | District Office of Social Affairs | Chan Cheko |
| Banteay Meanchey | Svay Chek | Sla Kram | 2015 | Law against Domestic Violence | Community Awareness | BMC/059/15 | 1 | 19 | 46 | 3 | 5 | 65 | $310.00 | 22-Jun-15 | 22-Jun-15 | District Office of Women’s Affairs | Nith Sophaon |
| Banteay Meanchey | Mongkol Borei | Koy Maeng | 2015 | Village and Commune Safety Policy | Community Awareness | BMC/060/15 | 1 | 29 | 37 | 0 | 0 | 66 | $207.60 | 23-Jun-15 | 23-Jun-15 | Commune/Sangkat Police Post | Art Sokun |
| Banteay Meanchey | Preah Netr Preah | Prasat | 2015 | Law on Migration | Community Awareness | BMC/061/15 | 1 | 9 | 38 | 0 | 0 | 47 | $240.70 | 19-Jun-15 | 19-Jun-15 | District Office of Women’s Affairs | Sun Sokchea |
| Battambang | Bavel | Khnach Romeas | 2015 | Law against Women and children rape | Community Awareness | BAT/091/15 | 1 | 5 | 39 | 0 | 0 | 44 | $207.00 | 8-Jul-15 | 8-Jul-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Koas Krala | Thipakdei | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/092/15 | 1 | 13 | 21 | 1 | 1 | 34 | $202.00 | 9-Jul-15 | 9-Jul-15 | District Police Inspectorate | Siek Phea |
| Battambang | Sangkae | Roka | 2015 | Drug business/use prevention | Community Awareness | BAT/093/15 | 1 | 11 | 25 | 9 | 17 | 36 | $208.00 | 10-Jul-15 | 10-Jul-15 | Commune/Sangkat Police Post | Chin Rang |
| Battambang | Banan | Phnum Sampov | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/094/15 | 1 | 20 | 17 | 0 | 0 | 37 | $202.00 | 13-Jul-15 | 13-Jul-15 | Commune/Sangkat Police Post | Mey Chhengly |
| Battambang | Moung Ruessei | Prey Touch | 2015 | Law against Domestic Violence | Community Awareness | BAT/095/15 | 1 | 25 | 50 | 0 | 0 | 75 | $217.50 | 14-Jul-15 | 14-Jul-15 | District Administration/Council | Ou Bopha Champa |
| Kampong Cham | Chamkar Leu | Ta Ong | 2015 | Drug business/use prevention | Community Awareness | KPC/082/15 | 1 | 40 | 17 | 1 | 2 | 57 | $200.00 | 10-Jul-15 | 10-Jul-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Stueng Trang | Me Sar Chrey | 2015 | Law against Domestic Violence | Community Awareness | KPC/084/15 | 1 | 41 | 25 | 0 | 0 | 66 | $200.00 | 10-Jul-15 | 10-Jul-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Prey Chhor | Prey Chhor | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/080/15 | 1 | 27 | 28 | 0 | 0 | 55 | $195.00 | 6-Jul-15 | 6-Jul-15 | District WCCC | Touch Vath |
| Kampong Cham | Chamkar Leu | Ta Ong | 2015 | Traffic Law and Public Order | Community Awareness | KPC/081/15 | 1 | 23 | 33 | 12 | 11 | 56 | $195.00 | 6-Jul-15 | 6-Jul-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Bos Khnor | 2015 | Law against Domestic Violence | Community Awareness | KPC/083/15 | 1 | 16 | 39 | 9 | 10 | 55 | $195.00 | 8-Jul-15 | 8-Jul-15 | District Office of Women’s Affairs | Un Chantha |
| Prey Veng | Kanhchriech | Chong Ampil | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | PVG/092/15 | 1 | 27 | 46 | 0 | 0 | 73 | $202.60 | 6-Jul-15 | 6-Jul-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Kanhchriech | Chong Ampil | 2015 | Law against Domestic Violence | Community Awareness | PVG/093/15 | 1 | 12 | 26 | 0 | 0 | 38 | $154.40 | 7-Jul-15 | 7-Jul-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Svay Antor | Angkor Tret | 2015 | Village and Commune Safety Policy | Community Awareness | PVG/094/15 | 1 | 25 | 25 | 0 | 0 | 50 | $200.00 | 8-Jul-15 | 8-Jul-15 | District Police Inspectorate | Theoun Chanthol |
| Prey Veng | Svay Antor | Angkor Tret | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | PVG/095/15 | 1 | 35 | 10 | 0 | 0 | 45 | $195.00 | 9-Jul-15 | 9-Jul-15 | District Police Inspectorate | Theoun Chanthol |
| Prey Veng | Ba Phnum | Roung Damrei | 2015 | Law against Domestic Violence | Community Awareness | PVG/096/15 | 1 | 17 | 28 | 0 | 0 | 45 | $201.00 | 8-Jul-15 | 8-Jul-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Ba Phnum | Roung Damrei | 2015 | Law against Domestic Violence | Community Awareness | PVG/097/15 | 1 | 12 | 32 | 0 | 0 | 44 | $197.60 | 9-Jul-15 | 9-Jul-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Kamchay Mear | Smaong Khang Tboung | 2015 | Law against Domestic Violence | Community Awareness | PVG/098/15 | 1 | 15 | 35 | 0 | 0 | 50 | $180.40 | 9-Jul-15 | 9-Jul-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Kamchay Mear | Smaong Khang Tboung | 2015 | Law against Domestic Violence | Community Awareness | PVG/099/15 | 1 | 7 | 45 | 0 | 0 | 52 | $189.60 | 10-Jul-15 | 10-Jul-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Kanhchriech | Chong Ampil | 2015 | Traffic Law and Public Order | Community Awareness | PVG/100/15 | 1 | 35 | 42 | 0 | 0 | 77 | $253.00 | 9-Jul-15 | 9-Jul-15 | District Police Inspectorate | Yim Sarim |
| Prey Veng | Preah Sdach | Lvea | 2015 | Law against Domestic Violence | Community Awareness | PVG/101/15 | 1 | 2 | 55 | 0 | 0 | 57 | $217.00 | 13-Jul-15 | 13-Jul-15 | District Office of Women’s Affairs | Khiev Saphean |
| Prey Veng | Preah Sdach | Lvea | 2015 | Law against Domestic Violence | Community Awareness | PVG/102/15 | 1 | 26 | 32 | 1 | 6 | 58 | $206.40 | 14-Jul-15 | 14-Jul-15 | District Office of Women’s Affairs | Khiev Saphean |
| Prey Veng | Svay Antor | Angkor Tret | 2015 | Law against Domestic Violence | Community Awareness | PVG/103/15 | 1 | 22 | 27 | 0 | 0 | 49 | $215.00 | 14-Jul-15 | 14-Jul-15 | District Office of Women’s Affairs | Chhim Chankhantey |
| Kampong Cham | Stueng Trang | Me Sar Chrey | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/085/15 | 1 | 13 | 50 | 0 | 0 | 63 | $195.00 | 16-Jul-15 | 16-Jul-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Prey Chhor | Khvet Thum | 2015 | Drug business/use prevention | Community Awareness | KPC/087/15 | 1 | 34 | 21 | 0 | 0 | 55 | $195.00 | 17-Jul-15 | 17-Jul-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Stueng Trang | Me Sar Chrey | 2015 | Drug business/use prevention | Community Awareness | KPC/092/15 | 1 | 34 | 34 | 10 | 7 | 68 | $205.00 | 22-Jul-15 | 22-Jul-15 | District Police Inspectorate | Soeun Tit |
| Kampong Cham | Chamkar Leu | Ta Ong | 2015 | Law against Domestic Violence | Community Awareness | KPC/094/15 | 1 | 11 | 49 | 0 | 7 | 60 | $205.00 | 28-Jul-15 | 28-Jul-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Chamkar Leu | Bos Khnor | 2015 | Drug business/use prevention | Community Awareness | KPC/086/15 | 1 | 27 | 33 | 5 | 2 | 60 | $210.00 | 16-Jul-15 | 16-Jul-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Prey Chhor | Khvet Thum | 2015 | Drug business/use prevention | Community Awareness | KPC/088/15 | 1 | 27 | 28 | 27 | 28 | 55 | $200.00 | 23-Jul-15 | 23-Jul-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Prey Chhor | Prey Chhor | 2015 | Drug business/use prevention | Community Awareness | KPC/089/15 | 1 | 30 | 30 | 30 | 30 | 60 | $210.00 | 24-Jul-15 | 24-Jul-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Prey Chhor | Khvet Thum | 2015 | Law against Domestic Violence | Community Awareness | KPC/090/15 | 1 | 28 | 32 | 0 | 0 | 60 | $210.00 | 21-Jul-15 | 21-Jul-15 | District WCCC | Touch Vath |
| Kampong Cham | Prey Chhor | Prey Chhor | 2015 | Law against Domestic Violence | Community Awareness | KPC/091/15 | 1 | 34 | 22 | 8 | 15 | 56 | $200.00 | 22-Jul-15 | 22-Jul-15 | District WCCC | Touch Vath |
| Kampong Cham | Chamkar Leu | Bos Khnor | 2015 | Law on Migration | Community Awareness | KPC/093/15 | 1 | 27 | 57 | 0 | 2 | 84 | $200.00 | 23-Jul-15 | 23-Jul-15 | District Office of Women’s Affairs | Un Chantha |
| Battambang | Koas Krala | Thipakdei | 2015 | Law against Domestic Violence | Community Awareness | BAT/096/15 | 1 | 17 | 17 | 3 | 2 | 34 | $205.00 | 16-Jul-15 | 16-Jul-15 | District Office of Women’s Affairs | Khhourn Saory |
| Battambang | Banan | Phnum Sampov | 2015 | Law against Domestic Violence | Community Awareness | BAT/097/15 | 1 | 10 | 27 | 0 | 0 | 37 | $204.00 | 17-Jul-15 | 17-Jul-15 | District Administration/Council | Theam Chantho |
| Battambang | Banan | Phnum Sampov | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | BAT/098/15 | 1 | 4 | 36 | 0 | 0 | 40 | $204.00 | 20-Jul-15 | 20-Jul-15 | District Administration/Council | Theam Chantho |
| Battambang | Sangkae | Roka | 2015 | Law against Women and children rape | Community Awareness | BAT/099/15 | 1 | 15 | 19 | 10 | 9 | 34 | $202.50 | 17-Jul-15 | 17-Jul-15 | Commune/Sangkat Police Post | Chin Rang |
| Battambang | Sangkae | Roka | 2015 | Law against Domestic Violence | Community Awareness | BAT/100/15 | 1 | 27 | 24 | 0 | 2 | 51 | $200.00 | 24-Jul-15 | 24-Jul-15 | Commune/Sangkat Police Post | Chin Rang |
| Battambang | Moung Ruessei | Prey Touch | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | BAT/101/15 | 1 | 27 | 48 | 0 | 0 | 75 | $205.50 | 21-Jul-15 | 21-Jul-15 | District Administration/Council | Chea Daravuth |
| Battambang | Bavel | Khnach Romeas | 2015 | Law against Domestic Violence | Community Awareness | BAT/102/15 | 1 | 26 | 20 | 3 | 6 | 46 | $207.00 | 22-Jul-15 | 22-Jul-15 | District Office of Women’s Affairs | Saem Pov |
| Battambang | Bavel | Khnach Romeas | 2015 | Law against Women and children rape | Community Awareness | BAT/103/15 | 1 | 9 | 33 | 1 | 18 | 42 | $193.00 | 27-Jul-15 | 27-Jul-15 | District Office of Women’s Affairs | Saem Pov |
| Battambang | Koas Krala | Thipakdei | 2015 | Drug business/use prevention | Community Awareness | BAT/104/15 | 1 | 15 | 19 | 1 | 3 | 34 | $199.00 | 23-Jul-15 | 23-Jul-15 | District Police Inspectorate | Siek Phea |
| Battambang | Moung Ruessei | Prey Touch | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/105/15 | 1 | 21 | 24 | 0 | 0 | 45 | $189.00 | 27-Jul-15 | 27-Jul-15 | Commune/Sangkat Police Post | Ing Sovann |
| Prey Veng | Kamchay Mear | Smaong Khang Tboung | 2015 | Traffic Law and Public Order | Community Awareness | PVG/104/15 | 1 | 26 | 48 | 0 | 0 | 74 | $240.20 | 21-Jul-15 | 21-Jul-15 | District Police Inspectorate | Uy Noeun |
| Prey Veng | Ba Phnum | Roung Damrei | 2015 | Traffic Law and Public Order | Community Awareness | PVG/105/15 | 1 | 9 | 38 | 0 | 0 | 47 | $211.60 | 21-Jul-15 | 21-Jul-15 | District Police Inspectorate | Lay Sakun |
| Prey Veng | Preah Sdach | Lvea | 2015 | Village and Commune Safety Policy | Community Awareness | PVG/106/15 | 1 | 20 | 49 | 0 | 3 | 69 | $187.00 | 23-Jul-15 | 23-Jul-15 | District Police Inspectorate | Nuon Sakhorn |
| Kampong Cham | Stueng Trang | Soupheas | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/102/15 | 1 | 64 | 30 | 0 | 0 | 94 | $195.00 | 10-Aug-15 | 10-Aug-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Prey Chhor | Krouch | 2015 | Drug business/use prevention | Community Awareness | KPC/099/15 | 1 | 24 | 33 | 18 | 17 | 57 | $195.00 | 7-Aug-15 | 7-Aug-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Lvea Leu | 2015 | Law against Domestic Violence | Community Awareness | KPC/096/15 | 1 | 13 | 47 | 7 | 14 | 60 | $195.00 | 6-Aug-15 | 6-Aug-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Stueng Trang | Soupheas | 2015 | Drug business/use prevention | Community Awareness | KPC/095/15 | 1 | 39 | 28 | 0 | 0 | 67 | $210.00 | 6-Aug-15 | 6-Aug-15 | District Police Inspectorate | Soeun Tit |
| Kampong Cham | Chamkar Leu | Lvea Leu | 2015 | Law on Migration | Community Awareness | KPC/097/15 | 1 | 38 | 37 | 22 | 14 | 75 | $200.00 | 13-Aug-15 | 13-Aug-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Prey Chhor | Krouch | 2015 | Drug business/use prevention | Community Awareness | KPC/098/15 | 1 | 39 | 16 | 0 | 0 | 55 | $200.00 | 6-Aug-15 | 6-Aug-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Prey Chhor | Tong Rong | 2015 | Drug business/use prevention | Community Awareness | KPC/100/15 | 1 | 15 | 42 | 0 | 0 | 57 | $210.00 | 11-Aug-15 | 11-Aug-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Lvea Leu | 2015 | Traffic Law and Public Order | Community Awareness | KPC/101/15 | 1 | 21 | 36 | 12 | 16 | 57 | $210.00 | 12-Aug-15 | 12-Aug-15 | Provincial Police Commissariat | Chun Chamnap |
| Battambang | Bavel | Khlaeng Meas | 2015 | Law against Women and children rape | Community Awareness | BAT/106/15 | 1 | 15 | 29 | 0 | 16 | 44 | $209.00 | 10-Aug-15 | 10-Aug-15 | District Office of Women’s Affairs | Saem Pov |
| Battambang | Koas Krala | Hab | 2015 | Law against Domestic Violence | Community Awareness | BAT/107/15 | 1 | 13 | 21 | 0 | 0 | 34 | $206.00 | 11-Aug-15 | 11-Aug-15 | District Office of Women’s Affairs | Khhourn Saory |
| Battambang | Moung Ruessei | Ta Lors | 2015 | Law against Domestic Violence | Community Awareness | BAT/108/15 | 1 | 33 | 55 | 0 | 0 | 88 | $212.50 | 12-Aug-15 | 12-Aug-15 | District Administration/Council | Ou Bopha Champa |
| Battambang | Sangkae | Kampong Preah | 2015 | Drug business/use prevention | Community Awareness | BAT/109/15 | 1 | 10 | 26 | 2 | 1 | 36 | $210.00 | 13-Aug-15 | 13-Aug-15 | Commune/Sangkat Police Post | Chhom Nge |
| Battambang | Banan | Snoeng | 2015 | Drug business/use prevention | Community Awareness | BAT/110/15 | 1 | 9 | 29 | 0 | 0 | 38 | $204.00 | 14-Aug-15 | 14-Aug-15 | District Administration/ Council | Theam Chantho |
| Prey Veng | Svay Antor | Chea Khlang | 2015 | Law against Domestic Violence | Community Awareness | PVG/107/15 | 1 | 19 | 31 | 0 | 3 | 50 | $210.00 | 6-Aug-15 | 6-Aug-15 | District Office of Women’s Affairs | Chhim Chankhantey |
| Prey Veng | Kanhchriech | Kouk Kong Kaeut | 2015 | Law against Domestic Violence | Community Awareness | PVG/108/15 | 1 | 14 | 31 | 0 | 0 | 45 | $211.00 | 6-Aug-15 | 6-Aug-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Kanhchriech | Kouk Kong Kaeut | 2015 | Law against Women and children rape | Community Awareness | PVG/109/15 | 1 | 25 | 20 | 0 | 0 | 45 | $182.90 | 7-Aug-15 | 7-Aug-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Svay Antor | Chea Khlang | 2015 | Village and Commune Safety Policy | Community Awareness | PVG/110/15 | 1 | 16 | 37 | 0 | 0 | 53 | $210.00 | 11-Aug-15 | 11-Aug-15 | District Police Inspectorate | Theoun Chanthol |
| Prey Veng | Svay Antor | Chea Khlang | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | PVG/111/15 | 1 | 22 | 23 | 0 | 0 | 45 | $194.00 | 12-Aug-15 | 12-Aug-15 | District Police Inspectorate | Theoun Chanthol |
| Prey Veng | Kamchay Mear | Smaong Khang Tboung | 2015 | Law against Domestic Violence | Community Awareness | PVG/112/15 | 1 | 25 | 24 | 0 | 0 | 49 | $180.40 | 11-Aug-15 | 11-Aug-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Kamchay Mear | Smaong Khang Cheung | 2015 | Law against Domestic Violence | Community Awareness | PVG/113/15 | 1 | 14 | 36 | 0 | 0 | 50 | $180.40 | 12-Aug-15 | 12-Aug-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Kanhchriech | Kouk Kong Kaeut | 2015 | Public Forum/Community Forum | Community Awareness | PVG/114/15 | 1 | 36 | 34 | 0 | 0 | 70 | $221.00 | 11-Aug-15 | 11-Aug-15 | District Police Inspectorate | Yim Sarim |
| Prey Veng | Preah Sdach | Banteay Chakrei | 2015 | Law against Domestic Violence | Community Awareness | PVG/115/15 | 1 | 12 | 43 | 0 | 0 | 55 | $217.00 | 11-Aug-15 | 11-Aug-15 | District Office of Women’s Affairs | Khiev Saphean |
| Prey Veng | Ba Phnum | Reaks Chey | 2015 | Traffic Law and Public Order | Community Awareness | PVG/117/15 | 1 | 15 | 30 | 0 | 0 | 45 | $206.00 | 12-Aug-15 | 12-Aug-15 | District Police Inspectorate | Lay Sakun |
| Prey Veng | Kamchay Mear | Smaong Khang Cheung | 2015 | Traffic Law and Public Order | Community Awareness | PVG/118/15 | 1 | 28 | 52 | 0 | 0 | 80 | $254.00 | 13-Aug-15 | 13-Aug-15 | District Police Inspectorate | Uy Noeun |
| Kampong Cham | Stueng Trang | Soupheas | 2015 | Law against Domestic Violence | Community Awareness | KPC/103/15 | 1 | 42 | 42 | 0 | 0 | 84 | $200.00 | 19-Aug-15 | 19-Aug-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Chamkar Leu | Ta Prok | 2015 | Traffic Law and Public Order | Community Awareness | KPC/104/15 | 1 | 24 | 31 | 0 | 0 | 55 | $200.00 | 19-Aug-15 | 19-Aug-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Ta Prok | 2015 | Drug business/use prevention | Community Awareness | KPC/105/15 | 1 | 28 | 26 | 0 | 0 | 54 | $200.00 | 20-Aug-15 | 20-Aug-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Prey Chhor | Krouch | 2015 | Law against Domestic Violence | Community Awareness | KPC/106/15 | 1 | 24 | 37 | 0 | 0 | 61 | $210.00 | 19-Aug-15 | 19-Aug-15 | District WCCC | Touch Vath |
| Kampong Cham | Prey Chhor | Tong Rong | 2015 | Law against Domestic Violence | Community Awareness | KPC/107/15 | 1 | 23 | 32 | 0 | 0 | 55 | $200.00 | 20-Aug-15 | 20-Aug-15 | District WCCC | Touch Vath |
| Kampong Cham | Prey Chhor | Tong Rong | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/108/15 | 1 | 27 | 28 | 0 | 0 | 55 | $200.00 | 21-Aug-15 | 21-Aug-15 | District WCCC | Touch Vath |
| Kampong Cham | Chamkar Leu | Ta Prok | 2015 | Law against Domestic Violence | Community Awareness | KPC/109/15 | 1 | 9 | 51 | 1 | 5 | 60 | $205.00 | 24-Aug-15 | 24-Aug-15 | District Office of Women’s Affairs | Un Chantha |
| Prey Veng | Preah Sdach | Banteay Chakrei | 2015 | Law against Domestic Violence | Community Awareness | PVG/116/15 | 1 | 16 | 40 | 0 | 0 | 56 | $210.00 | 21-Aug-15 | 21-Aug-15 | District Office of Women’s Affairs | Khiev Saphean |
| Prey Veng | Ba Phnum | Reaks Chey | 2015 | Law against Domestic Violence | Community Awareness | PVG/119/15 | 1 | 4 | 42 | 0 | 0 | 46 | $205.00 | 18-Aug-15 | 18-Aug-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Ba Phnum | Reaks Chey | 2015 | Law against Domestic Violence | Community Awareness | PVG/120/15 | 1 | 7 | 38 | 0 | 0 | 45 | $202.00 | 19-Aug-15 | 19-Aug-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Preah Sdach | Banteay Chakrei | 2015 | Public Forum/Community Forum | Community Awareness | PVG/121/15 | 1 | 18 | 46 | 0 | 0 | 64 | $187.00 | 20-Aug-15 | 20-Aug-15 | District Police Inspectorate | Nuon Sakhorn |
| Battambang | Banan | Snoeng | 2015 | Law against Women and children rape | Community Awareness | BAT/111/15 | 1 | 7 | 35 | 0 | 0 | 42 | $204.00 | 18-Aug-15 | 18-Aug-15 | District Administration/Council | Theam Chantho |
| Battambang | Sangkae | Kampong Preah | 2015 | Education for Gangs | Community Awareness | BAT/112/15 | 1 | 15 | 21 | 4 | 10 | 36 | $203.00 | 18-Aug-15 | 18-Aug-15 | Commune/Sangkat Police Post | Chom Ngek |
| Battambang | Sangkae | Kampong Preah | 2015 | Law against Women and children rape | Community Awareness | BAT/113/15 | 1 | 11 | 24 | 0 | 0 | 35 | $200.00 | 21-Aug-15 | 21-Aug-15 | Commune/Sangkat Police Post | Chom Ngek |
| Battambang | Koas Krala | Hab | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/114/15 | 1 | 19 | 15 | 1 | 19 | 34 | $207.00 | 19-Aug-15 | 19-Aug-15 | District Police Inspectorate | Siek Phea |
| Battambang | Koas Krala | Hab | 2015 | Drug business/use prevention | Community Awareness | BAT/115/15 | 1 | 19 | 13 | 4 | 6 | 32 | $206.00 | 25-Aug-15 | 25-Aug-15 | District Police Inspectorate | Siek Phea |
| Battambang | Banan | Snoeng | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/116/15 | 1 | 14 | 28 | 0 | 0 | 42 | $207.50 | 20-Aug-15 | 20-Aug-15 | Commune/Sangkat Police Post | Soeng Bannara |
| Battambang | Bavel | Khlaeng Meas | 2015 | Law against Domestic Violence | Community Awareness | BAT/117/15 | 1 | 19 | 22 | 4 | 12 | 41 | $193.00 | 20-Aug-15 | 20-Aug-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Bavel | Khlaeng Meas | 2015 | Law against Women and children rape | Community Awareness | BAT/118/15 | 1 | 27 | 14 | 1 | 3 | 41 | $207.00 | 26-Aug-15 | 26-Aug-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Moung Ruessei | Ta Lors | 2015 | Law against Women and children rape | Community Awareness | BAT/119/15 | 1 | 42 | 8 | 1 | 0 | 50 | $205.50 | 24-Aug-15 | 24-Aug-15 | District Administration/Council | Chea Daravuth |
| Battambang | Moung Ruessei | Ta Lors | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/120/15 | 1 | 33 | 55 | 0 | 0 | 88 | $199.00 | 27-Aug-15 | 27-Aug-15 | Commune/Sangkat Police Post | Nut Sophoeum |
| Kampong Cham | Prey Chhor | Chrey Vien | 2015 | Drug business/use prevention | Community Awareness | KPC/118/15 | 1 | 34 | 21 |  |  | 55 | $200.00 | 15-Sep-15 | 15-Sep-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Svay Teab | 2015 | Traffic Law and Public Order | Community Awareness | KPC/119/15 | 1 | 29 | 26 |  |  | 55 | $200.00 | 22-Sep-15 | 22-Sep-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Svay Teab | 2015 | Law on Migration | Community Awareness | KPC/120/15 | 1 | 21 | 30 |  |  | 51 | $190.00 | 16-Sep-15 | 16-Sep-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Chamkar Leu | Chamkar Andoung | 2015 | Law on Migration | Community Awareness | KPC/121/15 | 1 | 25 | 30 |  |  | 55 | $200.00 | 23-Sep-15 | 23-Sep-15 | District Office of Women’s Affairs | Un Chantha |
| Kampong Cham | Prey Chhor | Chrey Vien | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/122/15 | 1 | 21 | 30 |  |  | 51 | $190.00 | 17-Sep-15 | 17-Sep-15 | District WCCC | Touch Vath |
| Kampong Cham | Prey Chhor | Chrey Vien | 2015 | Law against Domestic Violence | Community Awareness | KPC/123/15 | 1 | 16 | 35 |  |  | 51 | $190.00 | 22-Sep-15 | 22-Sep-15 | District WCCC | Touch Vath |
| Kampong Cham | Stueng Trang | Peam Kaoh Snar | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | KPC/124/15 | 1 | 55 |  |  |  | 55 | $190.00 | 18-Sep-15 | 18-Sep-15 | District Office of Women’s Affairs | Phy Dara |
| Prey Veng | Svay Antor | Damrei Puon | 2015 | Village and Commune Safety Policy | Community Awareness | PVG/132/15 | 1 | 20 | 20 |  |  | 40 | $200.00 | 15-Sep-15 | 15-Sep-15 | District Police Inspectorate | Thoeun Chanthol |
| Prey Veng | Svay Antor | Damrei Puon | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | PVG/133/15 | 1 | 20 | 20 |  |  | 40 | $183.00 | 16-Sep-15 | 16-Sep-15 | District Police Inspectorate | Thoeun Chanthol |
| Prey Veng | Ba Phnum | Spueu Ka | 2015 | Law against Domestic Violence | Community Awareness | PVG/134/15 | 1 | 16 | 29 |  |  | 45 | $206.00 | 16-Sep-15 | 16-Sep-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Ba Phnum | Spueu Ka | 2015 | Law against Domestic Violence | Community Awareness | PVG/135/15 | 1 | 18 | 20 |  |  | 38 | $171.40 | 17-Sep-15 | 17-Sep-15 | District Office of Women’s Affairs | Prach Saroeun |
| Prey Veng | Kamchay Mear | Doun Koeng | 2015 | Traffic Law and Public Order | Community Awareness | PVG/136/15 | 1 | 35 | 20 |  |  | 55 | $196.50 | 18-Sep-15 | 18-Sep-15 | District Police Inspectorate | Uy Noeun |
| Battambang | Koas Krala | Kaos Krala | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/128/15 | 1 | 16 | 16 |  |  | 32 | $192.00 | 17-Sep-15 | 17-Sep-15 | District Police Inspectorate | Siek Phea |
| Battambang | Koas Krala | Kaos Krala | 2015 | Drug business/use prevention | Community Awareness | BAT/129/15 | 1 | 16 | 16 |  |  | 32 | $192.00 | 23-Sep-15 | 23-Sep-15 | District Police Inspectorate | Siek Phea |
| Battambang | Bavel | Lvea | 2015 | Law against Domestic Violence | Community Awareness | BAT/130/15 | 1 | 17 | 25 |  |  | 42 | $199.00 | 18-Sep-15 | 18-Sep-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Bavel | Lvea | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/131/15 | 1 | 20 | 20 |  |  | 40 | $193.00 | 22-Sep-15 | 22-Sep-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Moung Ruessei | Moung | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | BAT/132/15 | 1 | 30 | 20 |  |  | 50 | $192.50 | 18-Sep-15 | 18-Sep-15 | District WCCC | Chea Daravuth |
| Battambang | Sangkae | Reang Kesei | 2015 | Law against Domestic Violence | Community Awareness | BAT/133/15 | 1 | 18 | 14 |  |  | 32 | $190.00 | 21-Sep-15 | 21-Sep-15 | Commune/Sangkat Police Post | Sar Samay |
| Battambang | Moung Ruessei | Moung | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/134/15 | 1 | 35 | 15 |  |  | 50 | $191.00 | 23-Sep-15 | 23-Sep-15 | Commune/Sangkat Police Post | Kith Kimheng |
| Battambang | Banan | Ta Kream | 2015 | Law against Domestic Violence | Community Awareness | BAT/135/15 | 1 | 15 | 20 |  |  | 35 | $195.50 | 25-Sep-15 | 25-Sep-15 | District WCCC | Theam Chantho |
| Kampong Cham | Prey Chhor | Thma Pun | 2015 | Drug business/use prevention | Community Awareness | KPC/110/15 | 1 | 24 | 27 | 0 | 0 | 51 | $190.00 | 7-Sep-15 | 7-Sep-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Prey Chhor | Thma Pun | 2015 | Drug business/use prevention | Community Awareness | KPC/111/15 | 1 | 22 | 31 | 0 | 0 | 53 | $190.00 | 8-Sep-15 | 8-Sep-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Chamkar Andoung | 2015 | Traffic Law and Public Order | Community Awareness | KPC/112/15 | 1 | 25 | 24 | 0 | 0 | 49 | $190.00 | 10-Sep-15 | 10-Sep-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Chamkar Leu | Chamkar Andoung | 2015 | Drug business/use prevention | Community Awareness | KPC/113/15 | 1 | 15 | 33 | 0 | 0 | 48 | $190.00 | 11-Sep-15 | 11-Sep-15 | Provincial Police Commissariat | Chun Chamnap |
| Kampong Cham | Stueng Trang | Peam Kaoh Snar | 2015 | Drug business/use prevention | Community Awareness | KPC/114/15 | 1 | 56 | 25 | 2 | 3 | 81 | $200.00 | 8-Sep-15 | 8-Sep-15 | District Police Inspectorate | Soeun Tit |
| Kampong Cham | Stueng Trang | Peam Kaoh Snar | 2015 | Law against Domestic Violence | Community Awareness | KPC/116/15 | 1 | 16 | 40 | 0 | 0 | 56 | $190.00 | 9-Sep-15 | 9-Sep-15 | District Office of Women’s Affairs | Phy Dara |
| Kampong Cham | Prey Chhor | Thma Pun | 2015 | Law against Domestic Violence | Community Awareness | KPC/117/15 | 1 | 20 | 35 | 0 | 0 | 55 | $200.00 | 10-Sep-15 | 10-Sep-15 | District WCCC | Touch Vath |
| Kampong Cham | Chamkar Leu | Svay Teab | 2015 | Law against Domestic Violence | Community Awareness | KPC/115/15 | 1 | 17 | 43 | 0 | 0 | 60 | $185.00 | 9-Sep-15 | 9-Sep-15 | District Office of Women’s Affairs | Un Chantha |
| Battambang | Koas Krala | Kaos Krala | 2015 | Law against Domestic Violence | Community Awareness | BAT/121/15 | 1 | 12 | 24 | 0 | 0 | 36 | $195.00 | 8-Sep-15 | 8-Sep-15 | District Office of Women’s Affairs | Khuon Saory |
| Battambang | Sangkae | Reang Kesei | 2015 | Drug business/use prevention | Community Awareness | BAT/122/15 | 1 | 14 | 18 | 6 | 12 | 32 | $199.00 | 9-Sep-15 | 9-Sep-15 | Commune/Sangkat Police Post | Sar Samay |
| Battambang | Sangkae | Reang Kesei | 2015 | Gambling Prevention | Community Awareness | BAT/123/15 | 1 | 7 | 28 | 0 | 0 | 35 | $192.00 | 15-Sep-15 | 15-Sep-15 | Commune/Sangkat Police Post | Sar Samay |
| Battambang | Bavel | Lvea | 2015 | Law against Women and children rape | Community Awareness | BAT/124/15 | 1 | 15 | 27 | 5 | 2 | 42 | $197.00 | 9-Sep-15 | 9-Sep-15 | District Office of Women’s Affairs | Sem Pov |
| Battambang | Moung Ruessei | Moung | 2015 | Law against Domestic Violence | Community Awareness | BAT/125/15 | 1 | 23 | 42 | 0 | 0 | 65 | $202.50 | 10-Sep-15 | 10-Sep-15 | District Administration/ Council | Ou Bopha Champa |
| Battambang | Banan | Ta Kream | 2015 | Village and Commune Safety Policy | Community Awareness | BAT/126/15 | 1 | 7 | 29 | 0 | 0 | 36 | $198.50 | 11-Sep-15 | 11-Sep-15 | Commune/Sangkat Police Post | Tes Buntheoun |
| Battambang | Banan | Ta Kream | 2015 | Law on Suppression of Women/Children Trafficking | Community Awareness | BAT/127/15 | 1 | 10 | 25 | 0 | 0 | 35 | $196.50 | 15-Sep-15 | 15-Sep-15 | District Procurement Office | Theam Chantho |
| Prey Veng | Kanhchriech | Kouk Kong Lech | 2015 | Law against Women and children rape | Community Awareness | PVG/122/15 | 1 | 15 | 28 | 0 | 1 | 43 | $182.00 | 7-Sep-15 | 7-Sep-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Kanhchriech | Kouk Kong Lech | 2015 | Law against Domestic Violence | Community Awareness | PVG/123/15 | 1 | 16 | 32 | 0 | 0 | 48 | $207.60 | 8-Sep-15 | 8-Sep-15 | District Office of Women’s Affairs | Heang Lina |
| Prey Veng | Kanhchriech | Kouk Kong Lech | 2015 | Public Forum/Community Forum | Community Awareness | PVG/124/15 | 1 | 32 | 27 | 0 | 0 | 59 | $194.00 | 9-Sep-15 | 9-Sep-15 | District Police Inspectorate | Yim Sarim |
| Prey Veng | Svay Antor | Damrei Puon | 2015 | Law against Domestic Violence | Community Awareness | PVG/125/15 | 1 | 23 | 26 | 0 | 0 | 49 | $200.00 | 8-Sep-15 | 8-Sep-15 | District Office of Women’s Affairs | Chhim Chankhantey |
| Prey Veng | Ba Phnum | Spueu Ka | 2015 | Traffic Law and Public Order | Community Awareness | PVG/126/15 | 1 | 32 | 13 | 0 | 0 | 45 | $206.00 | 9-Sep-15 | 9-Sep-15 | District Police Inspectorate | Lay Sakun |
| Prey Veng | Preah Sdach | Kampong Soeng | 2015 | Public Forum/Community Forum | Community Awareness | PVG/127/15 | 1 | 64 | 16 | 0 | 0 | 80 | $187.00 | 9-Sep-15 | 9-Sep-15 | District Police Inspectorate | Seng Savorn |
| Prey Veng | Preah Sdach | Kampong Soeng | 2015 | Public Forum/Community Forum | Community Awareness | PVG/128/15 | 1 | 30 | 35 | 0 | 0 | 65 | $187.00 | 10-Sep-15 | 10-Sep-15 | District Police Inspectorate | Seng Savorn |
| Prey Veng | Kamchay Mear | Doun Koeng | 2015 | Law against Domestic Violence | Community Awareness | PVG/129/15 | 1 | 8 | 46 | 0 | 0 | 54 | $194.00 | 9-Sep-15 | 9-Sep-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Kamchay Mear | Doun Koeng | 2015 | Law against Domestic Violence | Community Awareness | PVG/130/15 | 1 | 15 | 39 | 0 | 0 | 54 | $192.20 | 11-Sep-15 | 11-Sep-15 | District Office of Women’s Affairs | Khin March |
| Prey Veng | Preah Sdach | Kampong Soeng | 2015 | Law against Domestic Violence | Community Awareness | PVG/131/15 | 1 | 30 | 35 | 0 | 0 | 65 | $200.40 | 14-Sep-15 | 14-Sep-15 | District Office of Women’s Affairs | Khiev Saphean |

Appendix C

CPCS Project Assessment Data, Apr–Sept 2015

Appendix C	CPCS Project Assessment Data, Apr–Sept 2015

| No | PIA Standard Name | Collected By | Date | Project Standard Name | Province | District | Commune | Scores |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Assessment by CCJAP staffs/counterparts |  |  |  |  | Assessment by Commune Councillor |  |  | Assessment by Beneficiaries |  |  |  |
|  |  |  |  |  |  |  |  | Ind 1.1* | Ind 1.2 | Ind 1.3 | Ind 1.4 | Ind 1.5 | Ind 2.1 | Ind 2.2 | Ind 2.3 | Ind 3.1 | Ind 3.2 | Ind 3.3 | Ind 3.4 |
| 1 | District Office of Women’s Affairs | Suon Sreng | 2-Apr-15 | Law against Domestic Violence | Prey Veng | Svay Antor | Svay Antor | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 2 | District Police Inspectoriat | Suon Sreng | 7-Apr-15 | Village and Commune Safety Policy | Prey Veng | Svay Antor | Svay Antor | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 3 | District Police Inspectoriat | Suon Sreng | 8-Apr-15 | Law on Suppression of Women/Children Trafficking | Prey Veng | Svay Antor | Svay Antor | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 4 | District Office of Women’s Affairs | Kong Sam Oun | 7-Apr-15 | Law against Domestic Violence | Prey Veng | Kamchay Mear | Cheach | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 5 | 4 | 5 | 5 |
| 5 | District Office of Women’s Affairs | Kong Sam Oun | 8-Apr-15 | Law against Domestic Violence | Prey Veng | Kamchay Mear | Cheach | 5 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 5 | 4 | 5 | 5 |
| 6 | District Police Inspectoriat | Kong Sam Oun | 22-Jun-15 | Traffic Law and Public Order | Prey Veng | Kamchay Mear | Kranhung | 3 | 4 | 4 | 5 | 5 | 3 | 4 | 3 | 4 | 3 | 4 | 5 |
| 7 | District Police Inspectoriat | Long Rumdol | 23-Jun-15 | Public Forum/Community Forum | Prey Veng | Preah Sdach | Krang Svay | 4 | 5 | 5 | 5 | 4 | 4 | 5 | 5 | 5 | 5 | 4 | 5 |
| 8 | District Office of Women’s Affairs | Neang Monan | 6-Jul-15 | Law against Women and children rape | Prey Veng | Kanhchriech | Chong Ampil | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 9 | District Office of Women’s Affairs | Neang Monan | 6-Jul-15 | Law against Women and children rape | Prey Veng | Kanhchriech | Chong Ampil | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 10 | District Office of Women’s Affairs | Neang Monan | 7-Jul-15 | Law against Domestic Violence | Prey Veng | Kanhchriech | Chong Ampil | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 4 | 5 | 5 |
| 11 | District Office of Women’s Affairs | Neang Monan | 7-Jul-15 | Law against Domestic Violence | Prey Veng | Kanhchriech | Chong Ampil | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 4 | 5 | 5 |
| 12 | District Office of Women’s Affairs | Buth Tara | 8-Jul-15 | Law against Domestic Violence | Prey Veng | Ba Phnum | Roung Damrei | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 4 | 5 | 5 | 5 |
| 13 | District Office of Women’s Affairs | Hars Sok | 9-Jul-15 | Law against Domestic Violence | Prey Veng | Ba Phnum | Roung Damrei | 4 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 4 |
| 14 | District Police Inspectoriat | Neang Monan | 9-Jul-15 | Traffic Law and Public Order | Prey Veng | Kanhchriech | Chong Ampil | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 15 | District Police Inspectoriat | Suon Sreng | 8-Jul-15 | Village and Commune Safety Policy | Prey Veng | Svay Antor | Angkor Tret | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 16 | District Police Inspectoriat | Suon Sreng | 9-Jul-15 | Law on Suppression of Women/Children Trafficking | Prey Veng | Svay Antor | Angkor Tret | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 17 | District Office of Women’s Affairs | Kong Sam Oun | 9-Jul-15 | Law against Domestic Violence | Prey Veng | Kamchay Mear | Smaong Khang Tboung | 4 | 4 | 3 | 4 | 5 | 4 | 4 | 4 | 4 | 5 | 4 | 5 |
| 18 | District Office of Women’s Affairs | Kong Sam Oun | 10-Jul-15 | Law against Domestic Violence | Prey Veng | Kamchay Mear | Smaong Khang Tboung | 4 | 3 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 3 | 4 | 5 |
| 19 | District Office of Women’s Affairs | Suon Sreng | 14-Jul-15 | Law against Domestic Violence | Prey Veng | Svay Antor | Angkor Tret | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 20 | District Office of Women’s Affairs | Long Rumdol | 13-Jul-15 | Law against Domestic Violence | Prey Veng | Preah Sdach | Lvea | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 4 | 5 |
| 21 | District Office of Women’s Affairs | Long Rumdol | 14-Jul-15 | Law against Domestic Violence | Prey Veng | Preah Sdach | Lvea | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 4 | 5 | 4 | 5 |
| 22 | District Police Inspectoriat | Kong Sam Oun | 21-Jul-15 | Traffic Law and Public Order | Prey Veng | Kamchay Mear | Smaong Khang Tboung | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 5 |
| 23 | District Police Inspectoriat | Hars Sok | 21-Jul-15 | Traffic Law and Public Order | Prey Veng | Ba Phnum | Roung Damrei | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 5 | 4 |
| 24 | District Police Inspectoriat | Long Rumdol | 23-Jul-15 | Public Forum/Community Forum | Prey Veng | Preah Sdach | Lvea | 5 | 5 | 4 | 4 | 4 | 4 | 5 | 4 | 4 | 5 | 4 | 5 |
| 25 | District Office of Women’s Affairs | Suon Sreng | 6-Aug-15 | Law against Domestic Violence | Prey Veng | Svay Antor | Chea Khlang | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 26 | District Office of Women’s Affairs | Neang Monan | 6-Aug-15 | Law against Domestic Violence | Prey Veng | Kanhchriech | Kouk Kong Kaeut | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 27 | District Office of Women’s Affairs | Neang Monan | 7-Aug-15 | Law against Women and children rape | Prey Veng | Kanhchriech | Kouk Kong Kaeut | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 28 | District Police Inspectoriat | Suon Sreng | 19-Aug-15 | Law against Domestic Violence | Prey Veng | Svay Antor | Chea Khlang | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 29 | District Police Inspectoriat | Neang Monan | 11-Aug-15 | Public Forum/Community Forum | Prey Veng | Kanhchriech | Kouk Kong Kaeut | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 30 | District Police Inspectoriat | Suon Sreng | 12-Aug-15 | Law on Suppression of Women/Children Trafficking | Prey Veng | Svay Antor | Chea Khlang | 5 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 5 |
| 31 | District Office of Women’s Affairs | Kong Sam Oun | 11-Aug-15 | Law against Domestic Violence | Prey Veng | Kamchay Mear | Smaong Khang Cheung | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 |
| 32 | District Office of Women’s Affairs | Kong Sam Oun | 12-Aug-15 | Law against Domestic Violence | Prey Veng | Kamchay Mear | Smaong Khang Cheung | 4 | 3 | 4 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 5 |
| 33 | District Office of Women’s Affairs | Hars Sok | 12-Aug-15 | Public Forum/Community Forum | Prey Veng | Ba Phnum | Reaks Chey | 4 | 5 | 4 | 5 | 4 | 5 | 5 | 4 | 5 | 5 | 4 | 5 |
| 34 | District Police Inspectoriat | Kong Sam Oun | 13-Aug-15 | Public Forum/Community Forum | Prey Veng | Kamchay Mear | Smaong Khang Cheung | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 4 | 3 | 4 | 3 |
| 35 | District Office of Women’s Affairs | Long Rumdol | 11-Aug-15 | Law against Domestic Violence | Prey Veng | Preah Sdach | Banteay Chakrei | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 |
| 36 | District Office of Women’s Affairs | Hars Sok | 18-Aug-15 | Law against Domestic Violence | Prey Veng | Ba Phnum | Reaks Chey | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 37 | District Office of Women’s Affairs | Hars Sok | 19-Aug-15 | Law against Domestic Violence | Prey Veng | Ba Phnum | Reaks Chey | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 38 | District Police Inspectoriat | Long Rumdol | 20-Aug-15 | Public Forum/Community Forum | Prey Veng | Preah Sdach | Banteay Chakrei | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 |
| 39 | District Office of Women’s Affairs | Long Rumdol | 21-Aug-15 | Law against Domestic Violence | Prey Veng | Preah Sdach | Banteay Chakrei | 4 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 |
| 40 | District Office of Women’s Affairs | Suon Sreng | 8-Sep-15 | Law against Domestic Violence | Prey Veng | Svay Antor | Damrei Puon | 5 | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 5 |
| 41 | District Police Inspectoriat | Neang Monan | 9-Sep-15 | Public Forum/Community Forum | Prey Veng | Kanhchriech | Kouk Kong Lech | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| 42 | District Office of Women’s Affairs | Kong Sam Oun | 9-Sep-15 | Law against Domestic Violence | Prey Veng | Kamchay Mear | Doun Koeng | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 |
| 43 | District Office of Women’s Affairs | Horm Raksmey | 10-Aug-15 | Law against Domestic Violence | Battambang | Bavel | Khlaeng Meas | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| 44 | District Office of Women’s Affairs | Chhoeun Sothun | 11-Aug-15 | Law against Domestic Violence | Battambang | Koas Krala | Hab | 4 | 3 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 |
| 45 | District Administration | Sorn Sin | 12-Aug-15 | Law against Domestic Violence | Battambang | Moung Ruessei | Ta Loas | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| 46 | Commune Police Post | In Vira | 13-Aug-15 | Drug business/use prevention | Battambang | Sangkae | Kampong Preah | 4 | 4 | 4 | 5 | 5 | 4 | 4 | 4 | 4 | 5 | 5 | 5 |
| 47 | District Administration | Chuon Chumpanhaphea | 14-Aug-15 | Law against Domestic Violence | Battambang | Banan | Snoeng | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 3 | 4 | 4 | 4 | 4 |
| 48 | District Police Inspectoriat | Chuon Chumpanhaphea | 18-Aug-15 | Law on Suppression of Women/Children Trafficking | Battambang | Banan | Snoeng | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | 4 |
| 49 | Commune Police Post | In Vira | 18-Aug-15 | Education for Gangs | Battambang | Sangkae | Kampong Preah | 4 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 5 | 5 | 5 |
| 50 | District Police Inspectoriat | Chhoeun Sothun | 19-Aug-15 | Village and Commune Safety Policy | Battambang | Koas Krala | Hab | 3 | 4 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| 51 | Commune Police Post | Chuon Chumpanhaphea | 20-Aug-15 | Village and Commune Safety Policy | Battambang | Banan | Snoeng | 4 | 4 | 4 | 3 | 3 | 4 | 4 | 3 | 4 | 4 | 4 | 4 |
| 52 | District Office of Women’s Affairs | Horm Raksmey | 20-Aug-15 | Law against Domestic Violence | Battambang | Bavel | Khlaeng Meas | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| 53 | Commune Police Post | In Vira | 21-Aug-15 | Law against Women and children rape | Battambang | Sangkae | Kampong Preah | 4 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 5 |
| 54 | District Administration | Sorn Sin | 24-Aug-15 | Law on Suppression of Women/Children Trafficking | Battambang | Moung Ruessei | Ta Loas | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| 55 | District Police Inspectoriat | Chhoeun Sothun | 25-Aug-15 | Drug business/use prevention | Battambang | Koas Krala | Hab | 3 | 4 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| 56 | District Office of Women’s Affairs | Horm Raksmey | 26-Aug-15 | Law against Women and children rape | Battambang | Bavel | Khlaeng Meas | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| 57 | Commune Police Post | Sorn Sin | 27-Aug-15 | Village and Commune Safety Policy | Battambang | Moung Ruessei | Ta Loas | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |

The figures of the table above are the scores (1 = Very poor, 2 = Poor, 3 = Fair, 4 = Good, 5 = Very good) provided by the participants (CCJAP/Counterparts, commune councillors, and project beneficiaries) who attended the CPCS awareness sessions against each indicator as mentioned below.

| *Indicator 1.1: Arrangement Indicator 1.2: Knowledge of the topics Indicator 1.3: Presentation Skills | Indicator 1.4: Methodology Indicator 1.5: Handouts | Indicator 2.1: Arrangement Indicator 2.2: Presentation Skills Indicator 2.3: Methodology | Indicator 3.1: Knowledge of the topics Indicator 3.2: Presentation Skills | Indicator 3.3: Knowledge Improvement Indicator 3.4: Level of Importance |
| --- | --- | --- | --- | --- |

Appendix D

Assets Handed Over to Government Agencies

Appendix D	Assets Handed Over to Government Agencies

| Asset ID | Item | Description | Location | Disposed to |
| --- | --- | --- | --- | --- |
| CJPA352 | Chair | CMF56AS | BAT | CNP July 2015 |
| CJPA358 | Chair | CV1198B | BAT | CNP July 2015 |
| CJPA359 | Chair | CV1198B | BAT | CNP July 2015 |
| CJPA366 | Desk | SCE 127 | BAT | CNP July 2015 |
| CJPA370 | Filing Cabinet | SG 71 | BAT | CNP July 2015 |
| CJPA153 | Motorbike | OI 8652 | BAT | CNP July 2015 |
| CJPA114 | Chair | CMF56AS | BMC | CNP July 2015 |
| CJPA118 | Chair | CV1198B | BMC | CNP July 2015 |
| CJPA119 | Chair | CV1198B | BMC | CNP July 2015 |
| CJPA104 | Desk | SCE 127 | BMC | CNP July 2015 |
| CJPA109 | Filing Cabinet | SG 71 | BMC | CNP July 2015 |
| CJPA135 | Laptop | Laptop | BMC | CNP July 2015 |
| CJPA211 | Chair | CMF56AS | KCH | CNP July 2015 |
| CJPA275 | Chair | CV1198B | KCH | CNP July 2015 |
| CJPA276 | Chair | CV1198B | KCH | CNP July 2015 |
| CJPA272 | Desk | SCE 127 | KCH | CNP July 2015 |
| CJPA206 | Filing Cabinet | SG 71 | KCH | CNP July 2015 |
| CJPA191 | Helmet | FF358 | KCH | CNP July 2015 |
| CJPA171 | Laptop | PC 24 | KCH | CNP July 2015 |
| CJPA187 | Motorbike | OI 8664 | KCH | CNP July 2015 |
| CJPA184 | Motorbike | OI 8661 | KDL | CNP July 2015 |
| CJPA070 | Chair | CMF56AS | KPC | CNP July 2015 |
| CJPA074 | Chair | CV1198B | KPC | CNP July 2015 |
| CJPA075 | Chair | CV1198B | KPC | CNP July 2015 |
| CJPA060 | Desk | SCE 127 | KPC | CNP July 2015 |
| CJPA065 | Filing Cabinet | SG 71 | KPC | CNP July 2015 |
| CJPA095 | Chair | CMF56AS | KPT | CNP July 2015 |
| CJPA099 | Chair | CV1198B | KPT | CNP July 2015 |
| CJPA100 | Chair | CV1198B | KPT | CNP July 2015 |
| CJPA089 | Conference Table | SMT 9118 | KPT | CNP July 2015 |
| CJPA085 | Desk | SCE 127 | KPT | CNP July 2015 |
| CJPA090 | Filing Cabinet | SG 71 | KPT | CNP July 2015 |
| CJPA200 | Helmet | FF358 | KPT | CNP July 2015 |
| CJPA139 | Laptop | Laptop | KPT | CNP July 2015 |
| CJPA002 | LCD Projector | 1210S (LC-602) | KPT | CNP July 2015 |
| CJPA262 | Chair | CMF56AS | KRT | CNP July 2015 |
| CJPA266 | Chair | CV1198B | KRT | CNP July 2015 |
| CJPA268 | Chair | CV1198B | KRT | CNP July 2015 |
| CJPA251 | Desk | SCE 127 | KRT | CNP July 2015 |
| CJPA256 | Filing Cabinet | SG 71 | KRT | CNP July 2015 |
| CJPA170 | Laptop | PC 26 | KRT | CNP July 2015 |
| CJPA157 | Car | OI 7495 | PNP | CNP July 2015 |
| CJPA022 | Filing Cabinet | Filing Cabinet | PNP | CNP July 2015 |
| CJPA231 | Chair | CV1198B | PVG | CNP July 2015 |
| CJPA232 | Chair | CV1198B | PVG | CNP July 2015 |
| CJPA233 | Chair | CV1198B | PVG | CNP July 2015 |
| CJPA234 | Chair | CV1198B | PVG | CNP July 2015 |
| CJPA292 | Chair | CMF56AS | PVG | CNP July 2015 |
| CJPA282 | Desk | SCE 127 | PVG | CNP July 2015 |
| CJPA287 | Filing Cabinet | SG 71 | PVG | CNP July 2015 |
| CJPA326 | Chair | CMF56AS | SRP | CNP July 2015 |
| CJPA330 | Chair | CV1198B | SRP | CNP July 2015 |
| CJPA331 | Chair | CV1198B | SRP | CNP July 2015 |
| CJPA316 | Desk | SCE 127 | SRP | CNP July 2015 |
| CJPA321 | Filing Cabinet | SG 71 | SRP | CNP July 2015 |
| CJPA195 | Helmet | FF358 | SRP | CNP July 2015 |
| CJPA155 | Car | OI 7496 | PNP | CNP on 1 October 2015 |
| CJPA115 | Chair | CMF56AS | BMC | Hand over to the Province July 2015 |
| CJPA116 | Chair | CMF56AS | BMC | Hand over to the Province July 2015 |
| CJPA117 | Chair | CMF56AS | BMC | Hand over to the Province July 2015 |
| CJPA120 | Chair | CV1198B | BMC | Hand over to the Province July 2015 |
| CJPA121 | Chair | CV1198B | BMC | Hand over to the Province July 2015 |
| CJPA108 | Conference Table | SMT 9118 | BMC | Hand over to the Province July 2015 |
| CJPA105 | Desk | SCE 127 | BMC | Hand over to the Province July 2015 |
| CJPA106 | Desk | SCE 127 | BMC | Hand over to the Province July 2015 |
| CJPA107 | Desk | SCE 147 | BMC | Hand over to the Province July 2015 |
| CJPA110 | Filing Cabinet | SG 71 | BMC | Hand over to the Province July 2015 |
| CJPA111 | Filing Cabinet | SG 71 | BMC | Hand over to the Province July 2015 |
| CJPA112 | Filing Cabinet | SG 71 | BMC | Hand over to the Province July 2015 |
| CJPA113 | Filing Cabinet | VD4D | BMC | Hand over to the Province July 2015 |
| CJPA194 | Helmet | FF358 | BMC | Hand over to the Province July 2015 |
| CJPA243 | LCD Monitor | LCD Monitor | BMC | Hand over to the Province July 2015 |
| CJPA178 | Motorbike | OI 8655 | BMC | Hand over to the Province July 2015 |
| CJPA220 | Print Server | Print Server | BMC | Hand over to the Province July 2015 |
| CJPA125 | Printer | Laser Jet Pro M1132 | BMC | Hand over to the Province July 2015 |
| CJPA081 | Refrigerator | Refrigerator | BMC | Hand over to the Province July 2015 |
| CJPA122 | Safe | 700 (155 kg) | BMC | Hand over to the Province July 2015 |
| CJPA244 | System Unit | System Unit | BMC | Hand over to the Province July 2015 |
| CJPA245 | UPS | UPS | BMC | Hand over to the Province July 2015 |
| CJPA084 | Water Dispenser | WD-Q771FCR | BMC | Hand over to the Province July 2015 |
| CJPA227 | Air-Con | Air-Con | KCH | Hand over to the Province July 2015 |
| CJPA212 | Chair | CMF56AS | KCH | Hand over to the Province July 2015 |
| CJPA213 | Chair | CMF56AS | KCH | Hand over to the Province July 2015 |
| CJPA214 | Chair | CMF56AS | KCH | Hand over to the Province July 2015 |
| CJPA277 | Chair | CV1198B | KCH | Hand over to the Province July 2015 |
| CJPA278 | Chair | CV1198B | KCH | Hand over to the Province July 2015 |
| CJPA205 | Conference Table | SMT 9118 | KCH | Hand over to the Province July 2015 |
| CJPA204 | Desk | SCE 140 | KCH | Hand over to the Province July 2015 |
| CJPA273 | Desk | SCE 127 | KCH | Hand over to the Province July 2015 |
| CJPA274 | Desk | SCE 127 | KCH | Hand over to the Province July 2015 |
| CJPA207 | Filing Cabinet | SG 71 | KCH | Hand over to the Province July 2015 |
| CJPA208 | Filing Cabinet | SG 71 | KCH | Hand over to the Province July 2015 |
| CJPA209 | Filing Cabinet | SG 71 | KCH | Hand over to the Province July 2015 |
| CJPA210 | Filing Cabinet | VD4D | KCH | Hand over to the Province July 2015 |
| CJPA190 | Helmet | FF358 | KCH | Hand over to the Province July 2015 |
| CJPA247 | LCD Monitor | LCD Monitor | KCH | Hand over to the Province July 2015 |
| CJPA188 | Motorbike | OI 8665 | KCH | Hand over to the Province July 2015 |
| CJPA267 | Print Server | Print Server | KCH | Hand over to the Province July 2015 |
| CJPA177 | Printer | Laser Jet Pro M1132 | KCH | Hand over to the Province July 2015 |
| CJPA217 | Refrigerator | Refrigerator | KCH | Hand over to the Province July 2015 |
| CJPA215 | Safe | 700 (155 kg) | KCH | Hand over to the Province July 2015 |
| CJPA249 | System Unit | System Unit | KCH | Hand over to the Province July 2015 |
| CJPA257 | UPS | UPS | KCH | Hand over to the Province July 2015 |
| CJPA216 | Water Dispenser | ABS-SC9 HC | KCH | Hand over to the Province July 2015 |
| CJPA059 | Camera | Camera | KDL | Hand over to the Province July 2015 |
| CJPA345 | Chair | CMF56AS | KDL | Hand over to the Province July 2015 |
| CJPA346 | Chair | CMF56AS | KDL | Hand over to the Province July 2015 |
| CJPA342 | Desk | SCE 127 | KDL | Hand over to the Province July 2015 |
| CJPA343 | Desk | SCE 127 | KDL | Hand over to the Province July 2015 |
| CJPA344 | Filing Cabinet | SG 71 | KDL | Hand over to the Province July 2015 |
| CJPA189 | Helmet | FF358 | KDL | Hand over to the Province July 2015 |
| CJPA339 | LCD Monitor | LCD Monitor | KDL | Hand over to the Province July 2015 |
| CJPA218 | Print Server | Print Server | KDL | Hand over to the Province July 2015 |
| CJPA174 | Printer | Laser Jet Pro M1132 | KDL | Hand over to the Province July 2015 |
| CJPA347 | Safe | 700 (155 kg) | KDL | Hand over to the Province July 2015 |
| CJPA340 | System Unit | System Unit | KDL | Hand over to the Province July 2015 |
| CJPA341 | UPS | UPS | KDL | Hand over to the Province July 2015 |
| CJPA348 | Water Dispenser | SC2 | KDL | Hand over to the Province July 2015 |
| CJPA058 | Camera | Camera | KPT | Hand over to the Province July 2015 |
| CJPA096 | Chair | CMF56AS | KPT | Hand over to the Province July 2015 |
| CJPA097 | Chair | CMF56AS | KPT | Hand over to the Province July 2015 |
| CJPA098 | Chair | CMF56AS | KPT | Hand over to the Province July 2015 |
| CJPA101 | Chair | CV1198B | KPT | Hand over to the Province July 2015 |
| CJPA102 | Chair | CV1198B | KPT | Hand over to the Province July 2015 |
| CJPA086 | Desk | SCE 127 | KPT | Hand over to the Province July 2015 |
| CJPA087 | Desk | SCE 127 | KPT | Hand over to the Province July 2015 |
| CJPA088 | Desk | SCE 147 | KPT | Hand over to the Province July 2015 |
| CJPA091 | Filing Cabinet | SG 71 | KPT | Hand over to the Province July 2015 |
| CJPA092 | Filing Cabinet | SG 71 | KPT | Hand over to the Province July 2015 |
| CJPA093 | Filing Cabinet | SG 71 | KPT | Hand over to the Province July 2015 |
| CJPA094 | Filing Cabinet | VD4D | KPT | Hand over to the Province July 2015 |
| CJPA201 | Helmet | FF358 | KPT | Hand over to the Province July 2015 |
| CJPA308 | LCD Monitor | LCD Monitor | KPT | Hand over to the Province July 2015 |
| CJPA180 | Motorbike | OI 8657 | KPT | Hand over to the Province July 2015 |
| CJPA311 | Print Server | Print Server | KPT | Hand over to the Province July 2015 |
| CJPA124 | Printer | Laser Jet Pro M1132 | KPT | Hand over to the Province July 2015 |
| CJPA082 | Refrigerator | Refrigerator | KPT | Hand over to the Province July 2015 |
| CJPA103 | Safe | 700 (155 kg) | KPT | Hand over to the Province July 2015 |
| CJPA309 | System Unit | System Unit | KPT | Hand over to the Province July 2015 |
| CJPA310 | UPS | UPS | KPT | Hand over to the Province July 2015 |
| CJPA083 | Water Dispenser | WD-Q771FCR | KPT | Hand over to the Province July 2015 |
| CJPA229 | Air-Con | Air-Con | KRT | Hand over to the Province July 2015 |
| CJPA263 | Chair | CMF56AS | KRT | Hand over to the Province July 2015 |
| CJPA264 | Chair | CMF56AS | KRT | Hand over to the Province July 2015 |
| CJPA265 | Chair | CMF56AS | KRT | Hand over to the Province July 2015 |
| CJPA269 | Chair | CV1198B | KRT | Hand over to the Province July 2015 |
| CJPA270 | Chair | CV1198B | KRT | Hand over to the Province July 2015 |
| CJPA252 | Desk | SCE 127 | KRT | Hand over to the Province July 2015 |
| CJPA253 | Desk | SCE 127 | KRT | Hand over to the Province July 2015 |
| CJPA254 | Desk | SCE 140 | KRT | Hand over to the Province July 2015 |
| CJPA258 | Filing Cabinet | SG 71 | KRT | Hand over to the Province July 2015 |
| CJPA259 | Filing Cabinet | SG 71 | KRT | Hand over to the Province July 2015 |
| CJPA260 | Filing Cabinet | SG 71 | KRT | Hand over to the Province July 2015 |
| CJPA261 | Filing Cabinet | VD4D | KRT | Hand over to the Province July 2015 |
| CJPA246 | LCD Monitor | LCD Monitor | KRT | Hand over to the Province July 2015 |
| CJPA183 | Motorbike | OI 8660 | KRT | Hand over to the Province July 2015 |
| CJPA337 | Print Server | Print Server | KRT | Hand over to the Province July 2015 |
| CJPA175 | Printer | Laser Jet Pro M1132 | KRT | Hand over to the Province July 2015 |
| CJPA307 | Refrigerator | Refrigerator | KRT | Hand over to the Province July 2015 |
| CJPA271 | Safe | 700 (155 kg) | KRT | Hand over to the Province July 2015 |
| CJPA248 | System Unit | System Unit | KRT | Hand over to the Province July 2015 |
| CJPA250 | UPS | UPS | KRT | Hand over to the Province July 2015 |
| CJPA306 | Water Dispenser | SC2 | KRT | Hand over to the Province July 2015 |
| CJPA327 | Chair | CMF56AS | SRP | Hand over to the Province July 2015 |
| CJPA328 | Chair | CMF56AS | SRP | Hand over to the Province July 2015 |
| CJPA329 | Chair | CMF56AS | SRP | Hand over to the Province July 2015 |
| CJPA332 | Chair | CV1198B | SRP | Hand over to the Province July 2015 |
| CJPA333 | Chair | CV1198B | SRP | Hand over to the Province July 2015 |
| CJPA320 | Conference Table | SMT 9118 | SRP | Hand over to the Province July 2015 |
| CJPA317 | Desk | SCE 127 | SRP | Hand over to the Province July 2015 |
| CJPA318 | Desk | SCE 127 | SRP | Hand over to the Province July 2015 |
| CJPA319 | Desk | SCE 140 | SRP | Hand over to the Province July 2015 |
| CJPA322 | Filing Cabinet | SG 71 | SRP | Hand over to the Province July 2015 |
| CJPA323 | Filing Cabinet | SG 71 | SRP | Hand over to the Province July 2015 |
| CJPA324 | Filing Cabinet | SG 71 | SRP | Hand over to the Province July 2015 |
| CJPA325 | Filing Cabinet | VD4D | SRP | Hand over to the Province July 2015 |
| CJPA196 | Helmet | FF358 | SRP | Hand over to the Province July 2015 |
| CJPA312 | LCD Monitor | LCD Monitor | SRP | Hand over to the Province July 2015 |
| CJPA150 | Motorbike | OI 8654 | SRP | Hand over to the Province July 2015 |
| CJPA315 | Print Server | Print Server | SRP | Hand over to the Province July 2015 |
| CJPA128 | Printer | Laser Jet Pro M1132 | SRP | Hand over to the Province July 2015 |
| CJPA336 | Refrigerator | Refrigerator | SRP | Hand over to the Province July 2015 |
| CJPA334 | Safe | 700 () | SRP | Hand over to the Province July 2015 |
| CJPA313 | System Unit | System Unit | SRP | Hand over to the Province July 2015 |
| CJPA314 | UPS | UPS | SRP | Hand over to the Province July 2015 |
| CJPA335 | Water Dispenser | SC2 | SRP | Hand over to the Province July 2015 |
| CJPA353 | Air-Con | Air-Con | BAT | Hand over to the province on 1 October 2015 |
| CJPA354 | Chair | CMF56AS | BAT | Hand over to the province on 1 October 2015 |
| CJPA355 | Chair | CMF56AS | BAT | Hand over to the province on 1 October 2015 |
| CJPA356 | Chair | CMF56AS | BAT | Hand over to the province on 1 October 2015 |
| CJPA357 | Chair | CMF56AS | BAT | Hand over to the province on 1 October 2015 |
| CJPA360 | Chair | CV1198B | BAT | Hand over to the province on 1 October 2015 |
| CJPA361 | Chair | CV1198B | BAT | Hand over to the province on 1 October 2015 |
| CJPA362 | Chair | CV1198B | BAT | Hand over to the province on 1 October 2015 |
| CJPA363 | Chair | CV1198B | BAT | Hand over to the province on 1 October 2015 |
| CJPA372 | Conference Table | SMT 9118 | BAT | Hand over to the province on 1 October 2015 |
| CJPA365 | Desk | SCE 127 | BAT | Hand over to the province on 1 October 2015 |
| CJPA367 | Desk | SCE 127 | BAT | Hand over to the province on 1 October 2015 |
| CJPA368 | Desk | SCE 128 | BAT | Hand over to the province on 1 October 2015 |
| CJPA369 | Desk | SCE 128 | BAT | Hand over to the province on 1 October 2015 |
| CJPA371 | Filing Cabinet | SG 71 | BAT | Hand over to the province on 1 October 2015 |
| CJPA197 | Helmet | FF358 | BAT | Hand over to the province on 1 October 2015 |
| CJPA239 | LCD Monitor | LCD Monitor | BAT | Hand over to the province on 1 October 2015 |
| CJPA151 | Motorbike | OI 8651 | BAT | Hand over to the province on 1 October 2015 |
| CJPA242 | Print Server | Print Server | BAT | Hand over to the province on 1 October 2015 |
| CJPA127 | Printer | Laser Jet Pro M1132 | BAT | Hand over to the province on 1 October 2015 |
| CJPA373 | Printer desk | Cabinet | BAT | Hand over to the province on 1 October 2015 |
| CJPA351 | Refrigerator | HS.56 BS | BAT | Hand over to the province on 1 October 2015 |
| CJPA364 | Safe | 500 | BAT | Hand over to the province on 1 October 2015 |
| CJPA240 | System Unit | System Unit | BAT | Hand over to the province on 1 October 2015 |
| CJPA241 | UPS | UPS | BAT | Hand over to the province on 1 October 2015 |
| CJPA129 | Water Dispenser | WD-Q771FCR | BAT | Hand over to the province on 1 October 2015 |
| CJPA225 | Air-Con | Air-Con | KPC | Hand over to the province on 1 October 2015 |
| CJPA057 | Camera | Camera | KPC | Hand over to the province on 1 October 2015 |
| CJPA071 | Chair | CMF56AS | KPC | Hand over to the province on 1 October 2015 |
| CJPA072 | Chair | CMF56AS | KPC | Hand over to the province on 1 October 2015 |
| CJPA073 | Chair | CMF56AS | KPC | Hand over to the province on 1 October 2015 |
| CJPA076 | Chair | CV1198B | KPC | Hand over to the province on 1 October 2015 |
| CJPA077 | Chair | CV1198B | KPC | Hand over to the province on 1 October 2015 |
| CJPA064 | Conference Table | SMT 9118 | KPC | Hand over to the province on 1 October 2015 |
| CJPA061 | Desk | SCE 127 | KPC | Hand over to the province on 1 October 2015 |
| CJPA062 | Desk | SCE 127 | KPC | Hand over to the province on 1 October 2015 |
| CJPA063 | Desk | SCE 140 | KPC | Hand over to the province on 1 October 2015 |
| CJPA066 | Filing Cabinet | SG 71 | KPC | Hand over to the province on 1 October 2015 |
| CJPA067 | Filing Cabinet | SG 71 | KPC | Hand over to the province on 1 October 2015 |
| CJPA068 | Filing Cabinet | SG 71 | KPC | Hand over to the province on 1 October 2015 |
| CJPA069 | Filing Cabinet | VD4D | KPC | Hand over to the province on 1 October 2015 |
| CJPA199 | Helmet | FF358 | KPC | Hand over to the province on 1 October 2015 |
| CJPA303 | LCD Monitor | LCD Monitor | KPC | Hand over to the province on 1 October 2015 |
| CJPA003 | LCD Projector | 1210S (LC-602) | KPC | Hand over to the province on 1 October 2015 |
| CJPA179 | Motorbike | OI 8656 | KPC | Hand over to the province on 1 October 2015 |
| CJPA219 | Print Server | Print Server | KPC | Hand over to the province on 1 October 2015 |
| CJPA123 | Printer | Laser Jet Pro M1132 | KPC | Hand over to the province on 1 October 2015 |
| CJPA079 | Refrigerator | Refrigerator | KPC | Hand over to the province on 1 October 2015 |
| CJPA078 | Safe | 700 () | KPC | Hand over to the province on 1 October 2015 |
| CJPA304 | System Unit | System Unit | KPC | Hand over to the province on 1 October 2015 |
| CJPA305 | UPS | UPS | KPC | Hand over to the province on 1 October 2015 |
| CJPA080 | Water Dispenser | WD-Q771FCR | KPC | Hand over to the province on 1 October 2015 |
| CJPA228 | Air-Con | Air-Con | PVG | Hand over to the province on 1 October 2015 |
| CJPA235 | Chair | CV1198B | PVG | Hand over to the province on 1 October 2015 |
| CJPA236 | Chair | CV1198B | PVG | Hand over to the province on 1 October 2015 |
| CJPA293 | Chair | CMF56AS | PVG | Hand over to the province on 1 October 2015 |
| CJPA294 | Chair | CMF56AS | PVG | Hand over to the province on 1 October 2015 |
| CJPA295 | Chair | CMF56AS | PVG | Hand over to the province on 1 October 2015 |
| CJPA296 | Chair | CV1198B | PVG | Hand over to the province on 1 October 2015 |
| CJPA297 | Chair | CV1198B | PVG | Hand over to the province on 1 October 2015 |
| CJPA298 | Chair | CV1198B | PVG | Hand over to the province on 1 October 2015 |
| CJPA299 | Chair | CV1198B | PVG | Hand over to the province on 1 October 2015 |
| CJPA286 | Conference Table | SMT 9118 | PVG | Hand over to the province on 1 October 2015 |
| CJPA283 | Desk | SCE 127 | PVG | Hand over to the province on 1 October 2015 |
| CJPA284 | Desk | SCE 127 | PVG | Hand over to the province on 1 October 2015 |
| CJPA285 | Desk | SCE 140 | PVG | Hand over to the province on 1 October 2015 |
| CJPA288 | Filing Cabinet | SG 71 | PVG | Hand over to the province on 1 October 2015 |
| CJPA289 | Filing Cabinet | SG 71 | PVG | Hand over to the province on 1 October 2015 |
| CJPA290 | Filing Cabinet | SG 71 | PVG | Hand over to the province on 1 October 2015 |
| CJPA291 | Filing Cabinet | VD4D | PVG | Hand over to the province on 1 October 2015 |
| CJPA192 | Helmet | FF358 | PVG | Hand over to the province on 1 October 2015 |
| CJPA193 | Helmet | FF358 | PVG | Hand over to the province on 1 October 2015 |
| CJPA338 | LCD Monitor | LCD Monitor | PVG | Hand over to the province on 1 October 2015 |
| CJPA185 | Motorbike | OI 8662 | PVG | Hand over to the province on 1 October 2015 |
| CJPA281 | Print Server | Print Server | PVG | Hand over to the province on 1 October 2015 |
| CJPA176 | Printer | Laser Jet Pro M1132 | PVG | Hand over to the province on 1 October 2015 |
| CJPA302 | Refrigerator | Refrigerator | PVG | Hand over to the province on 1 October 2015 |
| CJPA300 | Safe | 700 () | PVG | Hand over to the province on 1 October 2015 |
| CJPA279 | System Unit | System Unit | PVG | Hand over to the province on 1 October 2015 |
| CJPA280 | UPS | UPS | PVG | Hand over to the province on 1 October 2015 |
| CJPA301 | Water Dispenser | SC2 | PVG | Hand over to the province on 1 October 2015 |
| CJPA186 | Motorbike | OI 8663 | PVG | Kandal Province 1 October 2015 |
| CJPA198 | Helmet | FF358 | BAT | NMB July 2015 |
| CJPA001 | LCD Projector | 1210S (LC-602) | BMC | NMB July 2015 |
| CJPA181 | Motorbike | OI 8658 | KPT | NMB July 2015 |
| CJPA255 | Conference Table | SMT 9118 | KRT | NMB July 2015 |
| CJPA202 | Helmet | FF358 | KRT | NMB July 2015 |
| CJPA203 | Helmet | FF358 | KRT | NMB July 2015 |
| CJPA182 | Motorbike | OI 8659 | KRT | NMB July 2015 |
| CJPA168 | Laptop | PC 21 | PNP | NMB July 2015 |
| CJPA136 | Laptop | Laptop | SRP | NMB July 2015 |
| CJPA152 | Motorbike | OI 8653 | SRP | NMB July 2015 |

Appendix E

Actual Expenditure against Total Contract

Appendix E	Actual Expenditure against Total Contract

Table 4	Summary of CCJAP expenditure vs budget

| As per Contract no. 64318 Amendment #1 |  | Expenditure April 2013 – June 2015 (YEARS 1–3) |  |  |  | July 2015 – June 2016 (YEAR 4) |  |  |  | TOTAL EXPENDITURE AT PROJECT COMPLETION |  | Forecast variance from contract value at completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BUDGET CATEGORY | Contract Budget | Actual Expenditure (Apr–Jun 2013) | Actual Expenditure (July 2013 – June 2014) | Actual Expenditure (July 2014 – June 2015) | TOTAL expenditure to 30 June 2015 | Budget (July 2015 – June 2016) | Actual Expenditure (July 2015 – Sept 2015) | % of Budget spent | Remaining Budget | Total Actual to 30 Sept 2015 | Remaining Budget to project completion |  |
| MILESTONE CLAIMS | $2,089,315 | $522,329 | $417,863 | $626,795 | $1,566,986 | $522,329 | $0 | 0% | $522,329 | $1,566,986 | $522,329 |  |
| REIMBURSABLE COSTS |  |  |  |  |  |  |  |  |  |  |  |  |
| Long-Term Adviser fees | $2,653,534 | $162,562 | $788,697 | $852,701 | $1,803,961 | $628,874 | $143,647 | 23% | $485,227 | $1,947,608 | $705,926 | $220,699 |
| Short-Term Adviser fees | $92,160 | $10,977 | $15,923 | $2,048 | $28,948 | $17,913 | $0 | 0% | $17,913 | $28,948 | $63,212 | $45,299 |
| Adviser support costs | $164,588 | $12,907 | $33,289 | $58,031 | $104,227 | $55,024 | $6,906 | 13% | $48,118 | $111,134 | $53,454 | $5,337 |
| Activity costs | $4,977,203 | $0 | $339,522 | $1,319,632 | $1,659,155 | $1,329,734 | $626,067 | 47% | $703,667 | $2,285,222 | $2,691,981 | $1,988,314 |
| Reimbursable set up costs | $566,400 | $143,840 | $221,804 | $4,831 | $370,476 |  |  |  |  | $370,476 | $195,924 | $195,924 |
| Reimbursable operational costs | $1,456,800 | $28,683 | $263,237 | $257,248 | $549,168 | $181,992 | $44,914 | 25% | $137,078 | $594,081 | $862,719 | $725,640 |
| TOTAL | $12,000,000 | $881,298 | $2,080,335 | $3,121,287 | $6,082,921 | $2,735,866 | $821,534 | 30% | $1,914,332 | $6,904,455 | $5,095,545 | $3,181,214 |
| Project began April 2013 |  |  |  |  |  |  |  |  |  |  |  |  |
| Project ends June 2016 |  | 39 months |  |  |  |  |  |  |  |  |  |  |
| Project time elapsed to end September 2015 |  | 30 months |  |  |  |  |  |  |  |  |  |  |
| Percentage through project |  | 76.92% |  |  |  |  |  |  |  |  |  |  |

Figure 10	Contract Budget vs Actual Expenditure April 2013 – September 2015