| Ministry of Health | 2015 ANNUAL PERFORMANCE MONITORING REPORT, Volume 2 |
| --- | --- |
| March, 2016 | Second Health Sector Support Program, 2009-16 |

MINISTRY OF HEALTH

No. 53, Street 28, Beoung Kak I, Toul Kork

Phnom Penh, Kingdom of Cambodia.

Table of Contents

Annexes

Annex A. Program Development Objectives Indicators by Province and Provincial Rankings	3

Annex B. Program Development Objectives Indicators by OD and PRH	15

Annex C. Infrastructure Plan and Tables	48

Annex D. SOA Performance Graphs and Table of SDG Allocation	49

Annex E. Staff Deployment	92

Annex F. Good Governance Framework	95

Annex G. Status of Legal Covenants for WB Financing Agreement (Cr. 4470-KH)	114

Annex H. Health Equity Funds, Total 2015	120

## Annex A.Program Development Objectives Indicators by Province

# Annex B. Program Development Objectives Indicators by OD

Annex C. Infrastructure Plan and Tables

Annex D. SOA Tables and Graphs

Table of SDG Allocation

| Province | PRH/OD SOA | Contract Population 2015 | Contract MOH-PHD | Contract PHD with PRH or OD | SDG Imple-mentation Date | SDG 12 months contract budget | Program Director Approved Release SDG for Q3 | Program Director Approved Release SDG for Q4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Kampong Cham |  |  | 2-Feb-15 |  |  |  | 23-Jun-15 | 4-Aug-15 |
|  | Kg. Cham PRH | 1,031,738 |  | 16-Dec-14 | 1-Jan-10 | 165,000 |  |  |
|  | Chamkar Leu-Stueng Trang | 117,206 |  | 11-Dec-14 | 1-Jan-10 | 200,000 |  |  |
|  | Choeung Prey-Batheay | 200,873 |  | 16-Dec-14 | 1-Jan-10 | 237,500 |  |  |
|  | Prey Chhor-Kang Meas | 195,361 |  | 11-Dec-14 | 1-Jan-10 | 243,600 |  |  |
|  |  |  |  |  |  | 846,100 |  |  |
| Tbong Khmum |  |  | 2-Feb-15 |  |  |  | 20-Jul-15 | 18-Aug-15 |
|  | Memut | 137,731 |  | 11-Dec-14 | 1-Jul-09 | 177,793 |  |  |
|  | Ponhea Krek-Dambae | 222,473 |  | 19-Dec-14 | 1-Jul-09 | 254,600 |  |  |
|  |  |  |  |  |  | 432,393 |  |  |
| Koh Kong |  |  | 2-Feb-15 |  |  |  | 8-Jun-15 | 18-Aug-15 |
|  | Koh Kong PRH | 125,151 |  | 17-Dec-14 | 1-Aug-09 | 73,058 |  |  |
|  | Smach Meanchey | 59,678 |  | 31-Dec-14 | 1-Aug-09 | 109,586 |  |  |
|  | Sre Ambel | 65,473 |  | 12-Dec-14 | 1-Aug-09 | 201,160 |  |  |
|  |  |  |  |  |  | 383,804 |  |  |
| Mondul Kiri |  |  | 2-Feb-15 |  |  |  | 17-Jun-15 | 18-Aug-15 |
|  | Mondulkiri PRH | 70,935 |  | 11-Dec-14 | 1-Oct-09 | 91,378 |  |  |
|  | Sen Monorom | 70,935 |  | 12-Dec-14 | 1-Oct-09 | 185,525 |  |  |
|  |  |  |  |  |  | 276,903 |  |  |
| Preah Vihear |  |  | 2-Feb-15 |  |  |  | 8-Jun-15 | 10-Aug-15 |
|  | Preah Vihear PRH | 206,027 |  | 17-Dec-14 | 1-Oct-09 | 196,034 |  |  |
|  | Tbeng Meanchey | 206,027 |  | 17-Dec-14 | 1-Oct-09 | 416,573 |  |  |
|  |  |  |  |  |  | 612,607 |  |  |
| Prey Veng |  |  | 2-Feb-15 |  |  |  | 8-Jun-15 | 25-Aug-15 |
|  | Pearaing | 202,092 |  | 17-Dec-14 | 1-Jul-09 | 237,614 |  |  |
|  | Preah Sdach | 119,632 |  | 17-Dec-14 | 1-Jul-09 | 140,394 |  |  |
|  |  |  |  |  |  | 378,008 |  |  |
| Ratanak Kiri |  |  | 2-Feb-15 |  |  |  | 8-Jun-15 | 18-Aug-15 |
|  | Ratanakiri PRH | 196,557 |  | 18-Dec-14 | 1-Aug-10 | 220,501 |  |  |
|  | Banlong | 196,557 |  | 16-Dec-14 | 1-Aug-10 | 330,751 |  |  |
|  |  |  |  |  |  | 551,252 |  |  |
| Siem Reap |  |  | 2-Feb-15 |  |  |  | 1-Jul-15 | 14-Sep-15 |
|  | Siem Reap PRH | 1,123,240 |  | 19-Dec-14 | 1-Jan-10 | 182,038 |  |  |
|  | Kralanh | 122,556 |  | 9-Dec-14 | 1-Jan-10 | 149,729 |  |  |
|  | Siem Reap | 370,032 |  | 12-Dec-14 | 1-Jan-10 | 270,860 |  |  |
|  | Sotnikum | 287,462 |  | 9-Dec-14 | 1-Jan-10 | 342,000 |  |  |
|  | Angkor Chum | 232,948 |  | 22-Dec-14 | 1-Jan-10 | 257,851 |  |  |
|  |  |  |  |  |  | 1,202,478 |  |  |
| Takeo |  |  | 2-Feb-15 |  |  |  | 1-Jul-15 | 12-Aug-15 |
|  | Ta Keo PRH | 972,149 |  | 12-Dec-14 | 1-Jun-10 | 200,000 |  |  |
|  | Ang Rokar | 144,174 |  | 12-Dec-14 | 1-Jul-09 | 159,849 |  |  |
|  | Bati | 203,477 |  | 12-Dec-14 | 1-Jun-10 | 246,723 |  |  |
|  | Daun Keo | 224,492 |  | 12-Dec-14 | 1-Jun-10 | 217,758 |  |  |
|  | Kirivong | 233,983 |  | 12-Dec-14 | 1-Jul-09 | 262,801 |  |  |
|  | Prey Kabass | 165,330 |  | 12-Dec-14 | 1-Jun-10 | 200,467 |  |  |
|  |  |  |  |  |  | 1,287,598 |  |  |
| Otdar Meanchey |  |  | 2-Feb-15 |  |  |  | 8-Jun-15 | 18-Aug-15 |
|  | Otdar Meanchey PRH | 239,371 |  | 8-Dec-14 | 1-Jan-10 | 110,200 |  |  |
|  | Samraong | 239,371 |  | 5-Dec-14 | 1-Jan-10 | 440,800 |  |  |
|  |  |  |  |  |  | 551,000 |  |  |
| Bateay Meanchey |  |  | 2-Feb-15 |  |  |  | 17-Jun-15 | 1-Sep-15 |
|  | Poipet | 202,687 |  | 12-Dec-14 | 1-Jan-14 | 244,728 |  |  |
|  | Preah Net Preah | 153,606 |  | 11-Dec-14 | 1-Jan-14 | 181,729 |  |  |
|  |  |  |  |  |  | 426,457 |  |  |
| Battambang |  |  | 2-Feb-15 |  |  |  | 8-Jun-15 | 4-Aug-15 |
|  | Battambang PRH | 1,164,022 |  | 27-Jan-15 | 1-Jan-14 | 203,500 |  |  |
|  |  |  |  |  |  | 203,500 |  |  |
| Pursat |  |  | 2-Feb-15 |  |  |  | 8-Jun-15 | 18-Aug-15 |
|  | Bankan | 133,205 |  | 15-Dec-14 | 1-Jan-14 | 174,459 |  |  |
|  |  |  |  |  |  | 174,459 |  |  |
| Stung Treng |  |  | 2-Feb-15 |  |  |  | 23-Jun-15 | 18-Aug-15 |
|  | Stung Treng PRH | 130,628 |  | 12-Dec-14 | 1-Jan-14 | 111,093 |  |  |
|  | Stung Treng | 130,628 |  | 9-Dec-14 | 1-Jan-14 | 206,315 |  |  |
|  | 36 SOAs |  | 14 contracts |  |  | 317,408 |  |  |
|  | Total |  |  |  |  | 7,643,967 |  |  |

# Annex E. Staff Deployment

## Annex F. Good Governance Framework

## Status of Good Governance Framework Applicable to Activities funded by Pool account – Updated in January 2016

(Abbreviation: C = Completed, PC = Partially Completed,  SC = Substantially Completed, AS = Action Started, ANS = Action Not Started, AB =  Action Begun)

|  | Issue | Action to Mitigate Risk | Responsibility | Target/Monitoring | Status | Action/Target |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Element 1: Procurement |  |  |  |  |  |
| 1a | Ensure transparent and efficient procurement | The MoH shall use the services of an International ProcurementSpecialist/Advisor and National Procurement Staff engaged under TOR satisfactory to IDA for all procurements funded from the pool account at all levels under the Program. The individuals selected for these fiduciary positions will be subject to prior review by the IDA. . For contracts (in relation to item required by the SoAs for their operations) estimated to cost less than USD 50,000 per package, procurement may be carried out by the respective SoA. ,. Invite Civil Society Organizations for key procurement cycle activities | MoH (represented by HSSP2 ) has commenced work on the full range of procurement under its portfolio. The MoH/HSSP2 assumes full responsibility for the conduct of the procurement including fiduciary responsibility. The Procurement Review Committee (PRC) appointed in accordance with the RGCs SOP and regulation on externally donor funded programs will clear and sign on all procurement evaluation reports finalized under the HSSP2. In addition IDA will review ‘Prior Review’ category procurements at all required stages. IDA will carry out selective reviews for ‘Post Review’ category packages at a later date. For procurements conducted by the SoAs, a representative from the Procurment Group of the HSSP2 Secretariat attends the bid opening proceedings and subsequently reviews the bid evaluation report prepared by the SoA prior to contract award. This is carried out at the SoA offices in the provinces. Also, it has now been agreed with the IDA that procurement of items which do not have adequate bidders at the SoA provincial level may be carried out at the central level through the HSSP2 Secretariat. Also, as agreed with the IDA, in cases where the same type of equipment is required by several SoAs, the quantities are aggregated and procurement is carried out at the central level through the HSSP2 Secretariat. | All major procurements under HSSP2 are required to be substantially completed by mid 2015 (as in the latest approved Procurement Plan as on December 2014) so that physical deliver of goods or the physical ompletion of Works and Services are ensured by 31 December 2015 (the current HSSP2 closure date). IDA to monitor through quarterly portfolio review meetings and IDA prior and post reviews. Pool partners to monitor through supervision missions and IDA prior and post reviews. | The International Procurement Specialist/Advisor has been selected and is in place since 23 December 2013. The latest updated Procurement Plan has been approved by the IDA. All procurments are being conducted in accordance with the SOP and revised procurement thresholds. Procurement Training was provided by the HSSP2 Secretariat to the SoAs on three occasions in December 2013 (Sihanoukville), July 2014 (Stung Treng) and September 2015 (BanteyMeanchey) The latest IDA Post Review was conducted May 2014. The post review findings were issued in the form of a clean report of findings without any objectionable issues being raised. Procurement has been decentralized to SOAs. As on date, most of the planned procurements (as reflected in the updated and approved procurement plan) are completed. Only the following procurement packages are in the implementation pipeline: - Works for Improvement of Water Supply to HCs (ICB tender issued and bid opening on 21 Jan 2015) - Works for Improvement of sanitation to HCs (NCB tender issuance date is fixed on 19 January 2015 and bid opening on 17 Feb 2015) - RFP for QCBS package for selection of Health Equity Fund Operator for Cluster 23 and Cluster 24 has been scheduled to be issued on 15Jan 2015 with proposal submission deadline of 13 Feb 2015 | Continue donor monitoring through JQM and Post Review Missions Monitoring through Financial and Technical Audits. Monitoring of SoA procurement through HSSP2 Secretariat MEF has communicated that MEDICAM and Medical Association of Cambodia (who are NGO’s) have been mandated to attend Bid Openings and Contract Signing Proceedings. MoH is following this guideline for all NCB and NGO selections/Single Source Selections |
| 1b | Strengthen the design, delivery, contract administration and construction supervision capability of MOH. | MOH to engage a firm/s for at least the first three years of the Program, to assist on design, delivery, contract administration and construction supervision and train MOH and sub-national level staff. | MOH to prepare TOR with IDA NOL on behalf of pool partners. |  | Engineering Firm wascontracted for supervision of major civil works. One contract was awarded in Nov 2011 and the second contract was awarded in Jann 2013 | HSSP2 Secretariat Infrastructure team to continuous minitor progress of selected supervision firm as well as monitor construction contract progress. Provincial civil work supervision committee to monitor progress of health facilities construction/renovation in addition to the l monitoring firm |
| 1c | Insufficient procurement capacity of MOH | MOH to employ (i) an experienced Procurement and International Contract Management Advisor to assist MOH with its procurement activities and with contract management duties and especially to build procurement and contract management capacity within MOH’s own staff, and (ii) national individual consultants with procurement experience to provide local support for procurement coordination and follow-up of procurement activities. | MOH with IDA NOL to TOR and selection method. |  | International Procurement Specialist/Advisor appointed and in place since December 2013. National Chief Procurement Officer appointed in Sept 2012 Two National Procurement Assistants were appointed in June 2013 | Ensure that the HSSP2 Procurement Team (currently consisting of 1 international advisor and 1 national chief procurement officer and 1 procurement assistant) carry out their duties to ensure completion of all procurement planned for HSSP2 within December 2015. One Procurement Assistant resigned in September 2014 Procurement at sub national level assisted by HSSP2 secretariat procurement units |
| 1d | Clear procurement procedures and thresholds needed. | MoHis required to follow IDA’s Procurement and Consultant Guidelines and the procurement provisions of the Financing Agreement, including the use under NCB and Shopping methods as in the RGC’s Manual on Standard Operating Procedures for Implementing Externally Assisted Projects (SOP) including the Externally Assisted Procurement Manual for Goods, Works and Services (SOP/PM), mandated by Sub-Decree No. 14 on dated February 26, 2007. | MoH through the HSSP2 Procurement Group and the RGCs Procurement review Committee | Pool partners to monitor through supervision missions and quarterly review meetings among MEF, IPA and IDA. Supervision of MoH by IDA | Threshold for procurement - shopping, NCB, ICB as determined by MEF and agreements have been followed. New threshold for procurement to be conducted at HSSP2 secretariat and SOAs have bneen followed. | New procurementthresholdset by the Bank have been followed. (Nov 12 2013) |
| 1e | Informal payments by contractors suppliers and consultants | All contractors, suppliers and consultants – firms or individuals, national and international – bidding for contracts under the Program shall sign the Declaration on Ethical Conduct and Fraud and Corruption as articulated in the SOP/PM. Item 5 of the Declaration will be extended to read: “In connection with this procurement exercise and any contract that is awarded to us as a result thereof, no payments have been made or will be made by us, our associates, agents, shareholders, partners or their relatives or associates to any of the staff, associates, consultants, employees or relatives of such who are involved with the procurement process, contract implementation, and the issuance of progress payments on behalf of the purchaser, client or employer.” Include amended Declaration in all bidding documents, RFPs, and contracts. | MoH required to follow as per RGC’s SOP/Procurement Manual requirement | MOH to monitor. IDA to verify during prior and post reviews. | Program signed the Declaration on Ethical Conduct and Fraud and Corruption for record. They are included in all signed contracts. Contract awards information are disclosed on MOH website. (June 2012) | The amended Declaration has been incorporated in all new contracts. |
| 1f | Possible delayedProcurement Plans | Preparation of realistic annual Procurement Plan for goods, works and consultant services to be financed from the pool account, based on the AOP. | MOH/PHD and IDA NOL. | Procurement Plan will be updated bi-annually by mid March and mid-August. | Lated update of Procurement Plan as on December 2014 has been approved by the WB on behalf of the Pool Fund Partners. | Procurement Plan will be further updated as and when required to reflect the latest position on HSSP2 procurements. |
| 2 | Element 2: Financial Management |  |  |  |  |  |
| 2a | Weakness in FM procedures and practices at national and sub-national levels that may impact negatively on Program implementation. | A Financial Management Improvement Plan (FMIP) acceptable to the pool partners will be developed and implemented. | MOH with guidance from IDA and pool partners. | FMIP should be finalized so as to allow the action in item 2b, appointment of consulting firm to assist in implementing the plan by effectiveness. | SC: FMIP has been developed and approved. Contract of FMIP firm was expired in February 2011. Ongoing negotiation with FMIP for contract extension. There is a need to implement training to PHDs and ODs/SOAs. TOR is being developed. Revised TOR for competitive selection of new FMIP firm has been circulated for comments. (June 2012) | DBF and FMIP firm to continue implementing the FMIP. Training on financial management is being conducted in accordance with the approved plan. Finalize extension of FMIP contract by 15 December 2011. To finalize TOR by 1st July 2012 (June 2012) See the report from the discussion on FM (JRM). Pending the selection of FMIP2, DBP has gone ahead conducting training on improvement on FM Management. (Nov 12, 2013) |
| 2b | Weakness in MOH FM capacity. | MOH/IPA to recruit consulting firm by effectiveness, with TOR acceptable to the IDA, to help MOH implement FMIP and to strengthen FM capacity in MOH and PHD and OD levels | MOH to work closely with the consultants and drive for additional FM staff at PHD and OD levels. | Consulting firm recruited to help MOH implement FMIP and targets achieved. | See 2a. | See 2a. |
| 2c | Weak internal controls at central and provincial levels | Adopt SOP/FMM and enforce compliance with during Program implementation, already mandated by Sub-Decree No. 14 dated February 26, 2007. Supplement by detailed procedures in a Program FM Manual, which will be an update of the HSSP Manual. | MOH. IDA NOL to Program FM Manual. | Note in Financing Agreement, Program FM Manual satisfactory to IDA to be completed by Effectiveness. MEF and IDA to monitor adoption of SOP/FMM. Pool partner FM supervision missions to verify compliance with Program FM Manual. | SC: FM Manual has been approved. Increase supervision from central level to PHDs and ODs. External Audit firm present audit findings at every JQM. | Will invite auditing firm to present audit findings on JQM on 20th June 2012 and will circulated Khmer version of audit report to all implementing units by 15th July 2012 (June 2012). Combined technical and financial audit report to be shared with all Implementing Units starting audit Q2-2013. (Nov 12 2013) Combined technical and financial audit report to be shared with all Implementing Units every quarter |
| 2d | Clarity of FM reporting to pool partners. | Formulate and agree on a template for quarterly Interim Financial Reports (IFRs). During implementation, IFRs, audited by the external auditors, will be furnished by MOH to the pool partners not later than 90 days after the end of each quarter. | MOH and pool partners. | Agree on the IFR format and content during negotiations. MOH to ensure timely audit and to monitor the quality of each report together with the pool partners. To submit IFR within 45 days after ending each quarter. | SC: Completed Template for IFR. IFR for Q1, Q2 and Q3 have been submitted. IFR for Q4 2009, Q1,Q2, Q3, Q4 2010 and IFRs for Q1, Q2, Q3, Q4 2011 and Q1 2012were submitted within 45 days (on time). Q2, Q3, Q4, 2012 and Q1, 2013 submitted on time (May 2013). Q2-2013 expected to be submitted in mid-August 2013. | Next IFR to be sumbitted by 15thAugust 2012 Final IFR of Q2-2013 submitted on Oct 14 2013. IFR Q3-2013 to be submitted on mid-November (nov 12 2013) IFR have been submitted on time |
| 2e | Strengthen Internal Audit Unit of MOH | MOH will appoint an international audit advisor to help implement the IA manual and strengthen and provide training to the IAU, including hands-on, during the 6-monthly audit exercises. | MOH to prepare TOR. IPA to recruit. | Appoint IA advisor by three months after effectiveness. MOH to closely monitor the performance of IAU and advisor’s work. Pool partners to monitor the performance during supervision missions. MOH will monitor IAA’s performance in accordance with the TOR and inception report (including training plan). | SC: The draft contract has been approved by the Bank. Consultant will start his services by mid February. PC: Although contract has been signed since 11 march 2010, selected consultant has not been on board. The Consultant started his service on 18th August 2010. Submission of inception report in Octover 2010 (November 2010). Training provided by the consultant will be continued until November 2011. Will request to extend the consultant contract based on request from IAD. (June 2012) TA for capacity building to internal audit department have been completed. | Consultant’s first contracted ended on December 2011. The MOH will request for intermittent 12 months extension. |
| 2f | External audit. | MOH to prepare TOR (with greater emphasis on internal controls and ISA 240) for continuous external audit, satisfactory to the IDA. MOH to review the audit reports, develop an action plan to implement the audit recommendations and follow up the status of their implementation. MOH will update the status of audit recommendation to the pool partners through the quarterly IFRs. | MOH to prepare TOR with IDA NOL by negotiation. IPA to recruit external auditors, with IDA NOL. MOH to facilitate audit exercise MOH. | TOR agreed by Negotiation. Appoint by effectiveness. MOH to prepare action plans within one month of receipt of audit report and follow up monthly. MOH to update status of implementation in each IFR. Pool partners to monitor during FM supervision missions. | SC: PWC was selected for audit services in 2009. Request for extension of the existing contract to cover scope of audit services in 2010 will be submitted for no-objection. TOR for combined Technical and Financial Audit has been approved by WB in October 2010. Selection of consulting firm is being conducted by IPA. Extension of current PWC contract to cover scope of audit Q1 2011. Signed contract for combined technical and financial audit in November 2011 Q1, Q2, Q3 2012 audit reports have been submitted to the Bank (May 2013) Financial statement of external audit report submitited to the Bank on Sept 30 2013.(Nov 12 2013) | Report on management responses to the audit recommendations will be submitted to JPIG by 18 February 2010. Audit Q1, Q2, Q3, and Q4, 2010 have been submitted (Q4 2010 has been completed on 30th March, 2011). Combined technical and financial audit reports for Q2, Q3 2011 completed in March 2012).(June 2012) The audit Q3 report will be submitted by 15th June 2012. The Q4 2011 audit started from 1st June 2012. (June 2012) Q4-2012, And Compbined 2012 Audit report will be submitted to the Bank by end of June 2013. Combined technical and financial quarterly audit reports have been submitted on time. Audit both technical and financial report of Q4 2015 will submiied in late of March |
| 2g | Distribution, management and use of pharmaceutical and medical supplies. | Distribution of all pharmaceutical and medical supplies funded by the pool account shall be made through the Central Medical Store (CMS). Extend the supervision on the management and use of pharmaceutical and medical supplies to national hospitals and VCCT sites. | MOH/CMS/Department for Drugs and Foods/National Programs/PHDs/ODs. | Target commencement for March 2009. Reviews of the system and its related controls are part of the scope of internal and external audits. Pool partners to monitor during supervision missions. | ANS Action started (See medical repview report) | Pharmaceutical and medical supplies will continue to distribute through CMS distribution system. Reviews of the system and its related controls are part of the scope of internal and external audits. |
| 2h | Minimize cash transactions | All progress payments to contractors, suppliers and consultants – firms, individuals, national and international – to be made by check or transfer to bank accounts. Cash transactions not to exceed US$500 limit as per SOP/FMM. Retain evidence for audit and IDA supervision missions. | MOH/PHDs | Note in financing agreement. MOH to monitor as part of the scope of internal and external audits. Pool partners to monitor during supervision missions. | SC: Cash transaction policy has been included in FM Manual. | MOH to monitor as part of the scope of internal and external audits through reqular JQMs. (June 2012) |
| 2j | Eliminate inconsistencies in allowances paid to Government staff attending training, workshops and study tours. | Adopt DSA rates in Anukret 10 of April 12, 2004, updated in respect of DSA rates for in-country travel by MEF Decision Letter No. 2000 dated April 23, 2007. For international travel, some DSA rates specified in Anukret 10 are position-based and/or higher than UN norms, and are not acceptable to IDA for application on IDA-financed projects. In such cases, IDA will apply a ceiling for reimbursement equivalent to its own rates in use at the time of travel. | MEF/IDA to discuss and agree standard DSA for international travel, after which MEF to advise MOH. | Rates to be agreed by June 2008. Until then, for international travel, MOH may use IDA rates. IDA to monitor through FM supervision missions. | SC: Applied UNDP Rates for international travel. | MEF/IDA to discuss and agree standard DSA for international travel, after which MEF to advise MOH. Standard DSA have been approved by Development Partners. Development Partner agree to align with Category E, Article 7 of SD 216. This rate corresponds to US$34. MOH has prepared Prakas on the rate for outreach activities |
| 2k | Planning of training, workshops and study tours. | Establish Annual Training and Workshop Plan as part of the Annual Operational Plan (but discretely identifiable) to be endorsed by pool partners together with AOP endorsement. MOH will review regularly and updated biannually. Plan should include: 1. Detailed costs estimates. 2. Eligibility rules for attending training, workshops and study tours. Attendees must: - be engaged in work relevant to the training; - be competent in the language used; - after return, report on and share their experiences for the benefit of the project. 3. Evidence that training, workshops, study tours and other similar activities: - are in line with project aims and objectives; - meet identified needs within the sub-component plans; - have budget in line with planned expenditure. Cost guidelines to be established for selected training/workshop activities: - venue rental with refreshments/meals; - sound and projection equipment hire; - stationery/hand-outs ; - project-specific training and workshop materials; - simultaneous translators; - photocopying, reproduction, translation. Define evidence to be submitted by attendees for reimbursement of expenses which may include: - proof of attendance for period claimed with signed statement by the workshop, training or study tour organizer or host; - proof of travel by air – ticket stubs, travel agent’s receipt, airline boarding passes; - receipted hotel bills (for proof of stay); - receipts for incidental traveling expenses; receipted invoices for venue rental, food and beverage, sound/projection equipment, hire of simultaneous translator, stationery and handouts, use of photocopying facilities. Reimburse against receipts except where covered by fixed allowances in MEF’s letter No. 2000. Evidence of payment to be kept for attendees’ per diem and allowances. | MOH, which should follow Working Group guidelines when issued (see below). Subject to IDA NOL. Working group comprising MEF, IAs of all projects and IDA. Working group to define evidence and include in directive. MOH to ensure compliance. MOH. MOH. | Submit first Plan to IDA by 3 months after effectiveness. Thereafter annually along with AOP, with biannual updates submitted together with IFRs. MEF to establish working group by August 2008. Issue directive to all IDA-funded projects by October 2008. Directive issued by January 2009. IDA to monitor SOEs with withdrawal applications. IDA to monitor SOEs with withdrawal applications. Pool partners to verify during supervision missions. IDA to monitor SOEs with withdrawal applications. Pool partners to verify during supervision missions | SC: MOH and Pooled fund partners agreed to have training activities included in AOPs and quarterly workplans as oppose to a separate annual training plan. Training plan 2011 was approved in May 2011. Training activites in 2013 approved in AOP 2013. Included in SOEs Included in SOEs | MEF to establish working group. Issue directive to all IDA-funded projects. As of June 2012, this has not been yet established (June 2012). Training plan together with AOP 2012 has been submitted in February 2012 after revision in accordance with JPIG’s comments. Correct version of 2012 AOPs will be submitted to the WB on June 28 for review and approval. . |
| 2l | Delayed or non-existent reconciliation of advances for operating costs and expenses | The Program will maintain an advances register, as well as vehicle log books and fuel registers. Advances of operating expenses to staff or field offices to be reconciled within two weeks of the end of each month. No further advances to be paid to staff or field offices until the previous advance to those staff or offices has been reconciled and cleared against documentary evidence. | MOH. | Pool partners to verify compliance during supervision missions MOH to monitor application, IDA and pool partners to verify during FM supervision missions. | SC: The Program maintains advance register, as well as vehicle log books and fuel registers. Advances of operating expenses to staff or field offices are reconciled within two weeks of the end of each month. No further advances are paid to staff or field offices until the previous advance to those staff or offices has been reconciled and cleared against documentary evidence. | Finance unit conduct regular follow up advance register and will report through quarterly review meeting. (June 2012) Continue to follow up with IUs to speed up on advance clearance. (Nov 12, 2013) Continue to follow up with IUs to speed up on advance clearance (Jan 22, 2015) |
| 2m | MOH to adopt the MBPI in accordance with Anukret 29 of April 2008, for health managers and key technical staff. | MEF, CAR and MOH agree that MOH will adopt RGC’s MBPI. The MBPI will be implemented strictly according to an MBPI Manual to be prepared for the Program and sector. | MOH to complete the Program-specific MBPI Manual for MEF, CAR and IDA approval. | Cost sharing basis to be specified in the Financing Agreement. Manual to be approved before first disbursement of MBPI funds. MOH to monitor application, IDA and pool partners to verify during FM supervision missions. | SC: MBPI was canceled. POC payment was started from May 2011... POC was cancel in June 2012. | MBPI was terminated through Anukret number 206. |
| 2n | SDG Funds not reaching the units efficiently | Direct disbursement from the pooled and counterpart accounts directly to the bank accounts of the recipient units | MOH/responsible for Pooled and counterpart funds accounts | DPs to monitor during supervisions. | PC: Contracts between MOH and nine PHDs were signed. 21 out of 30 SDGs contracts were signed between PHDs and ODs/PRHs. All 30 SDGs contracts have been signed (November 2010). SDG contracts for 2011 were signed in March 2011. Routine activities were allowed using fund balance from 2010 for Q1 2011. SDG contracts were signed in Q1-2013. SDGshave been disbursed to almost all SOAsup to Q4-2013 (Nov 12 2013) | Functioning of 30 SDGs by June 2010 (May 2011). SDG contracts for 2012 has been signed in March 2012 .(June 2012 CF will be monitored closely.SDG contracts for 2015 are being finalized (Jan 23, 2015) CF have been disbursed on time in 2014. SDG Pooled Fund delay in Quarter 3, 2014 due to delay of releasing Fund from Development Partners to POOLED ACCOUNT. SDG fund have been disbursed to all SOA in 2015. Allow using fund balance from Q4 2014- Q1 2015 |
| 3 | Element 3: Disclosure |  |  |  |  |  |
| 3a | Minimize conflict of interest among Program staff | Program staff to disclose private and public affiliations or personal interests before becoming involved in any Program-related transaction or contract award decision. | MOH Program Director to request and retain written disclosures. | Pool partners to monitor during supervision missions. To monitor through review mission. | Disclosure statement for inclusion in contracts had been developed in put in use. | Will include in quarterly procurement report |
| 3b | Enhance transparency through greater public disclosure of Program information | Agree on information to be disclosed on MEF and MOH websites biannually, with hard copies available for public inspection on request, at locations to be agreed. At a minimum, disclosed information should include: - Program name, objectives, original and revised amount, sources of funding, effectiveness date, original closing date, revised closing date, number of extensions, name and address of implementing agency, name of Program Director with contact information, name of IDA TTL and contact information in the MEF-WB division and in the WB Office in Cambodia. - Details of Program components, percentage completion, data on performance indicators. - Details of Health Equity Fund Grants and Health Service Delivery Grants as they affect recipients. - AOPs, and procurement plans excluding cost estimates, identifying contracts to be procured in the next 12 months, nature of each contract, location, method of procurement, means of advertisement, bidding period, location where bidding documents and RFPs can be inspected, expected date of availability, and cost of bidding documents. - Consultant long and short lists. Bidding documents and RFPs available for inspection. - Bid closing dates, names of bidders and their bid prices at opening. - List and detail of contracts awarded, names of losing bidders and, if their bid prices were lower than the winning bidder, the reason for their rejection. - Program biannual progress reports - Planned and actual disbursements by sub-component. - Annual financial statements and audit opinion. - Other specific reports prepared by the Program. - Complaint handling and remedies mechanism. - Code of ethical conduct signed by all staff. MOH will also raise public awareness of the Program through a workshop at Program launch to which the media will be invited, and newsletters to stakeholders and/or media insertions every six months, explaining the Program content, its benefits to the public and means of participation. | MOH and IDA to agree final list and locations for public inspection of hard copies. MOH to arrange disclosure on MoH website. MOH Program Director, who will advise pool partners in advance of public awareness activities. | Agree by three months after Effectiveness. Biannually. Pool partners to verify during supervision missions. Program launch workshop prior to start of Program activities and newsletters and/or media insertions at six monthly intervals thereafter. Pool partners to monitor. | Dissemination of program information during launching workshop. Procurement portal on MoHwebite has been created. Currently all procurement and contract award information is posted on MOH website. Also posted in UNDB as required. | Procurement Plan is uploaded on the MoH website. Currently all procurement and contract award information is posted on MOHwebsite. Also posted in UNDB as required. Contract award information (along with required details of competition and evaluation results) also made available to parties who request for the same. Due to no funding support the MOH Website is no longerfunctioning Aconnstruction information has been put up on sign boards at all construction sites. Approved AOP is uploaded on MoH website. Annual Progress Report is uploaded on MoH website. |
| 4 | Element 4: Civil Society Role |  |  |  |  |  |
| 4a | Provide for greater involvement by Civil Society Organizations (CSOs) to enhance transparency. | Identify appropriate CSOs to witness selected aspects of Program implementation. Invite representatives to attend selected events as observers, such as: - bid openings - contract signings - information and skill sharing sessions - Program progress meetings - meetings with the Technical Working Group – Health at central and provincial levels, as part of the partnership arrangements to popularize the Program and obtain feedback on public awareness - hand over ceremonies for Program facilities other events as identified and agreed by MOH and pool partners Summarize all major CSO involvement in Program biannual progress reports to pool partners and copied to MEF | MOH to select CSOs and obtain MEF concurrence. MOH/pool partners to agree events to be witnessed by CSOs. MOH | MEF to provide MOH with concurrence to CSO not later than one month after Effectiveness. Agree list of events one month after Effectiveness. Observation to begin immediately thereafter. Pool partners to monitor CSO involvement through review of quarterly progress reports and supervision missions. Pool partners to verify satisfactory level of involvement of CSOs during supervision missions. | SC: Cambodian Medical Association and MEDICAM have been officially nominated. C: Cambodian Medical Association and MEDICAM have been officially nominated. Cambodian Medical Association and MEDICAM reported to have been participated in bids opening (May 2010). Involvement of COS in procurement 2012 is included in Annual Performance Review Report 2012. | MEF approved CSOs. MoH involves appropriate CSO in the bidding process as required. Report on progress of CSOs involvement be put in HSSP2 Semi Annual and Annual Progress report in 2010 and for the rest of program time. Involvement of CSO i is included in Annual Progress Report |
| 5 | Element 5: Complaint Handling and Remedy Mechanism |  |  |  |  |  |
| 5a | Formal complaints handling and remedy mechanism covering all aspects of the Program. | Design and adopt a mechanism able to address complaints received on all Program components and sub-components and propose remedies. Complaints handling procedures regarding procurement to follow process as set out in the SOP/PM. | MOH with IDA NOL. MOH | Design and adopt mechanism by three months after Effectiveness. Pool partners to monitor adoption during supervision missions IDA to monitor during prior or post reviews Pool partners to monitor adoption during supervision missions IDA to monitor during prior or post reviews | SC: Complaint mechanism is in place and procedure recorded in the bidding and contract documents. Update | Continue complaint handling mechanism which is in place. |
| 6 | Element 6: Code of Ethical Conduct |  |  |  |  |  |
| 6a | Program staff must to adhere to the Government’s code of ethical conduct for civil servants. | MOH to disseminate widely the relevant sections on code of ethical conduct contained in the Common Statute for Civil Servants 1994. | MOH with a copy to pool partners. | Disseminate by one month after Effectiveness. Pool partners to verify its application during supervision missions. | PC: Dissemination to program staff has started and new MOH staff. SC: Code of ethical conduct attached to all signed contracts (May 2010). | MOH follows the required procedural steps for code of ethical conduct. MOH will continue to disseminate the code of ethical conduct to new staff. |
| 7 | Element 7: Sanctions |  |  |  |  |  |
| 7a | Need to reinforce the Code of Ethical Conduct with sanctions for fraudulent and corrupt activity by staff of implementing agencies, the Program and contractors, suppliers and consultants. | It has been agreed that the sanctions defined in the Civil Service Code of 1994 will be applied to all project staff. Sanctions against contractors, suppliers and consultants will be those defined in Section 3 of the SOP/PM. IDA to apply sanctions available in its general and project-specific legal agreements, including the WB Group’s Anti-Corruption Guidelines (ACG) and Sanctions Regime issued in October 2006 and as may be updated subsequently. | MOH to disseminate sanctions with Code of Ethical Conduct. IDA to provide MOH a copy of its ACG and Sanctions Regime. | Disseminate sanctions along with the Code of Ethical Conduct by three months after Effectiveness. IDA provided copy of ACG to MOH during appraisal. IDA may apply sanctions whenever evidence is found. | PC: Dissemination to program staff has started and new MOH staff. | . |
| 8 | Element 8: Program Specific Elements |  |  |  |  |  |
| 8a | Weak capacity to implement the Program at sub-national level. | A multi-department Health Service Delivery, Monitoring and Supportive Supervision Team satisfactory to the pool partners will be established in MOH to provide guidance to PHDs and ODs. | MOH with IDA NOL to composition of the Team on behalf of pool partners | Agree composition of Team by one month after Effectiveness. Team to be established and functioning by two months after Effectiveness. To conduct regular monitoring activities. | SC: Internal Contracting Monitoring Group has been established. Few workshops have been conducted by the group C: SDMG has been established on 19 March 2010 (May 2010) SDMG jointed monitoring vist with JPIG in April 2013. Field monitoring have been conducted by SDMG to SOA between August and September 2013. (Nov 12 2013) | New SDMG members have been appointed in June 2012 (June 2012) Schedule of monitoring and supervision visit of SDMG to be developed and discussed at the next SDMG meeting. Regular monitoring of SDMG to sub-national level. (Nov 12 2013) SDMG conducted monitoring to SOAs in order to monitoring the quarterly progress and endorsement of SDG payment of quarter 1, 2, 3, and 4 of 2014. |
| 8b | Ensure control of the allocation and use of performance linked Health Service Delivery Grants. | A Health Service Delivery Grant Operation Manual will be prepared defining the criteria and mechanisms for grant allocation, eligibility of proposed expenditure of grant funds, disbursement arrangements and methods for monitoring and performance evaluation. | MOH with IDA NOL to Manual on behalf of pool partners. | Manual to be approved for disbursement. See item 8d for monitoring during Program implementation. | C: SDG Manual has been approved before effectiveness. Updated SDG manual has been approved and disseminated (May 2013) | The manual has been translated and disseminated (May 2010). 30 November 2011. Revised SDG Manual in accordance with JPIG’s comments has been circulated to JPIG in June 2012. (June 2012) Translation of updated SDG manual expected to be done by end September 2013. SDG manual in Khmer version have been distributed to all SOAs, relevant PHDs and SDMG members. |
| 8c | Ensure control of the allocation and use of Health Equity Fund Grants. | A Health Equity Fund GrantsOperation Manual will be prepared defining the arrangements for identification of the poor, the mechanisms for allocating benefits, management, administration arrangements and disbursement arrangements, and reporting, monitoring, evaluation and verification arrangements. The Manual will be aligned with the National Health Equity Fund Implementation Guidelines. | MOH with IDA NOL to Manual on behalf of pool partners. | Manual to be approved for disbursement. See item 8d for monitoring during Program implementation. | C: Manual has been approved. | The manual has been translated and disseminatedin 2009 |
| 8d | Monitoring and physical verification of performance, service, meeting of targets and acceptable quality of all Program deliverables. | Employ an experienced firm to undertake an annual independent technical audit, under terms of reference and with expected positions in the team acceptable to the pooling partners to review and assess the scope, location and quality of all activities implemented under the Project, in reference to achievement of the Development Objectives and outputs. The Technical Audit Consultants will report to the pool partners and MOH after each intermittent audit. MOH and the pool partners will review the audit reports and jointly develop an action plan to implement the audit recommendations and follow up their implementation status. MOH will update pool partners on the status of audit recommendation through the quarterly IFRs. | Team composition and TOR to be agreed by pool partners and advised to MOH. MOH and pool partners. | Agree TOR by August 2008, and Consultants on board by June 2009. Not later than one month after receipt of each audit report. Monitoring of the implementation of audit recommendations on an ongoing basis by MOH and pool partners. | S: Drafted TOR for consultation. Negotiate contract with technical auditing firm. Technical audit has been integrated with financial audit for 2010 (November 2010). Signed contract for Technical and Financial Audit in November 2011. See point 2f. Combined technical and financial audit of Q2-2013 have been submitted on Oct 14, 2013. )Nov 12 2013) Combined quarterly technical and financial audit report of 2014 have been submitted to Development Partners on time. | MOH to communicate the draft TOR to pool partners by June 15, 2009. Experienced firm will be selected by December 31, 2009. TOR of combined technical and financial audit has been submiited to IPA (November 2010). Combined Technical and Financial Audit consultant started their services in November 2011.(June 2012) Continue good practice of submission combined quarterly technical and financial audit report to development partners on time. |

## Annex G. Status of Legal Covenants for WB Financing Agreement (Cr. 4470-KH)

| Agreement Reference | Language | Status as of January 2016 |
| --- | --- | --- |
| Schedule 2, Section I.A.1.(a) | Establish and maintain a Health Sector Steering Committee to provide overall policy direction and general oversight of the Program, including review and approval of AOPs | Complied with |
| Schedule 2, Section 1.A.1.(b) | Establish and maintain a Technical Working Group – Health, to serve as a consultation forum among the Recipient and Program Partners, and facilitate exchange of information and policy dialogue among the parties | Complied with |
| Schedule 2, Section I.B.1.(b) | Implement the Project in accordance with the Project Operational Manual, SDG Operational Manual, HEF Operational Manual and MBPI Manual | Complied with Community scorecard is being piloted in 2011. CSC guideline and manual has been endorsed in May 2012. Cancellation of MBPI in 2009. Priority Operating Cost (POC) of MoH/HSSP2 of 239 positions is being implemented. POC cancelled in June 2012. Revised SDG Operational Manual approved January 2013. Translation of revised SDG Manual expected to be completed and disseminated by Dec 2013. SDG manual in Khmer version have distributed to all SOAs, relevant PHDs, SDGM members in July 2014. |
| Schedule 2, Section I.B.2.(a) | Undertake a joint annual performance review to be held not later than March of every year, during which they will jointly review progress in sector performance in the light of the Program Performance Indicators, and identify priorities for the next planning cycle | Complied with |
| Schedule 2, Section I.B.2.(b) | Undertake a joint annual operational plan and appraisal not later than September of every year, during which AOPs for the forthcoming Fiscal Year are to be consolidated and endorsed for final approval, and each Program Partner’s proposed share in the cost of the AOP and the Pooled Account, along with the Recipient’s own counterpart contribution, shall be duly noted and recorded | Complied with for AOP 2009 and 2010. JAPA 2011 conducted in January 2011 due to problem with new AOP database system development. JAPA 2012 was conducted in November 2011 (as suggested by the MOH in aide memoire May 2011) JAPA 2013 was conducted in November 2012. JAPA for 2014 is pending on national budget approval. |
| Schedule 2, Section 1.B.3.(a) | Establish and maintain a single non-interest bearing foreign exchange account (“Pooled Account”) | Complied with |
| Schedule 2, Section I.B.4.(a) | Proceeds of the Credit shall be used exclusively to finance Eligible Expenditures and in accordance with the respective AOP | Complied with |
| Schedule 2, Section I.B.4.(b) | The expenditures shall be deemed to have been jointly financed by the Pooling Partners in accordance with each Pooling Partner’s previously agreed percentage share of funds in the Pooled Account | Complied with |
| Schedule 2, Section I.B.6.(a) | Maintain an advance account to be operated and maintained by MOH (“Counterpart Fund Account”), into which it shall deposit from time to time its counterpart contribution corresponding to its share of the cost of the AOP for each Fiscal Year | Complied with |
| Schedule 2, Section I.B.6.(b) | Not later than thirty days after the date of the first deposit of funds into the Pooled Account, deposit into the Counterpart Fund Account an initial advance corresponding to the Recipient’s share of the approved AOP for the first two quarters of the first Fiscal Year, and thereafter replenish the Counterpart Fund Account on a quarterly basis, taking into account the opening balance in the Counterpart Fund Account and the Recipient’s share of the cost of the AOP for the next following quarter | Complied with (some delay of counterpart financing for SDG and HEF in 2010 and 2011). Counterpart financing for SDG and HEF in 2012 not yet fully disbursed). Counterpart financing for SDG disbursed up to Q4-2013. Counterpart fund for HEF replenished on time. Counterpart financing fully disbursed in 2014 Some delay in releasing Fund from the Bank to HSSP2’s Pooled Account led to delay in payment for HEF, SDG in Quarter 3, 2014. Delay of signed Agreement between WB and Government of Cambodia cause the delay of releasing fund to SOAs and NGOs for Q3 Q4 2015 |
| Schedule 2, Section I.B.7 | Establish a Joint Program Management Group (“Joint Program Management Group”) which shall meet on a quarterly basis, or more often as needed, to supervise the allocation of funds required to support activities to be financed out of the resources of the Pooled Account, review the application of such funds, and make recommendations for the release of new funds, based on satisfactory financial reports, cash forecasts and agreed triggers | Complied with |
| Schedule 2, Section I.B.8 | Apply the proceeds of the Credit and pooled Account allocated to Grants to finance Subprojects for the benefit of Eligible Beneficiaries in accordance with the guidelines, procedures and criteria set forth in the SDG Operational Manual or HEF Operational Manual and additional terms and conditions in Part D of Section 2 of the Financing Agreement | Complied with |
| Schedule 2, Section I.B.9.(a) | Not later than June 30, 2011, undertake, in conjunction with the Association and other Program Partners, a midterm review | Complied with. The MTR was completed December 2011 |
| Schedule 2, Section I.B.10 | Recipient shall take necessary measures to avoid any interruption in service delivery or decline in service standards across Provinces, including those to which the existing process of contractual arrangements involving NGOs applies pending adoption of the SDG Operational Manual | Complied with though need to ensure timely disbursement to SOAs (timely submission of quarterly report for SDMG’s review and approval in accordance with SDG Manual). SDMG will conduct field visits at least twice a year. SDG and HEF advance for two quarters instead of one quarter. |
| Schedule 2, Section I.C | The Recipient shall ensure that the Project is carried out in accordance with the provisions of the “Guidelines on Preventing and Combating Fraud and Corruption in Projects Financed by IBRD Loans and IDA Credits and Grants”, dated October 15, 2006 (“Anti-Corruption Guidelines”). | Complied with A mechanism for reporting complaint has been established in SDG manual. |
| Schedule 2, Section I.D.3.(b) | SDGs shall be provided out of resources provided by the Recipient’s central-level authorities to PHDs, using a resource allocation formula that takes into account population and other factors, to support the scaling up of delivery of integrated packages of essential preventive and curative care at district and health center levels, and on the basis of performance agreements between the Recipient’s central-level authorities and the Provinces | Complied with SDG has been disbursed direct to SOA Bank account |
| Schedule 2, Section I.D.3.(c) | SDGs shall be linked to Service Delivery Agreements (“SDAs”) to be signed between PHDs and Operational Districts (“ODs”) for service delivery, setting out the service delivery standards and performance targets upon which disbursements under the SDGs are contingent | Complied with |
| Schedule 2, Section I.D.3.(d) | HEF Grants shall be provided to Eligible NGOs to consolidate and expand the coverage of health care benefits packages available to the poor, and to finance membership dues for the benefit of participants in community-based health insurance schemes who are identified as poor | Complied with MTR recommended that CBO shall be eligible for managing HEF. CBOs have been appointed (through) to manage HEF in Khan Meanchey, Angkor Cum OD, Pursat OD and SvayRieng OD. |
| Schedule 2, Section I.D.3.(d) | For purposes of every Grant, a Grant Agreement shall be signed into between the Recipient and Beneficiary, setting forth the respective obligations of the parties thereunder, including: (i) the amount of the Grant, along with details of the agreed disbursement schedule; (ii) procurement procedures consistent with Section III of Schedule 2 to this Agreement; (iii) provisions for audits of the Grant; (iv) the amount of any counterpart or matching contribution to be made by the Beneficiary from its own funds or from other sources; (v) details of the Environmental Management Plan, Land Acquisition and Resettlement Action Plan or Indigenous Peoples Plan, if any; and (vi) an undertaking on the part of the Beneficiary to execute the Subproject with due diligence and efficiency and, upon its completion, to have in place a maintenance program to ensure the continued achievement of the objectives of the Grant and any counterpart or matching contribution | Complied with |
| Schedule 2, Section I.E.1.(a) | Implement the Project in accordance with the Social and Environmental Safeguards Framework | Complied with but need to be closely follow-up and cross-reference with Aide memoire. TOR for IP consultation is being drafted and consultation will be conducted during Q3-2013. IP Consultation had been conducted. IPPF have been completed in Jun 2014. |
| Schedule 2, Section I.E.1.(b) | For Subprojects requiring adoption of an Environmental Management Plan, a Land Acquisition and Resettlement Action Plan or an Indigenous Peoples Plan (i) have such Plans developed, approved and adopted; and (ii) comply or ensure compliance by the Beneficiaries with the requirements of such Plans | No land acquisition is required under the HSSP2 construction plan. Land titles have been reviewed and acquired lands have been investigated. The review report is being submitted for Bank’s approval. Land title for construction of 109 HCs and 5 HPs have been completed and concurred by the Bank. Land Acquisition Policy Framework will be updated with assistant from the Bank team.Land Acquisition Policy Framework updated and distributed to all SOAs and relevant PHDs in July 2014 IP consultation will be conducted in Dec 2013 and IPP will be developed accordingly. IPPF developed and distributed to all SOAs, relevant PHDs in July 2014 |
| Schedule 2, Section I.E.2 | Regularly collect, compile and submit to the Association on a semi-annual basis reports on the status of compliance with the Social and Environmental Safeguards Framework, giving details of: (a) measures taken in furtherance of the Social and Environmental Safeguards Framework; (b) conditions, if any, which interfere or threaten to interfere with the smooth implementation of such Social and Environmental Safeguards Framework; and (c) remedial measures taken or required to be taken to address such conditions | Draft first semester 2009 report has been submitted. 2009 Annual Report was submitted in March 2010. 1st Semi-annual report 2010 was submitted in October 2010. Annual Report of 2010 was submitted in April 2011. Draft first semester 2011 was submitted in November 2011. Delay due to the change to web-based HIS which required rigorous cross-check data quality. The draft Annual Performance Report 2011 was submitted in May 2012. First draft of Annual Progress Report will be shared with JPIG partners by mid-May 2013. Semi-annual performance report of first semester 2013 to be shared JPIG by Nov 15. |
| Schedule 2, Section II.A.1 | The Recipient shall monitor and evaluate the progress of the Project and prepare Project Reports in accordance with the provisions of Section 4.08 of the General Conditions and on the basis of the Program Performance Indicators. Each Project Report shall cover the period of six months, and shall be furnished to the Association not later than forty-five days (45) after the end of the period covered by such report. | Complied with some delays. Since it is not possible to provide this within current timeframe, need to document agreement to allow 90 days. Draft semi-annual performance report of first semester 2014 shared with JPIG in December 8, 2014 Draft Annual Performance Monitoring Report 2014 will be shared with JPIG in March 2015. |
| Schedule 2, Section II.B.2 | Prepare and furnish to the Association not later than 45 days after the end of each calendar quarter, interim financial reports for the Project covering the quarter | Complied with. |
| Schedule 2, Section II.B.3 | Have the interim financial reports audited quarterly on a continuous basis, and its Financial Statements audited annually in accordance with the provisions of Section 4.09 (b) of the General Conditions. The interim audited financial reports for each quarter shall be furnished to the Association not later than 90 days after the end of the quarter.The audited Financial Statements for each Fiscal Year shall be furnished to the Association not later than six months after the end of the Fiscal Year. | Complied with after delay. Annual financial audit 2010 was submitted on time. Annual audit financial report 2011 will be delayed due to the delay on the appointment of combined technical and financial auditing firm. IFR Q1-2013 have been shared with Partners. Audit opinion report for 2011 submitted to the Bank on 14 Oct 2013. IFR Q2-2013 submitted on time. IFR Q1, 2, 3 of 2014 submitted on time |
| Schedule 2, Section II.B.4 (a) | Appoint, not later than three months after the Effective Date, an internal audit advisor to assist in strengthening the capacity of the internal audit department | Contract signed in March 11 2010, the selected consultant was on board on 18th August 2010. Training to IAD staff will continue until November 2011. Will request for contract extension. TA for capacity building to internal audit department have been completed |
| Schedule 2, Section II.B.4 (b) | Appoint, not later than six months after the Effective Date, an independent auditor to carry out annual technical and performance audits | Complied with after delay (technical audit has been integrated with financial audit since semester 2, 2010). Combined technical and financial audit reports of 2014 submitted on time |

Annex H.Health Equity Funds

Health facilities contracted with health equity fund schemes

| Province | No. | Operational District(s) | Cluster | Model | Source of Fuding | HEFI | Contract Type | HEFO | Total HEF Coverage |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | NH | CPA3 | CPA2 | CPA1 | Total Hospitals | #FDHs | # HCs | #HPs |
| Banteay Meanchey | 1 | Mongkol Borei | 16 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 1 | 0 | 1 | 2 | 0 | 21 | 2 |
|  | 2 | Poipet | 16 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 0 | 1 | 0 | 1 | 3 | 13 | 2 |
|  | 3 | Preah Net Preah | 16 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 0 | 0 | 1 | 1 | 1 | 14 | 5 |
|  | 4 | Thma Puok | 13 | HEF | HSSP2 | URC-CHS | OBC | CHC | 0 | 0 | 1 | 0 | 1 | 1 | 12 | 0 |
| Battambang | 5 | Battambang | 18 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 1 | 0 | 0 | 1 | 3 | 20 | 5 |
|  | 6 | Maung Russei | 18 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 0 | 1 | 0 | 1 | 0 | 13 | 1 |
|  | 7 | Sampov Luon | 18 | HEF | HSSP2 | URC-CHS | OBC |  | 0 | 0 | 1 | 0 | 1 | 1 | 9 | 0 |
|  | 8 | Sangkae | 18 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 0 | 0 | 0 | 0 | 2 | 13 | 0 |
|  | 9 | Thmar Koul | 18 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 0 | 0 | 1 | 1 | 1 | 17 | 0 |
| Kampong Cham | 10 | Batheay | 10 | HEF | HSSP2 | URC-CHS | TBC | AFH | 0 | 0 | 0 | 1 | 1 | 0 | 7 | 0 |
|  | 11 | Chamkar Leu | 11 | HEF | HSSP2 | URC-CHS | OBC | AFH | 0 | 0 | 0 | 1 | 1 | 0 | 12 | 0 |
|  | 12 | Choeung Prey | 10 | HEF | HSSP2 | URC-CHS | TBC | AFH | 0 | 0 | 0 | 1 | 1 | 0 | 7 | 0 |
|  | 13 | Kampong Cham - Kg. Siem | 10 | HEF | HSSP2 | URC-CHS | TBC | AFH | 0 | 1 | 0 | 0 | 1 | 1 | 20 | 0 |
|  | 14 | Prey Chhor - Kang Meas | 11 | HEF | HSSP2 | URC-CHS | OBC | AFH | 0 | 0 | 0 | 1 | 1 | 0 | 15 | 0 |
|  | 15 | Srey Santhor - Kang Meas | 26 | HEF | HSSP2 | URC-CHS | OBC | CHC | 0 | 0 | 1 | 0 | 1 | 0 | 13 | 0 |
|  | 16 | Stueng Trang | 11 | HEF | HSSP2 | URC-CHS | OBC | AFH | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |
| Kampong Chhnang | 17 | Boribo | 9 | HEF | HSSP2 | URC-SHP | TBC | RHAC | 0 | 0 | 0 | 1 | 1 | 0 | 10 | 0 |
|  | 18 | Kampong Chhnang | 9 | HEF | HSSP2 | URC-SHP | TBC | RHAC | 0 | 1 | 0 | 0 | 1 | 3 | 14 | 0 |
|  | 19 | Kampong Tralach | 9 | HEF | HSSP2 | URC-SHP | TBC | RHAC | 0 | 0 | 0 | 1 | 1 | 0 | 12 | 0 |
| Kampong Speu | 20 | Kampong Speu | 21 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 0 | 0 | 0 | 1 | 17 | 0 |
|  | 21 | Kong Pisey | 21 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 1 | 0 | 1 | 1 | 20 | 0 |
|  | 22 | Ou Dongk | 21 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 1 | 0 | 1 | 1 | 8 | 0 |
|  | 23 | Phnom Srouch | 21 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |
| Kampong Thom | 24 | Baray and Santuk | 8 | Linkage HEF& CBHI/Voucher | HSSP2 | URC-CHS | TBC | AFH | 0 | 0 | 1 | 0 | 1 | 1 | 20 | 0 |
|  | 25 | Kampong Thom | 8 | Linkage HEF& CBHI/Voucher | HSSP2 | URC-CHS | TBC | AFH | 0 | 1 | 0 | 0 | 1 | 4 | 17 | 0 |
|  | 26 | Stong | 8 | Linkage HEF& CBHI/Voucher | HSSP2 | URC-CHS | TBC | AFH | 0 | 0 | 1 | 0 | 1 | 0 | 10 | 0 |
| Kampot | 27 | Angkor Chey | 14 | HEF/Voucher | HSSP2 | URC-SHP | TBC | BFH | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |
|  | 28 | Chhouk | 14 | HEF/Voucher | HSSP2 | URC-SHP | TBC | BFH | 0 | 0 | 0 | 0 | 0 | 2 | 17 | 0 |
|  | 29 | Kampong Trach | 14 | HEF/Voucher | HSSP2 | URC-SHP | TBC | BFH | 0 | 0 | 0 | 0 | 0 | 1 | 13 | 0 |
|  | 30 | Kampot | 14 | HEF/Voucher | HSSP2 | URC-SHP | TBC | BFH | 0 | 1 | 0 | 0 | 1 | 0 | 14 | 0 |
| Kandal | 31 | Ang Snuol | 24 | HEF | HSSP2 | URC-SHP | OBC | PFD | 0 | 0 | 0 | 1 | 1 | 0 | 8 | 0 |
|  | 32 | Kean Svay | 23 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 0 | 1 | 1 | 1 | 6 | 0 |
|  | 33 | Koh Thom | 23 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 1 | 0 | 1 | 1 | 11 | 0 |
|  | 34 | Ksach Kandal | 24 | HEF | HSSP2 | URC-SHP | OBC | PFD | 0 | 0 | 0 | 0 | 0 | 1 | 14 | 0 |
|  | 35 | Leuk Deak | 23 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 0 | 1 | 1 | 0 | 6 | 0 |
|  | 36 | Lvea Em | 24 | HEF | HSSP2 | URC-SHP | OBC | PFD | 0 | 0 | 0 | 1 | 1 | 2 | 9 | 0 |
|  | 37 | Muk Kam Poul | 24 | HEF | HSSP2 | URC-SHP | OBC | PFD | 0 | 0 | 1 | 0 | 1 | 2 | 4 | 0 |
|  | 38 | Ponhea Leu | 24 | HEF | HSSP2 | URC-SHP | OBC | PFD | 0 | 0 | 0 | 1 | 1 | 1 | 8 | 0 |
|  | 39 | Saang | 23 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 0 | 1 | 1 | 2 | 11 | 0 |
|  | 40 | Takhmao | 23 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 0 |
| Kep | 41 | Kep | 14 | HEF/Voucher | HSSP2 | URC-SHP | TBC | BFH | 0 | 0 | 0 | 1 | 1 | 0 | 4 | 1 |
| Koh Kong | 42 | Smach Mean Chey | 2 | HEF | HSSP2 | URC-CHS | TBC | RHAC | 0 | 0 | 1 | 0 | 1 | 3 | 4 | 3 |
|  | 43 | Srae Ambel | 2 | HEF | HSSP2 | URC-CHS | TBC | RHAC | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 0 |
| Kratie | 44 | Chhlong | 7 | HEF | HSSP2 | URC-SHP | TBC | AFH | 0 | 0 | 1 | 0 | 1 | 1 | 8 | 3 |
|  | 45 | Kratie | 7 | HEF | HSSP2 | URC-SHP | TBC | AFH | 0 | 1 | 0 | 1 | 2 | 1 | 19 | 9 |
| Mondul Kiri | 46 | Sen Monorom | 5 | HEF | HSSP2 | URC-CHS | TBC | AFH | 0 | 0 | 1 | 0 | 1 | 0 | 11 | 16 |
| Oddar Meanchey | 47 | Samraong | 13 | HEF | HSSP2 | URC-SHP | OBC | CHC | 0 | 0 | 1 | 1 | 2 | 0 | 32 | 0 |
| Pailin | 48 | Pailin | 18 | HEF | HSSP2 | URC-SHP | OBC | PFD | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |
| Phnom Penh | 49 | Bassak |  |  |  |  |  |  | 0 | 0 | 0 | 1 | 1 | 0 | 7 | 0 |
|  | 50 | Chaktomouk | 17 | HEF | HSSP2 | URC-SHP | OBC | KCHP | 1 | 1 | 0 | 0 | 2 | 2 | 3 | 0 |
|  | 51 | Dang Koa | 17 | HEF | HSSP2 | URC-SHP | OBC | KCHP | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |
|  | 52 | Mekong | 17 | HEF | HSSP2 | URC-SHP | OBC | KCHP | 0 | 0 | 0 | 2 | 2 | 0 | 7 | 0 |
|  | 53 | Por Senchey | 17 | HEF | HSSP2 | URC-SHP | OBC | KCHP | 0 | 0 | 0 | 1 | 1 | 0 | 5 | 0 |
|  | 54 | Sen Sok | 17 | HEF | HSSP2 | URC-SHP | OBC | KCHP | 0 | 0 | 0 | 1 | 1 | 0 | 4 | 0 |
| Preah Vihear | 55 | Tbeng Meanchey | 6 | HEF | HSSP2 | URC-CHS | TBC | AFH | 0 | 1 | 0 | 0 | 1 | 9 | 14 | 0 |
| Prey Veng | 56 | Baphnom | 22 | HEF/Voucher | HSSP2 | URC-SHP | OBC | CHC | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 0 |
|  | 57 | Kamchay Mear | 22 | HEF/Voucher | HSSP2 | URC-SHP | OBC | CHC | 0 | 0 | 0 | 1 | 1 | 1 | 11 | 0 |
|  | 58 | Kampong Trabek | 22 | HEF/Voucher | HSSP2 | URC-SHP | OBC | CHC | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |
|  | 59 | Mesang | 22 | HEF/Voucher | HSSP2 | URC-SHP | OBC | CHC | 0 | 0 | 0 | 1 | 1 | 0 | 9 | 0 |
|  | 60 | Neak Loeung | 22 | HEF/Voucher | HSSP2 | URC-SHP | OBC | CHC | 0 | 0 | 1 | 0 | 1 | 2 | 9 | 0 |
|  | 61 | Pearaing | 22 | HEF/Voucher | HSSP2 | URC-SHP | TBC | CHC | 0 | 0 | 1 | 0 | 1 | 0 | 9 | 0 |
|  | 62 | Porieng | 3 | HEF/Voucher | HSSP2 | URC-SHP | OBC | AFH | 0 | 1 | 0 | 0 | 1 | 0 | 5 | 0 |
|  | 63 | Preah Sdach | 3 | HEF/Voucher | HSSP2 | URC-SHP | TBC | AFH | 0 | 0 | 0 | 1 | 1 | 0 | 9 | 0 |
|  | 64 | Sithor Kandal | 3 | HEF/Voucher | HSSP2 | URC-SHP | TBC | AFH | 0 | 0 | 0 | 1 | 1 | 0 | 6 | 1 |
|  | 65 | Svay Antor | 22 | HEF/Voucher | HSSP2 | URC-SHP | OBC | CHC | 0 | 0 | 0 | 1 | 1 | 1 | 13 | 0 |
| Pursat | 66 | Bakan |  |  |  |  |  |  | 0 | 0 | 0 | 1 | 1 | 0 | 11 | 0 |
|  | 67 | Sampov Meas |  |  |  |  |  |  | 0 | 1 | 0 | 2 | 3 | 1 | 27 | 3 |
| Ratanakiri | 68 | Banlong | 5 | HEF | HSSP2 | URC-CHS | TBC | AFH | 0 | 0 | 1 | 1 | 2 | 7 | 7 | 16 |
| Siemreap | 69 | Ankor Chhum | 29 | Linkage HEF& CBHI | HSSP2 | URC-CHS | OBC | STSA | 0 | 0 | 0 | 2 | 2 | 0 | 21 | 0 |
|  | 70 | Kralanh | 13 | Linkage HEF& CBHI | HSSP2 | URC-CHS | OBC | CHC | 0 | 0 | 1 | 0 | 1 | 1 | 13 | 0 |
|  | 71 | Siem Reap | 12 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 1 | 0 | 0 | 1 | 1 | 27 | 0 |
|  | 72 | Sot Nikum | 12 | HEF | HSSP2 | URC-CHS | OBC | PFD | 0 | 0 | 1 | 0 | 1 | 1 | 24 | 0 |
| Sihanoukville | 73 | Preah Sihanouk | 19 | HEF | HSSP2 | URC-SHP | OBC | BFH | 0 | 1 | 0 | 0 | 1 | 0 | 13 | 1 |
| Stung Treng | 74 | Steung Treng | 20 | HEF | HSSP2 | URC-SHP | OBC | CHO | 0 | 1 | 0 | 0 | 1 | 2 | 10 | 0 |
| Svay Rieng | 75 | Chi Phu | 27 | HEF/Voucher | HSSP2 | URC-SHP | OBC | SRHFO | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |
|  | 76 | Romeas Hek | 27 | HEF/Voucher | HSSP2 | URC-SHP | OBC | SRHFO | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |
|  | 77 | Svay Rieng | 27 | HEF/Voucher | HSSP2 | URC-SHP | OBC | SRHFO | 0 | 1 | 0 | 0 | 1 | 0 | 13 | 0 |
|  | 78 | Svay Teap | 27 | HEF/Voucher | HSSP2 | URC-SHP | OBC | SRHFO | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |
| Takeo | 79 | Ang Rokar | 1 | Linkage HEF& CBHI | HSSP2 | URC-CHS | TBC | BFH | 0 | 0 | 0 | 1 | 1 | 0 | 11 | 1 |
|  | 80 | Bati | 15 | Linkage HEF& CBHI | HSSP2 | URC-SHP | TBC | BFH | 0 | 0 | 0 | 1 | 1 | 1 | 13 | 0 |
|  | 81 | Daun Keo | 25 | Linkage HEF& CBHI | HSSP2 | URC-SHP | TBC | BFH | 0 | 1 | 0 | 0 | 1 | 1 | 14 | 0 |
|  | 82 | Kirivong | 1 | Linkage HEF& CBHI | HSSP2 | URC-SHP | TBC | BFH | 0 | 0 | 1 | 0 | 1 | 0 | 13 | 0 |
|  | 83 | Koh Andet |  |  |  |  |  |  | 0 | 0 | 0 | 1 | 1 | 0 | 11 | 0 |
|  | 84 | Prey Kabass | 15 | Linkage HEF& CBHI | HSSP2 | URC-SHP | TBC | BFH | 0 | 0 | 0 | 1 | 1 | 1 | 13 | 0 |
| Tbong Khmum | 85 | Kroch Chhmar | 26 | HEF | HSSP2 | URC-CHS | OBC | CHC | 0 | 0 | 0 | 1 | 1 | 0 | 9 | 0 |
|  | 86 | Memut | 4 | HEF | HSSP2 | URC-CHS | TBC | RHAC | 0 | 0 | 1 | 0 | 1 | 0 | 11 | 0 |
|  | 87 | O Reang Ov | 26 | HEF | HSSP2 | URC-CHS | OBC | CHC | 0 | 0 | 0 | 1 | 1 | 0 | 8 | 0 |
|  | 88 | Ponhea Krek - Dambae | 4 | HEF | HSSP2 | URC-CHS | TBC | RHAC | 0 | 0 | 1 | 0 | 1 | 0 | 17 | 0 |
|  | 89 | Tbong Khmum | 4 | HEF | HSSP2 | URC-CHS | TBC | RHAC | 0 | 0 | 1 | 0 | 1 | 0 | 16 | 0 |
|  | Total |  |  |  |  |  |  |  | 1 | 16 | 24 | 41 | 82 | 76 | 1046 | 69 |

Unless an alternative target is given in this column, all mitigation measures will commence when Program activities begin and continue throughout the Program.