98

‘

PROJECT COMPLETION REPORT

Volume 2: Annexes

PROJECT COMPLETION REPORT

Volume 2: Annexes

THE KNOWLEDGE SECTOR INITIATIVE

THE KNOWLEDGE SECTOR INITIATIVE

April 2022

April 2022

Q q

Q q

Project Completion report

Volume 2: Annexes

Project Completion report

Volume 2: Annexes

THE KNOWLEDGE SECTOR INITIATIVE (KSI)

THE KNOWLEDGE SECTOR INITIATIVE (KSI)

April 2022

April 2022

Table of contents

Annexes	1

A.	Financial expenditure analysis	2

B.	KSI Phase 2 staffing (2017-2022)	6

C.	List of KSI-supported knowledge products (2017-2022)	7

D.	List of knowledge exchange activities in KSI Phase 2	32

E.	List of PR Value from media engagement activities	42

F.	Infographics of high-level webinars	43

G.	List of policy changes influenced by PRIs (2018-2021)	45

H.	List of KSI Phase 2 evaluations, with summaries of findings	47

# Annexes

  - Financial expenditure analysis

  - KSI Phase 2 staffing (2017–2022)

  - List of KSI-supported knowledge products (2017–2022)

  - List of knowledge exchange activities in KSI Phase 2

  - List of PR Value from media engagement activities

  - Infographics of high-level webinars

  - List of policy changes influenced by PRIs (2018–2021)

  - List of KSI Phase 2 evaluations, with summaries of findings

## A.	Financial expenditure analysis

Head contract line items budget

During the life of the program in Phase 2, several budget changes took place following a reorientation of the Australian aid program as well as to address the impact of COVID-19. The Total Program Value of KSI reached 97.1% (AUD43,695,105) from the original allocation of AUD45,000,000.

Table A.1.	Summary of program original and final approved budget, by item categories

| Contractual line items | Original budget | Final approved budget |
| --- | --- | --- |
| Reimbursable costs |  |  |
| Labor cost | 15,006,463 | 12,621,731 |
| Operational costs * | 19,128,743 | 15,704,194 |
| Program costs | 10,864,794 | 15,369,180 |
| TOTAL | 45,000,000 | 43,695,105 |

* Including Management Fee

Annual and accumulative spending of approved budget

The approved 5-Year budget allocation for the KSI project Phase 2 implementation Financial Year (FY) 2017–2022 is AUD43,695,105. The table below shows the annual budget and the percentage of absorption for each project fiscal year (July to June).

Table A.2.	Allocated budget and disbursed amounts, by fiscal year

| Year | Allocated budget | Disbursed amount | Ratio |
| --- | --- | --- | --- |
| Year 1 (FY2017–18) | 8,587,508 | 8,373,288 | 97.51% |
| Year 2 (FY2018–19) | 9,411,576 | 9,409,604 | 99.98% |
| Year 3 (FY2019–20) | 9,156,898 | 9,115,750 | 99.55% |
| Year 4 (FY2020–21) | 8,108,623 | 8,089,960 | 99.77% |
| Year 5 (FY2021–22)* | 8,430,500 | 8,430,500 | 100.00% |
| TOTAL | 43,695,105 | 43,419,102 | 99.37% |

* including forecast Jan–Jun 2022

Over the total period, KSI was able to disburse 99.37% (total AUD43,419,102) of the project budget.

Table A.3.	Program spending performance and burn rate, by fiscal year

| Burn Rate –Spending Performance at the life of Program, status Dec 2021 – AUD | Budget | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 * |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | FY2017–18 | FY2018–19 | FY2019–20 | FY2020–21 | FY2021–22 |
|  | 43,695,105 | 8,373,288 | 17,782,892 | 26,898,642 | 34,988,602 | 43,419,102 |
|  |  | 19% | 41% | 62% | 80% | 99% |

* including forecast Jan–Jun 2022

Table A.4.	Summary of annual breakdown of spending based on head contract line items

| Contractual line items | Actual spending Year 1 | Actual spending Year 2 | Actual spending Year 3 | Actual spending Year 4 | Actual and forecasted spending Year 5 | TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
| Reimbursable costs |  |  |  |  |  |  |
| Labor cost | 2,085,609 | 2,548,531 | 2,514,772 | 2,133,671 | 2,211,048 | 11,493,630 |
| Operational costs * | 3,952,851 | 3,046,175 | 2,623,733 | 2,375,126 | 3,927,233 | 15,925,118 |
| Program costs | 2,334,827 | 3,814,899 | 3,977,247 | 3,581,163 | 2,292,219 | 16,000,355 |
| TOTAL | 8,373,287 | 9,409,605 | 9,115,752 | 8,089,960 | 8,430,500 | 43,419,104 |

* Including Management Fee

Total program spending

KSI Phase 2 commenced 1 July 2017 with most of program spending for the first year focused on laying the groundwork, including diagnostics for more detailed initiative implementation. A total program cost of AUD16,000,355 was spent throughout the 5 years implementation. The allocation for the final year focused on closing out of initiatives, communicating results as well as supporting efforts on sustainable outcomes. Table A.5. below presents the annual spending for program cost per end-of-program outcome (EOPO). The costs for labor, STA/consultant, operation costs and management fee components have been allocated proportional to the share of each EOPO’s expenditures.

Table A.5.	 Program annual spending based on EOPO

| By EOPO | Actual spending Year 1 | Actual spending Year 2 | Actual spending Year 3 | Actual spending Year 4 | Actual and forecasted spending Year 5 | TOTAL | Ratio spending from Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| EOPO 1 | 406,079 | 1,103,797 | 884,526 | 681,265 | 680,154 | 3,755,820 | 8.65% |
| EOPO 2 | 17,044 | 304,514 | 202,320 | 47,123 | 0 | 571,001 | 1.32% |
| EOPO 3 | 882,117 | 623,666 | 1,097,603 | 336,276 | 233,545 | 3,173,207 | 7.31% |
| EOPO 4 | 17,044 | 591,509 | 354,363 | 44,334 | 336,158 | 1,343,408 | 3.09% |
| EOPO 5 | 6,074,424 | 5,524,512 | 4,230,141 | 5,553,582 | 4,302,145 | 25,684,804 | 59.16% |
| Program management | 976,578 | 1,261,607 | 2,346,799 | 1,427,381 | 2,878,498 | 8,890,863 | 20.48% |
| Total Program | 8,373,287 | 9,409,605 | 9,115,752 | 8,089,960 | 8,430,500 | 43,419,104 |  |

Note: The Program Cost by EOPO includes Labor, STA/consultant costs, operations costs and management fee. These costs have been allocated proportional to the share of each EOPO’s expenditures for that year.

Initiative-level spending

KSI initiatives to support its different EOPOs were implemented with different timeframes, based on the maturity of the concept, the momentum, the availability of funds and relevance to strategic priorities. These considerations were also used to determine the timeframe of the initiatives, and also varied from 1 year to a full 5 years’ implementation. Starting from July 2017 (the commencement of KSI Phase 2) the financial management system was restructured to account for expenditures of different initiatives as identified in the Annual Workplan. The largest portion of program expenditure has always been grants to Policy Research Institutes, reported at 53.3%. While Program Management Support is calculated at 10.8%, it consists of various expenditure categories such as 7% allocation for MERLA related and 3.8% Program Communication to promote KSI overall (not specifically on public discourse/advocacy work through engaging media), as well as responses to emerging priorities that may not directly fit into a particular initiative.

Support to initiatives that consists of technical assistance and program implementation/operational support, including staff time are not part of the calculation for the initiative-level spending as these were accounted separately under staffing cost and short-term technical assistance (both national and international). The amount of KSI investment to different initiatives is captured in the table below.

Table A.6. 	Initiatives level annual spending

| By activity category | Actual spending Year 1 | Actual spending Year 2 | Actual spending Year 3 | Actual spending Year 4 | Actual and forecasted spending Year 5 | TOTAL | Ratio |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dana Abadi | 220,806 | 93,705 | 263,015 | 117,537 | 0 | 695,063 | 4.34% |
| Policy Research Government | 221,229 | 384,361 | 61,361 | 19,910 | 11,934 | 698,795 | 4.37% |
| Knowledge Ecosystem | 0 | 0 | 0 | 76,531 | 85,840 | 162,371 | 1.01% |
| Procurement Regulation | 0 | 17,912 | 30,543 | 73,386 | 92,062 | 213,903 | 1.34% |
| Sisnas Iptek | 103,043 | 218,131 | 56,436 | 16,240 | 2,068 | 395,919 | 2.47% |
| University Lecturers: Incentives for Quality Research | 0 | 21,578 | 0 | 0 | 0 | 21,578 | 0.13% |
| Policy Analyst | 20,413 | 168,781 | 66,421 | 31,332 | 0 | 286,948 | 1.79% |
| Private Sector Engagement | 5,436 | 51,306 | 0 | 0 | 0 | 56,742 | 0.35% |
| AIPI – DIPI | 298,949 | 262,795 | 94,285 | 0 | 0 | 656,029 | 4.10% |
| IDF | 0 | 51,582 | 270,727 | 40,548 | 29,019 | 391,875 | 2.45% |
| Knowledge Center (incl. KRISNA) | 0 | 267,660 | 149,975 | 19,625 | 99,290 | 536,550 | 3.35% |
| PRI grants | 1,168,877 | 1,702,875 | 1,892,688 | 2,593,804 | 1,171,724 | 8,529,968 | 53.31% |
| GESI | 0 | 18,303 | 207,874 | 75,086 | 48,558 | 349,821 | 2.19% |
| Sub-national | 0 | 29,135 | 62,206 | 70,405 | 37,636 | 199,382 | 1.25% |
| Public discourse | 0 | 6,018 | 67,367 | 129,151 | 106,064 | 308,600 | 1.93% |
| Media engagement | 0 | 256,223 | 393,487 | 84,775 | 20,540 | 755,024 | 4.72% |
| Program Management Support | 296,075 | 264,534 | 360,863 | 232,833 | 587,483 | 1,741,788 | 10.89% |
| TOTAL | 2,334,827 | 3,814,899 | 3,977,247 | 3,581,163 | 2,292,219 | 16,000,355 | 100% |

Note: Amount of Program Cost exclude STA/ consultant costs

Table A.7.	Summary of value of PRI grants in Phase 2

|  | Transition phase grants | Strategic Partnership Grant (K2P component) | Strategic Partnership Grant (Investment component) | Resource partner grants | TOTAL |
| --- | --- | --- | --- | --- | --- |
| TOTAL (IDR), 16 PRIs | 28,794,274,659 | 55,304,384,825 | 5,723,871,594 | 4,629,624,418 | 94,452,155,496 |
| TOTAL (AUD), 16 PRIs | 2,742,312 | 5,267,084 | 545,131 | 440,917 | 8,995,443 |

Table A.8.	Summary of value of PRI Grants in Phase 1 and Phase 2

|  | Phase 1 | Phase 2 | TOTAL |
| --- | --- | --- | --- |
| TOTAL (IDR), 16 PRIs | 84,379,612,891 | 94,452,155,496 | 178,831,768,387 |
| TOTAL (AUD), 16 PRIs | 8,036,154 | 8,995,443 | 17,031,597 |

## B.	KSI Phase 2 staffing (2017-2022)

This section outlines the dynamics of the KSI staffing structure created for Phase 2. As requested by DFAT, during the initial transition period, KSI made significant changes to the staffing configuration to align with the objectives and enhanced program approach and considering the lessons from Phase 1 to increase flexibility, strengthen the quality of outputs, and work smarter. The new program structure recognised that applying a problem-based, politically smart approach requires different sets of skills and knowledge than more traditional ‘project’ approaches. The team required a balance of strong interpersonal and leadership skills, including facilitation, influencing and negotiations skills, strategic thinking and strong communications. The new team for KSI Phase 2 was organised into 4 main units, Monitoring and Evaluation Performance, Policy Development and Innovation, Strategic Partnership Management, Knowledge Exchange and Learning, supported by the operations team.

The program’s organisational chart, outlining program and operations personnel, is provided below.

KSI Organisation Chart status December 2021

KSI implementation is managed by a Senior Leadership Team (SLT) which is supported by program and operations team members. The SLT consists of a team leader, a deputy team leader, a performance, monitoring and evaluation lead, unit leads (strategic partnership management, policy and innovation development, and knowledge exchange and learning), an operations manager, finance manager and the RTI-designated program coordinator. In the early mobilisation stage for KSI Phase 2, KSI recruited 24 staff consisting of 13 male and 11 female staff to fill in the key positions needed. The number of staff reached its maximum 45 staff in Year 3 implementation signifying the peak of program mobilisation. Throughout the implementation, follow-up recruitments in relation to new positions or replacement positions were made and the original gender composition for the staff fluctuated. This led to the final composition of 8 male and 14 female staff at the end of the program. KSI considered GEDSI as part of recruitment, staff management, and decision making within the KSI program.

## C.	List of KSI-supported knowledge products (2017-2022)

This annex provides the list of KSI-supported knowledge products over the period 2014-2022.

Table C.1 provides a summary of the 1,072 knowledge products by type, produced since KSI Phase 1. The most common type of knowledge product (53.5%) is an article, followed by publication (26.5%). The 5 other types of knowledge products have less than 10% each.

Table C.1 	KSI-supported knowledge products, 2014-2022 (PHASE 1 & 2)

| Type of knowledge product | Number | Percentage |
| --- | --- | --- |
| Article | 573 | 53,5% |
| Publication | 284 | 26,5% |
| Story of Change, article | 50 | 4,7% |
| Videos | 95 | 8,9% |
| Infographics | 40 | 3,7% |
| Podcasts | 27 | 2,5% |
| Website | 3 | 0,4% |
| Total | 1,072 |  |

Table C.2 provides a summary of the 734 knowledge products by type, produced during KSI Phase 2.

Table C.2 	KSI-supported knowledge products, 2017-2022 (PHASE 2)

| Type of knowledge product | Number | Percentage |
| --- | --- | --- |
| Article | 358 | 49% |
| Publication | 230 | 31,5% |
| Story of Change, article | 10 | 1,4% |
| Videos | 77 | 10,5% |
| Infographics | 29 | 4% |
| Podcasts | 27 | 3,7% |
| Website | 3 | 0,4% |
| Total | 734 |  |

| No. | Title | Type of Information |
| --- | --- | --- |
| 1 | Performance Indicators of the Strategic Plan of the Ministry of Research and Technology/BRIN 2020-2024 (Indonesian Version) | Publication |
| 2 | Policy Review and Indonesian Research Data Management System (Indonesian Version) | Publication |
| 3 | Making Indonesia's Research and Development Better: Stakeholder Ideas and International Best Practices | Publication |
| 4 | Supporting the Improvement of Indonesia's Research and Innovation Ecosystem: International Lessons Learned and Stakeholders’ Input (Indonesian Version) | Publication |
| 5 | Guidelines for Optimizing the Role of Policy Analyst Functional Positions (Indonesian Version) | Publication |
| 6 | Partnerships between Government and Community Organizations in the Procurement of Government Goods and Services Using Type III Swakelola (Indonesian Version) | Publication |
| 7 | Knowledge-to-Policy Development Pilot Program in South Sulawesi | Publication |
| 8 | Bureaucratic Reform in Indonesia: Policy Analyst Experiences | Publication |
| 9 | Building a Sustainable and Independent Research Funding Implementation in Indonesia (Indonesian Version) | Publication |
| 10 | Promoting Evidence-Based Policy Making: Presidential Staff Office Experience and Development Priorities 2015-2019 (Indonesian Version) | Publication |
| 11 | Operationalization of Research and Development Funding Principles in the Management of Research Endowments (Indonesian Version) | Publication |
| 12 | Diagnostic Studies: Transformation of Research Governance in Higher Education | Publication |
| 13 | Knowledge Systems: Evidence to Policy Concepts in Practice | Publication |
| 14 | Building a Sustainable and Independent Research Funding Implementation in Indonesia: A Policy Brief (Indonesian Version) | Publication |
| 15 | KRISNA Sustainability Policy Paper as a Policy Instrument for Strengthening Bureaucratic Reform (Indonesian Version) | Publication |
| 16 | Story of Change: Indonesian Academy of Sciences (Indonesian Version) | Publication |
| 17 | Type III Swakelola | Publication |
| 18 | Research Endowment Policy Review: An Overview of Funding & Institutional Governance (Indonesian Version) | Publication |
| 19 | Potential Funding for Policy-Oriented Research from Private Sector (Indonesian Version) | Publication |
| 20 | Human Resources and Gender in Indonesian Higher Education (Indonesian Version) | Publication |
| 21 | Guidelines for Inclusive Events and Communications | Publication |
| 22 | Inclusive Events and Communication Guidelines | Publication |
| 23 | The Importance of Local Knowledge: Power, Context and Policy Making in Indonesia (Indonesian Version) | Publication |
| 24 | Update on Constraints in the Enabling Environment to the Provision of Knowledge in Executive and Legislative Government | Publication |
| 25 | Update on Constraints in the Enabling Environment to the Provision of Knowledge in Executive and Legislative Government | Publication |
| 26 | Critical Study on Development Planning and Budgeting in Indonesia | Publication |
| 27 | Policy and Causality: A Learning Approach | Publication |
| 28 | Policy, Change and Paradox in Indonesia | Publication |
| 29 | A Critical Review of Development Planning and Budgeting in Indonesia (Indonesian Version) | Publication |
| 30 | Understanding Policy Making in Indonesia: in Search of a Policy Cycle | Publication |
| 31 | White Book: Science, Technology and Higher Education Towards Indonesia 2045 (Indonesian Version) | Publication |
| 32 | Addressing Barriers to University Research: A Case Study at the Faculty of Medicine, University of Gadjah Mada and the Center for Health Policy and Management | Publication |
| 33 | GDN Reforms Research in Indonesia (Indonesian Version) | Publication |
| 34 | Diagnostic Study of Research Barriers at UIN Syarief Hidayatullah (Indonesian Version) | Publication |
| 35 | Diagnostic Study of Research Supporting Philanthropic Institutions Mapping (Indonesian Version) | Publication |
| 36 | Mapping of Research Supporting Philanthropic Institutions | Publication |
| 37 | Policy Journal Diagnostic Study | Publication |
| 38 | Strengthening the Use of Knowledge for Policy in Indonesia: A Collection of Selected Change Stories from Knowledge Sector Initiative (KSI) Phase I Program (Indonesian Version) | Publication |
| 39 | How to Evaluate Mental Revolution? | Publication |
| 40 | Can Policy Influence Be Measured?: The Experience of SurveyMETER in Producing Three Episode Studies of Research-based Policy Influence (Indonesian Version) | Publication |
| 41 | Commissioning Knowledge for Policy: Reforms in the Procurement of Research in Indonesia | Publication |
| 42 | Diverse Strategies for More Sustainable Production of Legal Knowledge: Insights from the Indonesian Center of Law and Policy Studies (PSHK) | Publication |
| 43 | Getting Evidence into Social Policy: Lessons from Australia 2007 to 2017 | Publication |
| 44 | How Do You Evaluate a Mental Revolution? | Publication |
| 45 | Investing in Knowledge: The Establishment of the Indonesian Science Fund | Publication |
| 46 | Is Measuring Policy Influence Like Measuring Thin Air?: The Experience of SurveyMETER in Producing Three Episode Studies of Research-based Policy Influence | Publication |
| 47 | Linking Values and Research Evidence for Policy Advocacy: The Journey of the Indonesian Forum for Budget Transparency | Publication |
| 48 | Using Evidence to Develop Social Policies: Lessons from Australia From 2007 to 2017 (Indonesian Version) | Publication |
| 49 | Linking Research Value and Evidence to Policy Advocacy: The Indonesian Forum's Journey for Budget Transparency (Indonesian Version) | Publication |
| 50 | Strategies for Generating More Sustainable Legal Knowledge: Insights from the Center for Law and Policy Studies (PSHK) (Indonesian Version) | Publication |
| 51 | Shifts in the Knowledge Sector in Indonesia from 2013-2016: A Synthesis of Cases of Change | Publication |
| 52 | Diagnostic Study: Addressing Barriers to University Research: A Case Study at the Faculty of Medicine, University of Gadjah Mada and the Center for Health Policy and Management | Publication |
| 53 | A Study on Organizational Development | Publication |
| 54 | Addressing Barriers to University Research | Publication |
| 55 | Fundraising Opportunity Assessment for Policy Research Institutes in Indonesia | Publication |
| 56 | Study of Fundraising Opportunities for Policy Research Institutes in Indonesia (Indonesian Version) | Publication |
| 57 | Lesson from the New Zealand Data Futures Forum: How to Unlock the Value of Data-driven Innovation and New ‘Evidence’ in Policy-making | Publication |
| 58 | Lessons for Building and Managing an Evidence Base for Policy | Publication |
| 59 | Managing a Government Think Tank: Inside the Black Box | Publication |
| 60 | Think Tank Management: Creating a Knowledge Repository (Indonesian Version) | Publication |
| 61 | Integrating and Presenting Complex Evidence for Policy Making: Experience with Annual Report Cards (Indonesian Version) | Publication |
| 62 | Overcoming Research Barriers at Universities (Indonesian Version) | Publication |
| 63 | Managing Government Think Tanks: Inside a Black Box (Indonesian Version) | Publication |
| 64 | Using Community Evidence to Improve Public Services: Lessons from the UPIK Program in Yogyakarta (Indonesian Version) | Publication |
| 65 | Using Evidence to Reflect on 20 Years of South African Democracy (Indonesian Version) | Publication |
| 66 | Lessons from the New Zealand Data Future Forum: How to Unlock the Value of Data-Driven Innovation and New 'Evidence' in Policy Making (Indonesian Version) | Publication |
| 67 | Lessons for Building and Managing an Evidence Base for Policy Making (Indonesian Version) | Publication |
| 68 | Research Knowledge Acquisition by National Level Decision Makers in Indonesia (Indonesian Version) | Publication |
| 69 | Reflections on Academies and Science Advice | Publication |
| 70 | Reflection on the Role of the Academy of Sciences in Supporting Science-Based Arguments (Indonesian Version) | Publication |
| 71 | Indonesian Knowledge Sector: A Contextual Analysis (Indonesian Version) | Publication |
| 72 | Organizational Development Studies (Indonesian Version) | Publication |
| 73 | Synthesising and Presenting Complex Evidence for Policy Making: Experience With Annual Report Cards | Publication |
| 74 | The Acquisition of Research Knowledge by National-Level Decision Makers in Indonesia | Publication |
| 75 | The Indonesian Knowledge Sector: A Contextual Analysis | Publication |
| 76 | Think Tank Management: Establishing a Knowledge Repository | Publication |
| 77 | Using Citizen Evidence to Improve Public Services: Lessons from the UPIK Program in Yogyakarta | Publication |
| 78 | Using Evidence to Reflect on South Africa's 20 Years of Democracy | Publication |
| 79 | Establishing Government Think Tanks: An Overview of Comparative Models | Publication |
| 80 | Investing in Evidence: Lessons from the UK Department for Environment, Food and Rural Affairs | Publication |
| 81 | Using Workshops to Develop an Evidence Strategy: Lessons from the UK Ministry of Environment, Food and Rural Affairs (Indonesian Version) | Publication |
| 82 | Relying on Evidence: Lessons from the UK Ministry of Environment, Food and Rural Affairs (Indonesian Version) | Publication |
| 83 | Developing a Government Think Tank: A Comparative Model Review (Indonesian Version) | Publication |
| 84 | Using Workshops to Develop an Evidence Strategy: Lessons from the UK Food Standards Agency | Publication |
| 85 | Working Politically: Research Contribution to Village Law Formulation (Indonesian Version) | Publication |
| 86 | Improving Health Services Through Knowledge Sharing and Communication: A Story of Change from the Regency of Lombok Barat | Publication |
| 87 | Working Politically: A Story of Change about the Contribution of Research Evidence to the New Village Law in Indonesia | Publication |
| 88 | Improving Health Services by Sharing Knowledge and Communication: A Story of Change from West Lombok (Indonesian Version) | Publication |
| 89 | Australia's Productivity Commission: Providing Independent Policy Advice to Government | Publication |
| 90 | Australian Productivity Commission: Providing Policy Advice Independently to the Government (Indonesian Version) | Publication |
| 91 | Guidelines for Inclusive Online Seminars for Participants with Disabilities (Indonesian Version) | Publication |
| 92 | Adequate Accommodation for Students with Disabilities during a Pandemic: Experience of Teaching Teachers Learning from Home (Indonesian Version) | Publication |
| 93 | Online Learning Guide for Students with Physical Disabilities (Indonesian Version) | Publication |
| 94 | Online Learning Guide for Students with Visual Disabilities | Publication |
| 95 | Do Local Governments in Indonesia Produce Evidence Based Policies | Publication |
| 96 | Indonesian Academy of Sciences Change Story: Partnership with Knowledge Sector Initiative (KSI) 2014-2019 (Indonesian Version) | Publication |
| 97 | Policy Brief: Building a Sustainable and Independent Research Funding Implementation in Indonesia (Indonesian Version) | Publication |
| 98 | Story of Change The Indonesian Academy of Sciences: Partnership with Knowledge Sector Initiative (KSI) 2014-2019 | Publication |
| 99 | The Era of Disruption: Indonesian Higher Education Opportunities and Challenges (Indonesian Version) | Publication |
| 100 | Science, Technology and Higher Education Towards Indonesia 2045 (Indonesian Version) | Publication |
| 101 | Opening Land Access for Young People and Marginalized Groups in Rural Areas (Indonesian Version) | Publication |
| 102 | Alternative Markets for Agricultural Products (Indonesian Version) | Publication |
| 103 | Study of Youth Employment Opportunities in Rural Areas (Indonesian Version) | Publication |
| 104 | Village Youth, Intergenerational Transition, and Social Change (Journal of Social Analysis, Vol. 20, No. 1 & 2, 2016 Special Edition) (Indonesian Version) | Publication |
| 105 | Food Independence Study (Journal of Social Analysis Vol. 19, No. 1, August 2015) (Indonesian Version) | Publication |
| 106 | Having More Access Leads to Better Welfare: Study of Access for People with Disabilities (PwD) and Its Spatial Impact | Publication |
| 107 | Revitalization of Vocational Schools and Its Relevance to the Business World and the Industrial World (Indonesian Version) | Publication |
| 108 | Communicating Sensitive Issues: The Challenges Facing Think Tanks | Publication |
| 109 | Learn from the Silk Value Chain Collaborative Study Process (Indonesian Version) | Publication |
| 110 | The Disappearance of the Female Weavers (Indonesian Version) | Publication |
| 111 | South Sulawesi Silk Commodity Value Chain Report (Indonesian Version) | Publication |
| 112 | South Sulawesi Silk Commodity Value Chain (Indonesian Version) | Publication |
| 113 | Questioning Women's Representation Data in Five Areas (Indonesian Version) | Publication |
| 114 | Citizen Political Transactions: Encouraging Citizen Political Participation in Elections & Development Planning (Indonesian Version) | Publication |
| 115 | Exploring Collaborative Research Models in Indonesia | Publication |
| 116 | Funding Governance Reform: Increasing the Effectiveness and Efficiency of the Ministry of Research and Technology/BRIN Funding Scheme (Indonesian Version) | Publication |
| 117 | Guidelines for Research Protocols and Community Service during the Covid-19 Pandemic and Other Emergency Conditions for Adapting to the New Normal (Indonesian Version) | Publication |
| 118 | Identification of Problems with the Personal Data Protection Bill (Indonesian Version) | Publication |
| 119 | Reforming Research in Indonesia: Policies and Practices (Indonesian Version) | Publication |
| 120 | Building an Agricultural Sector that Has Resilience to the COVID-19 Pandemic (Indonesian Version) | Publication |
| 121 | Encouraging Villages to Care for Women (Indonesian Version) | Publication |
| 122 | Optimizing the Utilization of Village Funds for Pandemic Impact Recovery (Indonesian Version) | Publication |
| 123 | Opportunities for Recovery from the Impact of the Covid-19 Pandemic Through Social Capital and Local Initiatives (Indonesian Version) | Publication |
| 124 | The Role and Strategy of BUM Desa in Restoring the Village Economy during the Pandemic (Indonesian Version) | Publication |
| 125 | Policy Advocacy for the Implementation of the Village Law (Indonesian Version) | Publication |
| 126 | Script of Policy Input for Strengthening Village Issues and Rural Areas in the Gunungkidul Regency RPJMD Technocratic Document 2021-2024 (Indonesian Version) | Publication |
| 127 | The Urgency of Simplifying the Implementing Regulations of the Village Law (Indonesian Version) | Publication |
| 128 | Input Paper for the 2020-2024 RPJMN - Village and Rural Area Sector (Indonesian Version) | Publication |
| 129 | Rural and Urban Disparity in the Special Region of Yogyakarta (Indonesian Version) | Publication |
| 130 | Caring for Local Democracy for Village Economic Transformation (Indonesian Version) | Publication |
| 131 | Asymmetric Village Assistance to Strengthen Villages in Indonesia (Indonesian Version) | Publication |
| 132 | Developing BUMDes for Village Economic Transformation (Indonesian Version) | Publication |
| 133 | Developing an Asymmetric Village Assistance Model in Indonesia (Indonesian Version) | Publication |
| 134 | Political Parties, Money and Elections (Indonesian Version) | Publication |
| 135 | Portrait of Local Politics & Economy in Indonesia: Dynamics of Democratization, Economic Development & Rural Areas (Indonesian Version) | Publication |
| 136 | Knowledge and Innovation Ecosystem Blueprint (Indonesian Version) | Publication |
| 137 | Indonesia's Knowledge Sector is Catching Up, but a Large Gap Persists | Publication (Indonesian Version) |
| 138 | What Shapes Evidence use in a Government Agency? | Publication |
| 139 | Perspectives and Experiences of the Research Culture at Universities in Indonesia: 2017 | Publication |
| 140 | Farming with Wisdom (Indonesian Version) | Publication |
| 141 | Farming with Wisdom | Publication |
| 142 | Blessings From the Sea: (Indonesian Version) Photo Essay | Publication |
| 143 | Blessings from the Sea: Photo Essay | Publication |
| 144 | Institutional Relations in Organizations Implementing Research, Development, Assessment. and Implementation with the Ministry of Research and Technology/National Research and Innovation Agency (Indonesian Version) | Publication |
| 145 | Diverse Strategies for More Sustainable Production of Legal Knowledge: Insights from the Indonesian Center of Law and Policy Studies (PSHK) | Publication |
| 146 | Impact of Large-Scale Social Restrictions in the Community on Hospital Visits (Indonesian Version) | Publication |
| 147 | BPJS Health's New Directors Need to Increase Effective Coverage of JKN | Publication |
| 148 | Harmonization of JKN Funds at BPJS Health with the concept of JKN Social Justice in the Health Financing RPP (Indonesian Version) | Publication |
| 149 | JKN Policy: Optimizing the Role and Functions of TKMKB through Strengthening of Independent Authorities (Indonesian Version) | Publication |
| 150 | Strengthening the Role of Local Governments in Overcoming the JKN Crisis (Indonesian Version) | Publication |
| 151 | The Surplus of BPJS Health and Implementation of Compensation Policy (Indonesian Version) | Publication |
| 152 | Evaluation of JKN Policy in 13 Provinces of Indonesia 2019 – 2020. (Indonesian Version) | Publication |
| 153 | National Health Insurance Program (JKN) Policy Review Report: Analysis in Three Aspects: Membership, Service and Financing (Indonesian Version) | Publication |
| 154 | Portrait: Fulfillment of Access to Health Services for Persons with Disabilities in the JKN Era (Indonesian Version) | Publication |
| 155 | Addressing Barriers to University Research: A Case Study of Four Universities in Indonesia | Publication |
| 156 | Overcoming Research Barriers at Universities: Case Studies of Four Universities in Indonesia (Indonesian Version) | Publication |
| 157 | Reviewing the 2006 Joint Ministerial Regulations and the Role Interfaith Forum: Findings from Database (Indonesian Version) | Publication |
| 158 | Freedom, Tolerance and Terrorism: research and religious policy in Indonesia. (Indonesian Version) | Publication |
| 159 | Global Practices for Building Innovation Ecosystems | Publication |
| 160 | Global Practices for Building Innovation Ecosystems: Annex | Publication |
| 161 | Establishing Evidence for Land Assignment History at Kalibakar Plantation: The Urgency to Take People's Testimonies into Account (Indonesian Version) | Publication |
| 162 | Agrarian Reform in the Protection and Conservation Forests: Is it possible? (Indonesian Version) | Publication |
| 163 | Regulatory Suffocating Participation: The Stagnation of Forestry Agrarian Reform in Balumpewa Village, Sigi Regency, Central Sulawesi | Publication |
| 164 | The Urgency of Accelerating the Release of Abandoned Land for TORA PT. Tulus Sintuwu Karya, Bunga Village, Sigi Regency, Central Sulawesi Province (Indonesian Version) | Publication |
| 165 | Sharpening Systemic Vulnerabilities in the Time of Covid-19 (Indonesian Version) | Publication |
| 166 | The Urgency of Socio-Economic Micro Studies in the Midst of Inequality in Land Tenure (Indonesian Version) | Publication |
| 167 | Gender Justice and Social Inclusion in Research Grants Ministry of Research, Technology and Higher Education 2013-2015 (Indonesian Version) | Publication |
| 168 | RA Policy: A Step Back in the Agrarian Reform Movement? (Indonesian Version) | Publication |
| 169 | A Portrait of Inequality of Land Tenure in Indonesia (Indonesian Version) | Publication |
| 170 | Three Important Notes Post-Determination of Customary Forests: Kasepuhan Karang and Tapang Sambas - Tapang Kemayu (Indonesian Version) | Publication |
| 171 | Barriers to Adoption of Research For Policy: Portrait of Political Dynamics of Batu Tourism Sector Policy and Structuring the Malioboro Region of Yogyakarta (Indonesian Version) | Publication |
| 172 | Research Permit Problems in Indonesia: Case Studies in DI Yogyakarta Province and East Java Province (Indonesian Version) | Publication |
| 173 | Reviewing Agrarian Reform and Social Forestry Policies (Indonesian Version) | Publication |
| 174 | Agrarian Conflicts and Indigenous Peoples' Rights in Forest Areas (Indonesian Version) | Publication |
| 175 | Breastfeeding and Toddler Diet During the Covid-19 Pandemic: It's Time to Activate Breastfeeding Behavior Changes and Interventions (Indonesian Version) | Publication |
| 176 | Parenting Patterns for Children Under Five Years During the Covid-19 Pandemic: Momentum of Change in Holistic Parenting by Mom and Dad (Indonesian Version) | Publication |
| 177 | Prevalence and Risk Factors of Dementia and Caregiver's Knowledge of the Early Symptoms of Alzheimer's Disease | Publication |
| 178 | What Prompts Policy Change? Comparative Analyses of Efforts to Create Age-Friendly Cities in 14 Cities in Indonesia | Publication |
| 179 | Advocacy to Support the Development of an Old-Age Policy: 2018 Bali Dementia Study Results Report (Indonesian Version) | Publication |
| 180 | Advocacy to Support the Development of an Old-Age Policy: 2018 Bali Dementia Study Results Report (Indonesian Version) | Publication |
| 181 | We Need to Pay Attention to Dementia Prevalence Figures (Indonesian Version) | Publication |
| 182 | Data Inspires Policy: Balikpapan City Study Episode Towards an Age Friendly City 2030 (Indonesian Version) | Publication |
| 183 | Two out of ten seniors develop dementia by the time they reach 70 years of age: Dementia Studies at Yogyakarta Special Region (Indonesian Version) | Publication |
| 184 | Information Strengthening Policy: Episode Study of Denpasar City's Commitment to Realizing an Integration Policy of Child Friendly Cities, Elderly Friendly Cities, and Green Open Spaces in Healthy Cities (Indonesian Version) | Publication |
| 185 | Weaving Partnerships for Policy: An Episode Study on the Declaration of Jakarta as a Dementia Friendly and Elderly Friendly City (Indonesian Version) | Publication |
| 186 | Two of Ten Elderly Have Dementia when Entering Age of 70 Years Old: Evidence from Dementia Study in Yogyakarta | Publication |
| 187 | Data Inspires Policy: Balikpapan City Study Episode Towards an Age Friendly City 2030 (Indonesian Version) | Publication |
| 188 | Collection of Policy Recommendations: Handling the Multidimensional Crisis of the COVID-19 Pandemic (Indonesian Version) | Publication |
| 189 | KRISNA Sustainability as a Policy Instrument for Strengthening Bureaucratic Reform (Indonesian Version) | Publication |
| 190 | Transformation of Research Governance in Higher Education (Indonesian Version) | Publication |
| 191 | Overcoming Research Barriers at Universities: A case study from Universitas Indonesia (Indonesian Version) | Publication |
| 192 | Addressing Barriers to University Research: A Case Study of Atma Jaya Catholic University of Indonesia | Publication |
| 193 | Overcoming Research Barriers at Universities: Case Study Atma Jaya Catholic University of Indonesia (Indonesian Version) | Publication |
| 194 | Lessons Learned from the Pilot Program for Knowledge-Based Policy Development in South Sulawesi (Indonesian Version) | Infographics |
| 195 | KSI Year in Review 2021 (Indonesian Version) | Infographics |
| 196 | KSI Year in Review 2021 | Infographics |
| 197 | KSI Year in Review 2020 (Indonesian Version) | Infographics |
| 198 | KSI Year in Review 2020 | Infographics |
| 199 | Improving Funding Governance to Realize Ideal Research (Indonesian Version) | Infographics |
| 200 | The Urgency of Social Research in Handling a Pandemic | Infographics |
| 201 | Inclusive Innovation for Covid-19 Pandemic Mitigation (Indonesian Version) | Infographics |
| 202 | KSI Year in Review 2019 (Indonesian Version) | Infographics |
| 203 | KSI Year in Review 2019 | Infographics |
| 204 | KSI Partners (Indonesian Version) | Infographics |
| 205 | KSI Partners | Infographics |
| 206 | 2018 End of Year Reflection | Infographics |
| 207 | KSI Year in Review 2018 | Infographics |
| 208 | IDF In Numbers | Infographics |
| 209 | The Contribution of Research in Promoting Balikpapan's Age-Friendly City Policy | Infographics |
| 210 | Evidence Policy Unit in Finland: the Government Policy Analysis Unit (Politiikka-analyysiyksikkö) | Infographics |
| 211 | Evidence Policy Unit in South Africa: the Department for Planning, Monitoring and Evaluation (DPME) | Infographics |
| 212 | Evidence Policy Unit in Colombia: SINERGIA | Infographics |
| 213 | Evidence Policy Unit in Malaysia: PEMANDU | Infographics |
| 214 | KSI Phase I Achievements Against 6 Key Barriers in Research | Infographics |
| 215 | Higher Education and R&D Expenditure (Indonesian Version) | Infographics |
| 216 | Higher Education and R&D Expenditure | Infographics |
| 217 | Manufacturing Performance (Indonesian Version) | Infographics |
| 218 | Manufacturing Performance | Infographics |
| 219 | Academic Publications Performance | Infographics |
| 220 | Creating an Indonesian Science Fund (Indonesian Version) | Infographics |
| 221 | Creating an Indonesian Science Fund | Infographics |
| 222 | Story of Change: Improving Health Services by Sharing Knowledge and Communication in West Lombok (Indonesian Version) | Infographics |
| 223 | Relying on Evidence: Lessons Learned from the Ministry of Environment, Food and Rural Affairs (DEFRA) | Infographics |
| 224 | Providing Policy Advice Independently to the Government (Indonesian Version) | Infographics |
| 225 | Interdisciplinary Collaboration Promotes Health Science Relevance (Indonesian Version) | Article |
| 226 | Creative Economy Actors Withering during the Pandemic | Article |
| 227 | Creative Economy Actors Withering during the Pandemic (Indonesian Version) | Article |
| 228 | Social Science Highlights the Pandemic's Impact on Vulnerable Groups | Article |
| 229 | Social Sciences Highlight the Impact of the Pandemic on Vulnerable Groups (Indonesian Version) | Article |
| 230 | Type III Swakelola Creates Sustainable Collaboration Between Government and CSOs (Indonesian Version) | Article |
| 231 | Collaboration of Policy Analysts For Development Recommendations | Article |
| 232 | Women's Welfare Is Paramount to Regeneration of Silk Industry | Article |
| 233 | Roadmap for the Elimination of Violence Against Women in Indonesia​ | Article |
| 234 | Roadmap for the Elimination of Violence Against Women in Indonesia (Indonesian Version) | Article |
| 235 | Policy Analysts’ Collaboration for Development Plan Recommendations (Indonesian Version) | Article |
| 236 | Women's Welfare Is Important for Silk Regeneration (Indonesian Version) | Article |
| 237 | PPIM UIN Sustainability to Guard Religious Tolerance | Article |
| 238 | PPIM UIN Sustainability Guards Religious Tolerance (Indonesian Version) | Article |
| 239 | Ensuring the Financial Sustainability of Policy Research Institutes | Article |
| 240 | Monitoring the Financial Sustainability of Policy Research Institutes (Indonesian Version) | Article |
| 241 | Low Carbon Development Can Reduce Extreme Poverty (Indonesian Version) | Article |
| 242 | Low carbon development is expected to reduce extreme poverty | Article |
| 243 | SMERU's Active Role in Promoting Evidence-Based Policy (Indonesian Version) | Article |
| 244 | SMERU's Active Role in Promoting Evidence-Based Policy | Article |
| 245 | PUSAD Paramadina Encourages Institutionalization of FKUB Database (Indonesian Version) | Article |
| 246 | PUSAD Paramadina Promotes Institutionalization of Religious Harmony Forum Database | Article |
| 247 | Dissemination Efforts Policy Analyst Functional Position Guidelines (Indonesian Version) | Article |
| 248 | On the Continuing Dissemination of the Policy Analyst Guideline | Article |
| 249 | Multi-stakeholder Collaboration Encourages Policy Innovation in the Regions (Indonesian Version) | Article |
| 250 | Multi-stakeholder Collaboration Encourages Policy Innovation in the Regions | Article |
| 251 | PSHK Research and Advocacy Pushes Regulatory Reform (Indonesian Version) | Article |
| 252 | PSHK Research and Advocacy Pushes Regulatory Reform | Article |
| 253 | Sajogyo Institute Advocacy For Agrarian Policy Reform (Indonesian Version) | Article |
| 254 | Sajogyo Institute Advocacy for Agrarian Policy Reform | Article |
| 255 | Enhancing Government and Non-Government Think Tank Collaboration: BRIN Exploration of Business Process Mechanism (Indonesian Version) | Article |
| 256 | Improving the Collaboration between the Government and Non-Government Think Tanks: BRIN Explores the Business Process Mechanism | Article |
| 257 | Simplification of Mechanisms to Promote Type III Swakelola Implementation (Indonesian Version) | Article |
| 258 | Streamlining of Mechanisms to Promote Type III Swakelola Implementation | Article |
| 259 | FITRA Strengthens the Use of Type III Swakelola in South Sulawesi (Indonesian Version) | Article |
| 260 | FITRA Strengthens the Use of Type III Swakelola in South Sulawesi | Article |
| 261 | KPPOD Influences the Implementing Regulations for the Omnibus Law on Job Creation (Indonesian Version) | Article |
| 262 | KPPOD Influences the Implementing Regulations for the Omnibus Law on Job Creation | Article |
| 263 | Research for Policy Needs to Involve Think Tank Organizations (Indonesian Version) | Article |
| 264 | Research for Policy Needs to Involve Think Tank Organizations | Article |
| 265 | Article 33 Indonesia's Advocacy for Revitalizing Vocational Schools (Indonesian Version) | Article |
| 266 | Article 33 Indonesia's Advocacy for Revitalizing Vocational Schools | Article |
| 267 | ELSAM Study and Advocacy to Ensure the Respect and Fulfillment of Human Rights (Indonesian Version) | Article |
| 268 | ELSAM's Study and Advocacy to Ensure the Respect and Fulfillment of Human Rights | Article |
| 269 | Institutional Strengthening Necessary to Ensure GEDSI Policy Implementation (Indonesian Version) | Article |
| 270 | Institutional Strengthening Necessary to Ensure GEDSI Policy Implementation | Article |
| 271 | All Research Stages Needs to be Communicated with Stakeholders (Indonesian Version) | Article |
| 272 | All Research Stages Needs to be Communicated with Stakeholders | Article |
| 273 | IRE Advocacy for a More Effective Village Policy and Budget Design (Indonesian Version) | Article |
| 274 | IRE Advocacy for a More Effective Village Policy and Budget Design | Article |
| 275 | From Local to National: Learning from SurveyMETER Study (Indonesian Version) | Article |
| 276 | From Local to National: Learning from SurveyMETER Study | Article |
| 277 | The Journey of the Knowledge and Innovation Ecosystem Blueprint (Indonesian Version) | Article |
| 278 | The Journey of the Knowledge and Innovation Ecosystem Blueprint | Article |
| 279 | CSIS Strengthens Evidence-Based Pandemic Management (Indonesian Version) | Article |
| 280 | CSIS Strengthens Evidence-Based Pandemic Management | Article |
| 281 | FK-KMK UGM PKMK Innovation Improves Health Knowledge Management in the Pandemic Era (Indonesian Version) | Article |
| 282 | Innovation from PKMK FK-KMK UGM to Improve Knowledge Management on Health in the Pandemic Era | Article |
| 283 | PUI-PT PPH PUK2IS UAJ Advocacy for Strengthening Mental Health Policies in Pandemic Situations (Indonesian Version) | Article |
| 284 | PUI-PT PPH PUK2IS UAJ Advocates Mental Health Policy in Pandemic Situation | Article |
| 285 | Government Institutions Need to Optimize the Role of Policy Analysts (Indonesian Version) | Article |
| 286 | Government Institutions Need to Optimize the Role of Policy Analysts | Article |
| 287 | Limited Supply of Vaccination Barriers (Indonesian Version) | Article |
| 288 | Limited Supply Hinders Vaccination | Article |
| 289 | Knowledge and Innovation is the Foundation of Development (Indonesian Version) | Article |
| 290 | Knowledge and Innovation is the Foundation of Development | Article |
| 291 | GESI Mainstreaming needs Collaboration (Indonesian Version) | Article |
| 292 | GESI Mainstreaming needs Collaboration | Article |
| 293 | The Work of Cakra Wikara Indonesia in Encouraging Equal and Participatory Politics (Indonesian Version) | Article |
| 294 | The Work of Cakra Wikara Indonesia in Encouraging Equal and Participatory Politics | Article |
| 295 | AKATIGA Advocacy Research Unlocks Inclusive Job Opportunities in Rural Areas (Indonesian Version) | Article |
| 296 | AKATIGA Advocacy Research Unlocks Inclusive Job Opportunities in Rural Areas | Article |
| 297 | During the Pandemic, the Double Burden Holds Back Female Researchers (Indonesian Version) | Article |
| 298 | During the Pandemic, the Double Burden Holds Back Female Researchers | Article |
| 299 | Digital Transformation as an Opportunity to Advance the Knowledge and Innovation Ecosystem (Indonesian Version) | Article |
| 300 | Digital Transformation as an Opportunity to Advance the Knowledge and Innovation Ecosystem | Article |
| 301 | Happy International Women's Day 2021 (Indonesian Version) | Article |
| 302 | Happy International Women's Day | Article |
| 303 | A Value Chain Study to Mark the Beginning of Silk Industry Recovery in South Sulawesi (Indonesian Version) | Article |
| 304 | A Value Chain Study to Mark the Beginning of Silk Industry Recovery in South Sulawesi | Article |
| 305 | SMERU Mitigates Learning Inequality during the COVID-19 Pandemic (Indonesian Version) | Article |
| 306 | SMERU Mitigates Learning Inequality during the COVID-19 Pandemic | Article |
| 307 | PPIM UIN Promotes Tolerance through Islamic Education (Indonesian Version) | Article |
| 308 | PPIM UIN Promotes Tolerance through Islamic Education | Article |
| 309 | PUSAD Paramadina Advocates the Strengthening of the Religious Harmony Forum (Indonesian Version) | Article |
| 310 | PUSAD Paramadina Advocates the Strengthening of the Religious Harmony Forum | Article |
| 311 | KPPOD Influences Omnibus Law on Job Creation: Safeguarding Regional Autonomy, Creating Ease of Business and Certainty (Indonesian Version) | Article |
| 312 | KPPOD Influences Omnibus Law on Job Creation: Safeguarding Regional Autonomy, Creating Ease of Business and Certainty | Article |
| 313 | Vaccination Program: The Need for a Robust Distribution Plan (Indonesian Version) | Article |
| 314 | Vaccination Programs: The Need for a Robust Distribution Plan | Article |
| 315 | Working with CSOs to Tackle Covid-19 Pandemic (Indonesian Version) | Article |
| 316 | Working with CSOs to Tackle Covid-19 Pandemic | Article |
| 317 | Collaboration Facilitates Research and Innovation Ecosystem Development (Indonesian Version) | Article |
| 318 | Collaboration Facilitates Research and Innovation Ecosystem Development | Article |
| 319 | The Much-Needed Space for DPOs' Participation (Indonesian Version) | Article |
| 320 | The Much-Needed Space for DPOs' Participation | Article |
| 321 | Encouraging Research Ecosystems, Encouraging Evidence-Based Policy (Indonesian Version) | Article |
| 322 | Recommendation for KRISNA Optimization, Strengthening Through Dashboard (Indonesian Version) | Article |
| 323 | Recommendation for KRISNA Optimization, Strengthening Through Dashboard | Article |
| 324 | Improving KRISNA Towards an Ultimate Planning and Budgeting System System (Indonesian Version) | Article |
| 325 | Improving KRISNA Towards an Ultimate Planning and Budgeting System | Article |
| 326 | KRISNA's Journey to Integrate Planning and Budgeting (Indonesian Version) | Article |
| 327 | KRISNA's Journey to Integrate Planning and Budgeting | Article |
| 328 | Derivative Rules of the Job Creation Law Need to Involve the Community (Indonesian Version) | Article |
| 329 | Young People Need Access to Become Farmers (Indonesian Version) | Article |
| 330 | Emergency Curriculum to Support School Flexibility (Indonesian Version) | Article |
| 331 | Emergency Curriculum to Support School Flexibility | Article |
| 332 | Rapid Research to Promote Evidence-Based Policy-Making (Indonesian Version) | Article |
| 333 | Rapid Research to Promote Evidence-Based Policy-Making | Article |
| 334 | Needed: A Protocol for Inclusive Research (Indonesian Version) | Article |
| 335 | Needed: A Protocol for Inclusive Research | Article |
| 336 | Knowledge Sector and COVID-19 Mitigation (Indonesian Version) | Article |
| 337 | Knowledge Sector and COVID-19 Mitigation | Article |
| 338 | The Dynamic Roles of KSI's Partners in the COVID-19 Pandemic (Indonesian Version) | Article |
| 339 | The Dynamic Roles of KSI's Partners in the COVID-19 Pandemic | Article |
| 340 | Inclusive Research Needs Infrastructure Support (Indonesian Version) | Article |
| 341 | Pandemic Management Policy Requires Data Ecosystem (Indonesian Version) | Article |
| 342 | Pandemic Management Policy Requires Data Ecosystem | Article |
| 343 | Educational Services Must Be Adapted to Students' Conditions (Indonesian Version) | Article |
| 344 | Mainstreaming Gender Perspective Still Meets Challenges (Indonesian Version) | Article |
| 345 | KSI Explores the Potential Utilization of Swakelola Tipe III (Indonesian Version) | Article |
| 346 | KSI Explores the Potential Utilization of Swakelola Tipe III | Article |
| 347 | Can the Covid-19 Pandemic Boost Inclusive Education? | Article |
| 348 | Knowledge Management-Based Health Systems Need to be Encouraged (Indonesian Version) | Article |
| 349 | Knowledge Management-Based Health Systems Need to be Encouraged | Article |
| 350 | Budget Transparency and Synchronization of Fiscal Policy to Overcome COVID-19 (Indonesian Version) | Article |
| 351 | Budget Transparency and Synchronization of Fiscal Policies to Overcome COVID-19 | Article |
| 352 | Promoting Inclusive Education, AIDRAN Supported the Ministry of Education and Culture to Issue Online Learning Guidelines for Students with Disabilities (Indonesian Version) | Article |
| 353 | Promoting Inclusive Education, AIDRAN Supported the Ministry of Education and Culture to Issue Online Learning Guidelines for Students with Disabilities | Article |
| 354 | Think Policy Society, Youth Efforts to Improve the Quality of Public Policy in Indonesia (Indonesian Version) | Article |
| 355 | Why Knowledge Systems Matter: Four Perspectives & Insights (Indonesian Version) | Article |
| 356 | Why Knowledge Systems Matter: Four Perspectives & Insights | Article |
| 357 | Alignment of COVID-19 Pandemic Research Drives Inclusive and Sustainable Policies (Indonesian Version) | Article |
| 358 | Knowledge and Innovation Ecosystem Addresses the Impact of COVID-19 (Indonesian Version) | Article |
| 359 | Knowledge and Innovation Ecosystem Addresses the Impact of COVID-19 | Article |
| 360 | Entering the New Normal, Development Cooperation Needs a New Focus (Indonesian Version) | Article |
| 361 | Entering the New Normal, Development Cooperation Needs a New Focus | Article |
| 362 | The Important Role of Social Science in Solving Pandemic Problems (Indonesian Version) | Article |
| 363 | RISPRO KI Diaspora 2020, Collaboration of Indonesian-Diaspora Researchers to Overcome the Impact of Covid-19 (Indonesian Version) | Article |
| 364 | Research Funding Should Be Sustainable and Independent (Indonesian Version) | Article |
| 365 | Research Funding Should be Sustainable and Independent | Article |
| 366 | RISPRO KI Diaspora 2020, Collaboration of Indonesian-Diaspora Researchers to Overcome the Impact of Covid-19 (Indonesian Version) | Article |
| 367 | Maintaining Industrial Pace Amid COVID-19 Pandemic (Indonesian Version) | Article |
| 368 | Maintaining Industrial Pace Amid COVID-19 Pandemic | Article |
| 369 | The Urgency of Comprehensive Personal Data Protection Regulations (Indonesian Version) | Article |
| 370 | The Urgency of Comprehensive Personal Data Protection Regulation | Article |
| 371 | Mitigating the Impact of Covid-19: Social Safety Net for Marginal Groups (Indonesian Version) | Article |
| 372 | Mitigating the Impact of Covid-19: Social Safety Net for Marginal Groups | Article |
| 373 | The Role of Think Tanks in Handling Covid-19 (Indonesian Version) | Article |
| 374 | The Role of Think Tanks in Handling Covid-19 | Article |
| 375 | Guidelines for Compiling Accessible Online Lectures or Exams for People with Disabilities (Indonesian Version) | Article |
| 376 | Covid-19 and Social Economic Solutions for Marginalized Groups (Indonesian Version) | Article |
| 377 | Policy Bootcamp: A Network of Young Professionals Learning About Public Policy from Each Other (Indonesian Version) | Article |
| 378 | Policy Bootcamp: A Network of Young Professionals Learning About Public Policy from Each Other | Article |
| 379 | Improving the Quality of Public Services with Behavioral Approach Research (Indonesian Version) | Article |
| 380 | Improving the Quality of Public Services with Behavioral Insight Research | Article |
| 381 | Economic Growth Needs Research Support (Indonesian Version) |  |
| 382 | Young Researchers Push for Changes in Research Policy | Article |
| 383 | Young Researchers Push for Changes in Research Policy (Indonesian Version) | Article |
| 384 | Researchers Can Communicate Science in Various Ways (Indonesian Version) | Article |
| 385 | Building an Effective National Research and Innovation Agency (Indonesian Version) | Article |
| 386 | Building an Effective National Research and Innovation Agency | Article |
| 387 | Are partnership agreements a way forward for Doing Development Differently? | Article |
| 388 | Cultivate Research Climate in Higher Education with Incentives and Focus on Output (Indonesian Version) | Article |
| 389 | Indonesia's Social Science Research Performance Remains Inadequate | Article |
| 390 | Indonesia's Social Science Research Performance Remains Inadequate (Indonesian Version) | Article |
| 391 | Indonesian NGOs Now Can Access Government Funds for Community Services | Article |
| 392 | Indonesian NGOs Now Can Access Government Funds for Community Services (Indonesian Version) | Article |
| 393 | Reflection: Changes in Civil Society and Knowledge Production in the New Order and Reform Era (Indonesian Version) | Article |
| 394 | The Advancement of Culture is Still Hampered by Research Funds and Human Resources (Indonesian Version) | Article |
| 395 | Optimizing Research Results for Application in Policy (Indonesian Version) | Article |
| 396 | How to Accelerate Poverty Reduction in South Sulawesi (Indonesian Version) | Article |
| 397 | Realizing Cross-Sectoral Partnerships in Public Policy: MoU signing between PSHK and Eurocham (Indonesian Version) | Article |
| 398 | Improving the National Health Insurance Scheme to Achieve Universal Health Coverage | Article |
| 399 | AIPI's Position: Criminal Sanctions for Researchers Must Be Abolished (Indonesian Version) | Article |
| 400 | AIPI's Position: Criminal Sanctions for Researchers Must be Abolished | Article |
| 401 | Road to IDF 2019: Capturing Ideas and Innovations in Batam & Semarang (Indonesian Version) | Article |
| 402 | Road to IDF 2019: Capturing Ideas and Innovations in Batam and Semarang | Article |
| 403 | Inequality of Women in the Bureaucracy (Indonesian Version) | Article |
| 404 | Inequality of Women in Bureaucracy | Article |
| 405 | Research Funding Needs to be Professionally Managed (Indonesian Version) | Article |
| 406 | Research Funding Needs to be Professionally Managed | Article |
| 407 | Inclusive Research Needs to Involve Persons with Disabilities (Indonesian Version) | Article |
| 408 | Inclusive Research Needs to Involve Persons with Disabilities | Article |
| 409 | Supporting IDF 2019, KSI's Commitment to Evidence-based Policy (Indonesian Version) | Article |
| 410 | Supporting IDF 2019, KSI's Commitment to Evidence-based Policy | Article |
| 411 | New Mandala Fellowship Program for Indonesian Policy Researchers and Analysts (Indonesian Version) | Article |
| 412 | New Mandala Fellowship Program for Indonesian Researchers | Article |
| 413 | Aceh Provincial Government Teams Up with KSI to Improve Quality of R&D (Indonesian Version) | Article |
| 414 | Aceh Provincial Government Teams Up with KSI To Improve Quality of R&D | Article |
| 415 | Strengthening Public Policymaking Through Collaboration with Industry (Indonesian Version) | Article |
| 416 | Strengthening Public Policymaking Through Collaboration with Industry | Article |
| 417 | Presidential Decree 16/2018,(Indonesian Version) | Article |
| 418 | Presidential Decree 16/2018 : An Entry to Cooperation with Civil Society Organizations | Article |
| 419 | Self-Management of Goods and Services to Improve the Quality of Community Services (Indonesian Version) | Article |
| 420 | Procurement Changes Help Improve Public Service Delivery | Article |
| 421 | Bali Commits To Working On Dementia Prevention (Indonesian Version) | Article |
| 422 | Bali Commits To Working On Dementia Prevention | Article |
| 423 | Strengthening Knowledge Ecosystems Through Research and Business Forums (Indonesian Version) | Article |
| 424 | Strengthening Knowledge Ecosystems Through Research and Business Forums | Article |
| 425 | Economic Development Through Appropriate Technology (Indonesian Version) | Article |
| 426 | IKK socialization and technical guidance in Makassar (Indonesian Version) | Article |
| 427 | IKK seminar and workshop held in Makassar | Article |
| 428 | KSI Holds Seminar On Evidence-Based Policy In NTB (Indonesian Version) | Article |
| 429 | KSI Holds Seminar On Evidence-Based Policy In NTB | Article |
| 430 | IDF 2018 Closing Ceremony: Unemployment Reduction to Be Next Year's Theme (Indonesian Version) | Article |
| 431 | IDF 2018 Closing Ceremony: Unemployment Reduction to Be Next Year's Theme | Article |
| 432 | IDF 2018, Talks about Participatory Meetings to Overcome Gaps Between Archipelago Regions (Indonesian Version) | Article |
| 433 | IDF 2018: An Inclusive Forum on Addressing the Country's Regional Disparities | Article |
| 434 | Through IDF 2018, KSI promotes Equitable Regional Development in Indonesia | Article |
| 435 | KSI supports the government's effort to reduce regional disparities through 2018 IDF | Article |
| 436 | LAN-KSI Synergize to Optimize Knowledge Management (Indonesian Version) | Article |
| 437 | LAN-KSI Synergize To Optimize Knowledge Management | Article |
| 438 | Strong Research Ecosystem Needed To Boost Indonesia's Economic Competitiveness (Indonesian Version) | Article |
| 439 | Strong Research Ecosystem Needed To Boost Indonesia's Economic Competitiveness | Article |
| 440 | Building a Research Cooperation Development Network (Indonesian Version) | Article |
| 441 | KSI Supports Bappenas to Build Networks with Researchers | Article |
| 442 | KRISNA-DAK Helps Local Government With Submission Of Special Allocation Funds (DAK) Proposals (Indonesian Version) | Article |
| 443 | KRISNA-DAK Helps Local Government With Submission Of Special Allocation Funds (DAK) Proposals | Article |
| 444 | CCPHI To Connect Researchers And The Private Sector (Indonesian Version) | Article |
| 445 | CCPHI To Connect Researchers And The Private Sector | Article |
| 446 | LPPM Grant Guidelines to Include Gender and Social Inclusion (GESI) Aspects (Indonesian Version) | Article |
| 447 | Research Grant Guidelines to Include Gender and Social Inclusion Perspectives | Article |
| 448 | KSI Supports Indonesian Media To Tackle Hoaxes (Indonesian Version) | Article |
| 449 | KSI Supports Indonesian Media To Tackle Hoaxes | Article |
| 450 | ARK Indonesia and The Conversation Supporting Ministry of Foreign Affairs to Translate Research into Policy | Article |
| 451 | Exploring cross-DFAT collaboration in West Nusa Tenggara | Article |
| 452 | Gender Inequality in Human Resources and Higher Education | Article |
| 453 | Indonesia Development Forum Strategic Partnership with the Indonesian Policy Research Alliance | Article |
| 454 | The Development Partner Disability Coordination Meeting | Article |
| 455 | The Indonesia Development Forum 2017: A New Pathway towards a More Inclusive Indonesia | Article |
| 456 | Ideas and Innovations Marketplace: Pitching Ideas and Innovations to Address Inequality | Article |
| 457 | A Note from Team Leader | Article |
| 458 | Indonesia and Australia Continue Cooperation to Improve Knowledge Sector | Article |
| 459 | Removing Constraints to Downstreaming Research Outputs into Commercial Products | Article |
| 460 | Improving Policy Analysis Skills | Article |
| 461 | Regional Seminars: Local Economic Governance to Address Inequality | Article |
| 462 | AIPI White Papers Launching: Science as Fundamental for Development | Article |
| 463 | Momentum for Reforms in Higher Education and Research | Article |
| 464 | Launch of Annotation of Law No. 30/2014 on Government Administration or Law on Government Administration | Article |
| 465 | Quality education. For whom? | Article |
| 466 | Shaping Disability Inclusive Development in Indonesia | Article |
| 467 | SurveyMETER research uptake in the Regulation of Social Services Ministry No. 4 Years 2017 | Article |
| 468 | Road to the Indonesian Development Forum 2017 | Article |
| 469 | Book Launch of KSI Partners on Villages | Article |
| 470 | International workshops on the Knowledge Sector in Indonesia: Learning from the past for the future | Article |
| 471 | Training for Policy Analysts for Middle and Junior Career Paths | Article (Indonesian Version) |
| 472 | Trainings on Policy Analyst for Middle and Junior Career | Article |
| 473 | Focus Group Discussion on Governance Revitalization in Higher Education and Research (Indonesian Version) | Article |
| 474 | Focus Group Discussion on Revitalization of Governance in Higher Education and Research | Article |
| 475 | Participation of KSI Partners in the Indonesian Women's Ulema Congress (Indonesian Version) | Article |
| 476 | KSI Partner Participation in the Congress of Indonesian Women Ulama | Article |
| 477 | Article 33 teams up with Kemenko PMK in exercising alternative formulation for the Village Fund (Dana Desa) | Article |
| 478 | The Launch of Integrated e-Planning, Budgeting and Performance Information | Article |
| 479 | Indonesia Development Forum 2017 | Article |
| 480 | SMERU's Indonesian Poverty and Livelihood Map (Indonesian Version) | Article |
| 481 | SMERU's Indonesian Poverty and Livelihood Map | Article |
| 482 | The Indonesia Alliance for Policy Research (Indonesian Version) | Article |
| 483 | The Indonesia Alliance for Policy Research | Article |
| 484 | Discussion Forum on the Implementation of Bureaucratic Reforms with Special Attention to Higher Education and the Establishment of a 'Task Force' for Higher Education Reform (Indonesian Version) | Article |
| 485 | Discussion Forum on the Implementation of Bureaucratic Reform with the Special Attention of Higher Education and the Establishment of ‘Task Force’ on Higher Education Reform | Article |
| 486 | One Indonesian Data: Towards a Better System and Governance for Successful Development (Indonesian Version) | Article |
| 487 | One Indonesian Data: Towards Better System and Governance for Successful Development | Article |
| 488 | Knowledge Sharing of Journal Management Policies and Practices (Indonesian Version) | Article |
| 489 | Knowledge Sharing on Journal Management Policy and Practice | Article |
| 490 | PSHK participates in Pre-Session Universal Periodic Review on Human Rights, in Geneva on 4-7 April and celebrates the Disability Law (Indonesian Version) | Article |
| 491 | PSHK participates in Pre-Session Universal Periodic Review on Human Rights, in Geneva on 4-7 April and celebrates the Disability Law | Article |
| 492 | KSI Sharing Return to Investment Methodology (Indonesian Version) | Article |
| 493 | KSI Sharing Return to Investment Methodology | Article |
| 494 | Culture as a Driver of National Development (Indonesian Version) | Article |
| 495 | Culture as a Driver for National Development | Article |
| 496 | International Workshop on Developing Inclusive Growth Index for Indonesia (Indonesian Version) | Article |
| 497 | International Workshop on Developing Inclusive Growth Index for Indonesia | Article |
| 498 | Syntegrity: Building a Shared Vision for the Knowledge Sector Program | Article |
| 499 | A Day Before the Doing Development Differently Workshop in Jakarta | Article |
| 500 | Doing Development Differently means Doing Monitoring & Learning Differently Too | Article |
| 501 | Open Merit and Promotion System – Revised State Civil Service Act 2014 (Indonesian Version) | Article |
| 502 | Local Actor Led Policy Development - KSI and Partners at the 2017 Australasian Aid Conference (Indonesian Version) | Article |
| 503 | Developing Communications Strategy for Policy Research and Government Institutions | Article |
| 504 | Downstreaming Research Products into Commercialization through Science Techno Park | Article |
| 505 | Government's Commitment to Increase the Number of Research Grants for Women (Indonesian Version) | Article |
| 506 | Implementing 'The New Development' Agenda | Article |
| 507 | Indonesian Policy Research Alliance: Identifying Assets (Indonesian Version) | Article |
| 508 | Bappenas and Kemenko PMK are Leading Harmonization of Village Indexes | Article |
| 509 | GESI Perspectives in R&D for Inclusive Public Policies (Indonesian Version) | Article |
| 510 | Barriers for Quality Research among Islamic States Universities | Article |
| 511 | CSIS Study on Implementation of Merit-based Recruitment for Civil Servants | Article |
| 512 | The complexity of “smart” practices across Indonesia (Indonesian Version) | Article |
| 513 | Policy Advocacy and Public Discourse on the Revisions to the 2014 Civil Service Law (UU ASN) | Article |
| 514 | Government committed to move up the number of research grants for women | Article |
| 515 | Government committed to move up the number of research grants for women | Article |
| 516 | International Conference on “Data Revolution for Policy Makers” | Article |
| 517 | “Local actor-led policy development” - KSI and Partners at the 2017 Australasian Aid Conference | Article |
| 518 | The complexities of smart practices across Indonesia | Article |
| 519 | Estimate Return on Investment of Policy Research and Policy Engagement | Article |
| 520 | The Financial Benefits to Using Data for SDGs with Dr. Luis Crouch | Article |
| 521 | “Meritocracy and Open Promotion System” – Revisions to the 2014 Civil Service Law | Article |
| 522 | The Research Excellence Alliance: Identifying Assets | Article |
| 523 | Media Discussion on Regional Economic Governance 2016 | Article |
| 524 | Knowledge Sharing Session with Media on Merit-based System and Open Recruitment in Indonesia's Civil Service | Article |
| 525 | KSI Research Partners meet to Discuss Joint Agendas | Article |
| 526 | KSI Knowledge Sharing Session: ‘How do you Evaluate a Mental Revolution?’ | Article |
| 527 | KSI Knowledge Sharing Session: Commercialization of Research Results & Patent Implementation | Article |
| 528 | National Seminar on “Innovative Development, Creative Leaders and Competitive Regions | Article |
| 529 | Puskapol Celebrates 10 years with a Book Launch | Article |
| 530 | Forum Kajian Desa Partners Continue to Engage with Government Agencies | Article |
| 531 | KSI's Partner Provide Policy Advice on Village Development | Article |
| 532 | KSI Highlights Gender in Research and Public Policy | Article |
| 533 | LAN Showcases Policy Analyst and Role of Women in Public Policy | Article |
| 534 | Indonesia's PISA results show need to use education resources more efficiently | Article |
| 535 | Article: Indonesia’s PISA Results Show a Need to Use Education Resources More Efficiently | Article |
| 536 | Discussion Forum on Human Resource Management in Universities to Provide Input to the Draft Government Regulation of PPPK | Article |
| 537 | Field Visit of the Bappenas e-Planning Team to Yogyakarta and Surabaya | Article |
| 538 | GESI Perspectives in R&D for Inclusive Public Policies | Article |
| 539 | Gender Equality and Social Inclusion Perspectives in Research and Development for Inclusive Public Policy | Article |
| 540 | Lembaga Administrasi Negara visit Thailand to Learn about Policy Analysis | Article |
| 541 | The launch of the Australia-Indonesia Science Symposium | Article |
| 542 | DIPI Call for Research: Review Panel | Article |
| 543 | CSIS Study on Implementation of Merit-based Recruitment for Civil Servants | Article |
| 544 | KSI Partners Facilitate Public Consultation on Simplified Reporting System for Government Research | Article |
| 545 | KSI’s Forum Kajian Desa Brief Bappenas’ Directorate of Disadvantaged Regions Transmigration and Villages | Article |
| 546 | SMERU Develops its Capacity through Horizontal Learning and Knowledge Exchanges | Article |
| 547 | Bappenas Networks with Government Think Tanks | Article |
| 548 | Bappenas' Integration of Planning Documents Gearing Up | Article |
| 549 | Round-Table Discussion on Women's Research Center in Higher Education | Article |
| 550 | Vice President Jusuf Kalla Dialogue with the Commissioner of the Australian Public Service Commission | Article |
| 551 | PPIM's Research Pleases the Minister of Religious Affairs | Article |
| 552 | Round Table Discussion on University Centers for Women and Gender Studies | Article |
| 553 | Bangladesh delegation + BCURE Project team on Bappenas' lessons learned of evidence-based planning | Article |
| 554 | GESI Training for Communications Practitioners | Article |
| 555 | RCA+ - Mixed Methods Training and Tertiary Education Study | Article |
| 556 | M&E Knowledge Sharing with BAPPENAS & Ministry of Social Affairs | Article |
| 557 | Launch of Science Discussion Forum between ALMI and KSP | Article |
| 558 | Addressing Complex Human Resource Management in Universities | Article |
| 559 | SMERU Briefing to Bappenas' Directorate for Industry, Creative Economy and Tourism | Article |
| 560 | PUSAD Paramadina's Knowledge Exchange Forum on Religious Tolerance and Violence | Article |
| 561 | Functional Positions of Policy Analyst, Researcher and Lecturer: Strengthening the Role of Think Tanks in Indonesia | Article |
| 562 | Policy Analyst, Researcher and Lecturer Functional Positions: Strengthening Think Tanks in Indonesia | Article |
| 563 | London Conference Evidence Works 2016 A Global Forum For Government | Article |
| 564 | The 'demand' side of evidence-based policy making: why and how. Two great days of discussion and sharing in London | Article |
| 565 | KSI’s Supporting DFAT and Partner Projects on Policy Influence and Knowledge-to-Policy | Article |
| 566 | Alliance for Research Excellence Declared | Article |
| 567 | Update on the KSI Stories of Change Initiative | Article |
| 568 | Bappenas Knowledge Center, Monitoring Visit to Bima | Article |
| 569 | Socialization of the Functional Position of Policy Analyst to Subnational Governments | Article |
| 570 | Countdown: Australia-Indonesia Science Symposium, 28-Nov to 1-Dec, 2016 | Article |
| 571 | Socialization of Bappenas' PAK and Mapping of Local Think Tanks | Article |
| 572 | AIPI Annual Assembly | Article |
| 573 | Philanthropy Plays an Increasing Role in Supporting Research in Indonesia | Article |
| 574 | Philanthropy's Growing Role in Supporting Research in Indonesia | Article |
| 575 | Indonesian Policy Analyst Association: Improving Public Policy, Reducing State Budget Inefficiency | Article |
| 576 | Indonesian Association of Policy Analysts: Improving Public Policy, Reducing Inefficient Use of State Budget | Article |
| 577 | Bureaucratic Reform in Higher Education: Updates and Challenges on Policy Formulation and Implementation | Article |
| 578 | Indonesia-Australia science cooperation to be one step further after high-level visit | Article |
| 579 | Indonesia-Australia science cooperation to be one step further after high-level visit | Article |
| 580 | Annual Report Cards: one way for government organizations to synthesise and present complex evidence for policy making | Article |
| 581 | Bappenas Educational Media for Smart Practices | Article |
| 582 | Inside the 'black box' of policy making: when policy researchers enter the bureaucracy | Article |
| 583 | Studies on Gender and Bureaucracy: Critical Notes of the Meeting of the Bureaucratic Reform Working Group | Article |
| 584 | Study on Gender and Bureaucracy: Critical Note on Bureaucratic Reform Working Group Meeting | Article |
| 585 | Local Knowledge and Wisdom Expected to be the Policy Base | Article |
| 586 | Public Policy Should be Based on Data and Knowledge | Article |
| 587 | Public Policy Must Be Based on Data and Knowledge (Indonesian Version) | Article |
| 588 | “One Size Fits All” Is No Longer Relevant for Sustainable Development in Indonesia (Indonesian Version) | Article |
| 589 | Nurturing the First Cohort of Indonesian Policy Analysts | Article |
| 590 | Free Yourself from Fear- Popular Writing for Research | Article |
| 591 | Free Yourself from Fear – Popular Writing for Research (Indonesian Version) | Article |
| 592 | Book: Local Knowledge in Sustainable Water Management (Indonesian Version) | Article |
| 593 | The Indonesian Science Fund, Paving the Way for Indonesia's Science & Research | Article |
| 594 | From the Visit of University of Newcastle President Prof Caroline McMillen | Article |
| 595 | UGM Research: Local Community Marginalization in the management of mining operations in NTT (Indonesian Version) | Article |
| 596 | UGM: Banyuwangi Gold Mining High Risk (Indonesian Version) | Article |
| 597 | UGM Polgov Team Holds Discussion of Research Results in Tanahbumbu (Indonesian Version) | Article |
| 598 | Workshop "Formulation of the Joint SID Platform to Support the Implementation of the Village Law” (Indonesian Version) | Article |
| 599 | PolGov UGM Encourages Local Communities to Get Involved in Mining Management in NTT (Indonesian Version) | Article |
| 600 | Realizing a Prosperous Indonesia through the Use of Science (Indonesian Version) | Article |
| 601 | AIPI: The Key to Success in Using Demographic Dividend (Indonesian Version) | Article |
| 602 | The Long Road to Secure Torong Besi (Indonesian Version) | Article |
| 603 | Village Fund Discussion: Many Interests Leading to Obstacles (Indonesian Version) | Article |
| 604 | Issues and Opportunities in Higher Education : Finding Ways to Promote Science-Based Research - A Third Seminar | Article |
| 605 | Issues and Opportunities in Higher Education: Looking for Ways to Promote Research-Based Science - Third Seminar (Indonesian Version) | Article |
| 606 | Matchmaking for Public Policy Funding – Initial Dialogue with Private Sector and Philanthropic Organizations (Indonesian Version) | Article |
| 607 | Matchmaking for Public Policy Funding – Initial Dialogue with Private Sector and Philanthropy Organizations | Article |
| 608 | Matchmaking for Public Policy Funding – Initial Dialogue with Private Sector and Philanthropic Organizations (Indonesian Version) | Article |
| 609 | Data innovation as a new source of evidence for policy making: the experience of the New Zealand Data Futures Forum | Article |
| 610 | FISIP-UI To Educate Farmers About Climate Change (Indonesian Version) | Article |
| 611 | Local Knowledge to Restore Three Season Markers | Article |
| 612 | Local Knowledge to Restore the Three Season Markers (Indonesian Version) | Article |
| 613 | Knowledge Sector Interview with Mari Pangestu | Article |
| 614 | Knowledge Sector Interview with Mari Pangestu by Zack Petersen (Indonesian Version) | Article |
| 615 | Building Capacity of Policy Analyst Instructors through Implementation of ToT of Policy Analyst | Article |
| 616 | Building Policy Analyst Teaching Capacity Through Implementation of Policy Analyst ToT (Indonesian Version) | Article |
| 617 | Jaleswari Pramodhawardhani's Interview on Nulistik Forum Discussion: Making Policy Paper is a Creative Work | Article |
| 618 | Jaleswari Pramodhawardhani's Interview on Nulistik Forum Discussion: Making Policy Papers is Creative Work (Indonesian Version) | Article |
| 619 | Writing Forum Discussion: Guarding Research Results for Policy | Article |
| 620 | Writing Forum Discussion: Controlling Research Results for Policy (Indonesian Version) | Article |
| 621 | KSI Working Group Meeting: Bureaucratic Reform to Improve Policy Making Process | Article |
| 622 | KSI Working Group Meeting: Bureaucratic Reform for Policy Making Process (Indonesian Version) | Article |
| 623 | KSI Working Group Meeting: Supporting Village-Led Development | Article |
| 624 | KSI Working Group Meeting: Support Village-Led Development (Indonesian Version) | Article |
| 625 | KSI Working Group Meeting: Strengthening the Synergy Between Research, Funding and Human Resources | Article |
| 626 | KSI Working Group Meeting: Strengthening Synergies Between Research, Financing and Human Resources (Indonesian Version) | Article |
| 627 | Smart Practice | Article |
| 628 | Workshops and Science Field Shops (Indonesian Version) | Article |
| 629 | Do Think Tanks Underinvest in Management? A Conversation with Raymond Struyk | Article |
| 630 | Are Think Tanks Underinvesting in Management? A Conversation with Raymond Struyk (Indonesian Version) | Article |
| 631 | Research Capacity Strengthening for Regional Development Innovation | Article |
| 632 | Strengthening R&D Research Capacity for Regional Development Innovation (Indonesian Version) | Article |
| 633 | Conditions and Prospects of Higher Education Ability to Develop Science (Indonesian Version) | Article |
| 634 | Condition and Prospects of Higher Education Ability on Developing Science | Article |
| 635 | AIPI and Kemenristek-DIKTI: Kick-Off Meeting about National Policy on S&T and Higher Education | Article |
| 636 | AIPI and Kemenristek-DIKTI: Kick-Off Meeting on National Policy on S&T and Higher Education (Indonesian Version) | Article |
| 637 | Development 2.0: future or already reality? A discussion with Michael Woolcock | Article |
| 638 | Development 2.0: Future or Reality? Discussion with Michael Woolcock (Indonesian Version) | Article |
| 639 | What can Indonesian Research Institutes Learn from Chinese Think Tanks? | Article |
| 640 | One Day Seminar Notes (Indonesian Version) | Article |
| 641 | Knowledge Sector Initiative (KSI) Supports Local Knowledge in Policy Making | Article |
| 642 | KSI Supports Local Knowledge in Policy Making (Indonesian Version) | Article |
| 643 | AIPI and LPDP Signed Memorandum of Understanding on the Indonesian Science Fund (Indonesian Version) | Article |
| 644 | Announcement - KSI Local Knowledge Grants Selection Results 2015/2016 | Article |
| 645 | Announcement - Results of the 2015/2016 KSI Local Knowledge Grant Selection (Indonesian Version) | Article |
| 646 | Signing of Memorandum of Understanding between IRE and Yogyakarta City KPU (Indonesian Version) | Article |
| 647 | Past Human Rights Violations: Proposed Institutionalization for Equitable Settlement (Indonesian Version) | Article |
| 648 | Bridging Policy and Public Interest - National Institute of Public Administration (LAN) | Article |
| 649 | Bridging Policy and Public Interests - The State Administration Agency (LAN) (Indonesian Version) | Article |
| 650 | Ecological Crisis, More Women Leaders Need to Appear | Article |
| 651 | SAINS 2045 - What One Young Indonesian Scientist Learns from His Slum Neighborhood | Article |
| 652 | Science 2045 - What One Young Indonesian Scientist Learns from the His Neighborhood (Indonesian Version) | Article |
| 653 | Press conference : Research Institute and Ministry of National Development Planning/Bappenas Encourage Research Contribution for Better Public Policy (Indonesian Version) | Article |
| 654 | Behind the Image of the Poor Local Fisherman: Building Indonesia's Maritime Policy Network | Article |
| 655 | Behind the Image of a Poor Fisherman on a Boat: Building an Indonesian Maritime Policy Network (Indonesian Version) | Article |
| 656 | Reportage: Workshop for Diagnostic Study Mechanism on University Barriers to Research | Article |
| 657 | Young Scientists Forum III: Promoting Excellent Scientific Culture- The Launching of the 2045 SCIENCE Consultation Draft (Indonesian Version) | Article |
| 658 | Minister of Finance, State Minister of National Development Planning Support the Autonomous Funding Mechanism for Science in Indonesia | Article |
| 659 | Minister of Finance and Minister of National Development Planning/Head of Bappenas Support Autonomous Research Funding System (Indonesian Version) | Article |
| 660 | AIPI Silver Jubilee: Remarks to the Young Academy and Young Scientists Network by Fred Carden | Article |
| 661 | AIPI Silver Celebration: Foreword by the Academy and Network of Young Scientists by Fred Carden, Jakarta 26 May 2015 (Indonesian Version) | Article |
| 662 | AIPI Launches SCIENCE (A Century of Science Inspiration) 2045 and Forms an Academy of Young Scientists (Indonesian Version) | Article |
| 663 | 25 Years of AIPI: It's Time to Awaken the Passion for Science in Indonesia (Indonesian Version) | Article |
| 664 | SCIENCE 2045: Interview with Study Director Hasnawati Saleh | Article |
| 665 | Science 2045 - Interview with Study Director Hasnawati Saleh (Indonesian Version) | Article |
| 666 | Supporting the Life of Batik-Makers through Action Research | Article |
| 667 | Supporting the Life of Batik-Makers through Action Research (Indonesian Version) | Article |
| 668 | Reportage: Study Visits to Think Tank Institutions in China (Indonesian Version) | Article |
| 669 | Business development: What Research Has To Do With It (Indonesian Version) | Article |
| 670 | Quality Policy Research Starts with a Good Design (Indonesian Version) | Article |
| 671 | The Hourglass Method in Writing Opinion Articles (Indonesian Version) | Article |
| 672 | Making Research More Interesting - Lessons Learned from the Communication Workshop (Indonesian Version) | Article |
| 673 | 45 Crucial Scientific Questions for the Future of the Nation (Indonesian Version) | Article |
| 674 | Opinion for Working Paper - Investing in Evidence: Some Lessons Learned from the UK for Ministries in Indonesia (Indonesian Version) | Article |
| 675 | Data Innovation Conference for Policy Makers 2014 5 (Indonesian Version) | Article |
| 676 | Data Innovation Conference for Policy Makers 2014 4 (Indonesian Version) | Article |
| 677 | Data Innovation Conference for Policy Makers 2014 3 (Indonesian Version) | Article |
| 678 | The Importance of NGO Think Tanks in Policy Making in the Parliament (Indonesian Version) | Article |
| 679 | Successful Research Proposal Writing – Get Started and Continue Without Giving Up (Indonesian Version) | Article |
| 680 | Business Development: What Research Has To Do With It | Article |
| 681 | Business development: What Research Has To Do With It (Indonesian Version) | Article |
| 682 | Quality Policy Research Starts with Good Design | Article |
| 683 | Quality Policy Research Starts with Good Design (Indonesian Version) | Article |
| 684 | Hourglass Method in Writing Opinion Article | Article |
| 685 | Making Research More Engaging – Learning from Communications Workshops | Article |
| 686 | Making Research More Interesting - Learning from the Communication Workshop (Indonesian Version) | Article |
| 687 | 45 Fundamental Scientific Questions for the Future of the Nation | Article |
| 688 | Call for Applications: Junior and Senior Fellowships 2015-2016 | Article |
| 689 | Opinion for Working Paper - Investing in Evidence: Some Lessons Learned from the UK for Ministries in Indonesia (Indonesian Version) | Article |
| 690 | Opinion on Working Paper - Investing in Evidence: Some Lessons from the UK for Indonesian Ministries | Article |
| 691 | Data Innovation for Policy Makers Conference 2014 5 | Article |
| 692 | Data Innovation for Policy Makers Conference 2014 4 | Article |
| 693 | Data Innovation for Policy Makers Conference 2014 3 | Article |
| 694 | Data Innovation for Policy Makers Conference 2014 2 | Article |
| 695 | Data Innovation Conference for Policy Makers 2014 2 | Article |
| 696 | The Problem of Articles on Hate Speech and Defamation in the Virtual Realm (Indonesian Version) | Article |
| 697 | Data Innovation for Policy Makers Conference 2014 1 | Article |
| 698 | Learning from National Research Agenda 2010-2014 | Article |
| 699 | Lessons Learned National Research Agenda 2010-2014 (Indonesian Version) | Article |
| 700 | Invitation - Making Good Policy: the challenges of evidence in policy reform | Article |
| 701 | KPPOD Brief - October-December 2014 Edition (Indonesian Version) | Article |
| 702 | Fajri Nursyamsi, a PSHK Researcher, Together with the Working Group on the Bill on Persons with Disabilities met with Members of Commission VIII DPR RI from the PAN faction (Indonesian Version) | Article |
| 703 | Multi-Stakeholder in Internet Settings: Is it there and Why? (Indonesian Version) | Article |
| 704 | OPINION: Integrating Human Rights and the Internet (Indonesian Version) | Article |
| 705 | Indonesian Science Fund Soft Launching | Article |
| 706 | Indonesian Science Fund Soft Launching (Indonesian Version) | Article |
| 707 | Local Knowledge Grant Scheme - Registration Closes January 31 2015, 17:00 WIB (Indonesian Version) | Article |
| 708 | Aceh Tsunami, 10 Years Later (Indonesian Version) | Article |
| 709 | Business and human rights: More than pure CSR | Article |
| 710 | Opportunities and Challenges in the Implementation of the Village Law (Indonesian Version) | Article |
| 711 | Science Enrichment Program - Learning from Australia Scientific Excellence | Article |
| 712 | Science Enrichment Program - Learning from Australian Scientific Excellence (Indonesian Version) | Article |
| 713 | #TheExchangeJakarta: Learning About Collaboration from the On Think Tanks Exchange | Article |
| 714 | 'Chief storyteller' to UN, NGOs: Tell their story, not yours | Article |
| 715 | A 'revolution' to fill the data gap | Article |
| 716 | A Political Approach to The Social Sector | Article |
| 717 | Community knowledge + mobile phones = evidence for policy response | Article |
| 718 | International Conference - Innovation for Policy Makers | Article |
| 719 | International Conference - Data Innovation for Policy Makers (Indonesian Version) | Article |
| 720 | Lessons from the Jakarta Meeting - The Exchange (On Think Tanks) | Article |
| 721 | Indonesian Science Agenda – Responding to the Nation's Challenge in a Century of Independence | Article |
| 722 | Indonesian Science Agenda – Responding to the Nation's Challenges in a Century of Independence (Indonesian Version) | Article |
| 723 | Overcoming University Barriers for Research | Article |
| 724 | Overcoming University Barriers to Conducting Research (Indonesian Version) | Article |
| 725 | Impact Evaluation of Beneficiaries of PNPM/RESPEK in Papua and West Papua (Indonesian Version) | Article |
| 726 | Welcoming the New DPRD, Is There Any (New) Hope? (Indonesian Version) | Article |
| 727 | Promoting Pro-Community Plantation (Indonesian Version) | Article |
| 728 | The story of Munir's case (Indonesian Version) | Article |
| 729 | A bumpy road: Using data to inform policymaking | Article |
| 730 | The Importance of NGO Think Tanks in Policy Making in the Parliament (Indonesian Version) | Article |
| 731 | Writing a Successful Research Proposal – From Getting Started to Never Giving Up (Indonesian Version) | Article |
| 732 | Writing a Successful Research Proposal – From Getting Started to Never Giving Up | Article |
| 733 | The Role of Universities in Translating HIV/AIDS Research Results into Public Policy (Indonesian Version) | Article |
| 734 | Monitoring, Evaluation and Learning for Organizational Strategic Capacity Development | Article |
| 735 | Knowledge Sector Initiative Participates in Inauguration of Australia-Indonesia Research Summit | Article |
| 736 | KSI Partners To Sign Core Fund Grant Agreement (Indonesian Version) | Article |
| 737 | Effective Writing Workshop: Keep it Short and Simple! (Indonesian Version) | Article |
| 738 | Building Effective Communication Skills for Quality Policy (Indonesian Version) | Article |
| 739 | Two Indonesian Think-Tanks Participate in The Exchange in Lima, Peru (Indonesian Version) | Article |
| 740 | Five Partners Receive Core Fund Grants to Strengthen Research Capacity (Indonesian Version) | Article |
| 741 | Discussion on Sustainable Development Post-MDG 2015 (Indonesian Version) | Article |
| 742 | Workers Getting More Education | Article |
| 743 | Should We be Worried about Territorial Disputes in East Asia? | Article |
| 744 | Launching of Indonesia Development Forum and Announcement of IDF 2017 Call for Papers | Article |
| 745 | Working with CSOs to Tackle Covid-19 Pandemic | Story of Change |
| 746 | Working with CSOs to Tackle Covid-19 Pandemic (Indonesian Version) | Story of Change |
| 747 | A Long Road toward Research-Based Policy Making | Story of Change |
| 748 | Story of Change: Indonesian Academy of Sciences (Indonesian Version) | Story of Change |
| 749 | Achieve Inclusive Development Through Type III Self-Management | Story of Change |
| 750 | Achieve Inclusive Development Through Type III Self-Management | Story of Change (Indonesian Version) |
| 751 | Reducing the Gender Gap in Research | Story of Change (Indonesian Version) |
| 752 | Reducing the Gender Gap in Research | Story of Change |
| 753 | Selected Stories of Change from The Knowledge Sector Indonesia (KSI) Program Phase 1 (Indonesian Version) | Story of Change |
| 754 | Selected Stories of Change from The Knowledge Sector Indonesia (KSI) Program Phase 1 | Story of Change |
| 755 | Changes for Relevance and Regeneration (Indonesian Version) | Story of Change |
| 756 | Eight Years of Advocacy by Puskapol UI: The Ups and Downs of Overseeing the Issue of Women's Political Representation (Indonesian Version) | Story of Change |
| 757 | Gotong Royong (Collaboration) between Knowledge Sector Initiative (KSI) and the Indonesian Academy of Sciences (AIPI) | Story of Change |
| 758 | Leveraging Research to Improve the Quality of Health Policy (Indonesian Version) | Story of Change |
| 759 | Bureaucratic Dialogue Culture, Beginning of Bureaucratic Synergy and Researchers (Indonesian Version) | Story of Change |
| 760 | Strategic Steps to Prepare a Strategic Plan for Improving Governance of the UI Puskapol Institution (Indonesian Version) | Story of Change |
| 761 | Maintaining the Process Accountability and Knowledge Quality: The Story of Changes in Organizational Governance of PUSAD Paramadina (Indonesian Version) | Story of Change |
| 762 | From Data Collection to a Policy Reference: SurveyMETER's Story of Change after learning from experience in the Knowledge Sector (Indonesian Version) | Story of Change |
| 763 | Revolution in the Maternal and Child Health Service: Umbu Rara Meha Hospital Experience (Indonesian Version) | Story of Change |
| 764 | Setting up Foundation for the Awakening of Young Scientists – The Establishment of the Indonesian Academy of Young Scientists (Indonesian Version) | Story of Change |
| 765 | Along with Disabilities (Indonesian Version) | Story of Change |
| 766 | Transforming the Role of SMERU in Public Policy Formulation (Indonesian Version) | Story of Change |
| 767 | Building a Marine Fisheries Socio-Economic Knowledge Network (Indonesian Version) | Story of Change |
| 768 | The Long Road to Regulatory Reform: A Story behind the Birth of a Policy (Indonesian Version) | Story of Change |
| 769 | Puskapol Research Communication Strategy: Moving from the State to the Public Domain (Indonesian Version) | Story of Change |
| 770 | New Hope, New AIPI (Indonesian Version) | Story of Change |
| 771 | Turn, to the Right Path (Indonesian Version) | Story of Change |
| 772 | SOPs and Workplans as Starting Points for Change in PPIM (Indonesian Version) | Story of Change |
| 773 | Idealism of Bina Praja Journal Management (Indonesian Version) | Story of Change |
| 774 | Computer Interview: A New Way to Save on Survey Costs - A Story of Change for Efficient and Quality Research Data Collection (Indonesian Version) | Story of Change |
| 775 | Telling Stories About Local Traditions and Forest Conservation Through Film (Indonesian Version) | Story of Change |
| 776 | From Paper To Touch Screen (Indonesian Version) | Story of Change |
| 777 | The School Operators Task Force of Bogor City Government Initiative to Improve School Facilities and Infrastructure Database (Indonesian Version) | Story of Change |
| 778 | The Growth of a Knowledge Sharing Culture State Administration Institution (LAN) (Indonesian Version) | Story of Change |
| 779 | Speak up for those who are discriminated (Indonesian Version) | Story of Change |
| 780 | Improving Human Resources Management at Research Insitutes: SMERU Experience (Indonesian Version) | Story of Change |
| 781 | Indonesian Science Fund: Unleashing the Potentials of Indonesian Children to Open the Door to the Nobel Prizes (Indonesian Version) | Story of Change |
| 782 | From Fact Providers to Drivers of Policy Change: A Transformation (Indonesian Version) | Story of Change |
| 783 | Finding Partners to Power the Knowledge Sector (Indonesian Version) | Story of Change |
| 784 | SCIENCE45: Working and Befriending Colleagues from Other Disciplines (Indonesian Version) | Story of Change |
| 785 | AIPI Publications: AIPI Editor and the Effort to Voice Results from the “Work in Silence” (Indonesian Version) | Story of Change |
| 786 | Researchers and Obstacles Communicating Science (Indonesian Version) | Story of Change |
| 787 | Review Action: Commitment to the Weak (Indonesian Version) | Story of Change |
| 788 | “Melesi” : an Embryo for the Establishment of Village Health Insurance (Indonesian Version) | Story of Change |
| 789 | The Importance of the Role of Keujruen Blang for Farmers: A story on How to Promote Local Knowledge to Support Rice Management in Aceh (Indonesian Version) | Story of Change |
| 790 | The Metamorphosis of the Indonesian Academy of Sciences (Indonesian Version) | Story of Change |
| 791 | A Quicker Response to Manage Disasters Through Cross-Sectoral Coordination (Indonesian Version) | Story of Change |
| 792 | Efforts to Improve Health Services in West Lombok (Indonesian Version) | Story of Change |
| 793 | Improving West Lombok's Health Services | Story of Change |
| 794 | Working Politically: Research Contribution to Village Law Formulation (Indonesian Version) | Story of Change |
| 795 | Working Politically: Contribution of Research Evidence to the New Village Law in Indonesia | Story of Change |
| 796 | The Balcony Podcast: On Expertise | Podcasts |
| 797 | How Does Indonesia Design Laws? ft. (Indonesian Version) Gita Putri & Dendy Raditya | Podcasts |
| 798 | The Balcony Podcast: On Behavior | Podcasts |
| 799 | Voiced Assumptions: Things You Must Know About the State Budget ft.(Indonesian Version) Misbah Hasan | Podcasts |
| 800 | uTara Podcasts: A Democratic Country and Youth Optimism (Indonesian Version) | Podcasts |
| 801 | uTara Podcasts: Where do you want to take BRIN to? (Indonesian Version) | Podcasts |
| 802 | uTara Podcasts: A Cake from the Private Sector to Support Research (Indonesian Version) | Podcasts |
| 803 | uTara Podcasts: Does the state set aside something for CSOs? (Indonesian Version) | Podcasts |
| 804 | uTara Podcasts: The Difference Between Being Verbose and Being Scientific, and How This Relate to Policy Making (Indonesian Version) | Podcasts |
| 805 | uTara Podcasts: Why is Indonesia lagging behind Korea and Taiwan? (Indonesian Version) | Podcasts |
| 806 | uTara Podcasts: Even Data-Based Policies Can Go Wrong, Let Alone Inspiration (Indonesian Version) | Podcasts |
| 807 | uTara Podcasts: A Policy Without Research is One Without Direction (Indonesian Version) | Podcasts |
| 808 | uTara Podcasts: It's time now for the fishermen and farmers to talk about the industrial revolution 4.0 (Indonesian Version) | Podcasts |
| 809 | uTara Podcasts: Research Findings are piling up to the sky, but which have been implemented for the interest of our nation? (Indonesian Version) | Podcasts |
| 810 | Talking Indonesia: Policy in Focus: Big Data, Privacy and Elections with Wahyudi Djafar (ELSAM) | Podcasts |
| 811 | Talking Indonesia: Disparities Between Regions | Podcasts |
| 812 | KSI Podcast Series - Improving Think Tank Management | Video podcasts |
| 813 | KSI Podcast Series - Investing Evidence in Policy Making | Video podcasts |
| 814 | KSI Podcast Series – Productivity Commission: Providing Independent Policy Advice to Government | Video podcasts |
| 815 | KSI Podcast Series – Government Think Tanks: an Overview of Comparative Models | Video podcasts |
| 816 | KSI Podcast Series – Working Politically: the Contribution of Research in the Formulation of the Village Law | Video podcasts |
| 817 | Knowledge-Based Policy Development – Silk Commodities (Indonesian Version) | Videos |
| 818 | Guidelines for Optimizing the Role of Policy Analyst Functional Positions (Indonesian Version) | Videos |
| 819 | KRISNA for Better Planning and Budgeting (Indonesian Version) | Videos |
| 820 | Why Do We Delay Passing Important Laws? - On Patriarchy (Indonesian Version) | Videos |
| 821 | KSIxChange#19: The Position of Think Tanks in the Midst of the Covid-19 Pandemic (Indonesian Version) | Videos |
| 822 | COVID-19: Explanation in Bisindo (Indonesian Version) | Videos |
| 823 | KSIxChange #18: Covid-19 and Social Economic Impact for Marginalized Groups in Indonesia (Indonesian Version) | Videos |
| 824 | AKATIGA - Type III Swakelola (Indonesian Version) | Videos |
| 825 | VLOG Frame & Sentences: Why is the Quality of Indonesian Research Lagging Behind? - On Scientific Temper (Indonesian Version) | Videos |
| 826 | Indonesia: Workshop on Doing Development Differently | Videos |
| 827 | Journalistic Video Tutorial Episode 8: Publication (Indonesian Version) | Videos |
| 828 | Journalism Video Tutorial Episode 7: Editing Process(Indonesian Version) | Videos |
| 829 | Journalistic Video Tutorial Episode 6: Building Paragraphs (Indonesian Version) | Videos |
| 830 | Journalistic Video Tutorial Episode 5: Creating a Writing Outline (Indonesian Version) | Videos |
| 831 | Journalistic Video Tutorial Episode 4: Interview (Indonesian Version) | Videos |
| 832 | Journalistic Video Tutorial Episode 3: Research and Reporting (Indonesian Version) | Videos |
| 833 | Video Journalism Tutorial Episode 2: Newsworthy Criteria (Indonesian Version) | Videos |
| 834 | Video Journalism Tutorial Episode 1: Ideas and Angles (Indonesian Version) | Videos |
| 835 | KPP Video Toolkit: Video 5 – Knowledge Intermediaries (Indonesian Version) | Videos |
| 836 | KPP Video Toolkit: Video 4 – How Groups of People Get Together and Use Evidence and Knowledge (Indonesian Version) | Videos |
| 837 | KPP Video Toolkit: Video 4 – How Groups of People Gather and Use Evidence and Knowledge | Videos |
| 838 | KPP Video Toolkit: Video 2 – Types of Knowledge Used in the Policy Process (Indonesian Version) | Videos |
| 839 | KPP Video Toolkit: Video 3 – Political Context (Indonesian Version) | Videos |
| 840 | KPP Video Toolkit: Video 3 – The Political Context | Videos |
| 841 | KPP Video Toolkit: Video 1 – Introduction to Knowledge for Policy (Indonesian Version) | Videos |
| 842 | KPP Video Toolkit: Video 2 – Types of Knowledge Used in the Policy Process | Videos |
| 843 | KPP Video Toolkit: Video 1 – Introduction to Knowledge into Policy | Videos |
| 844 | Dr. Fenny M. Dwivany | Videos |
| 845 | Prof. Sangkot Marzuki | Videos |
| 846 | Dr Jim Peacock | Videos |
| 847 | Roby Muhammad (Part 1) | Videos |
| 848 | Roby Muhammad (Part 2) | Videos |
| 849 | Professor David Cooper | Videos |
| 850 | Professor Ove Hoegh Gulberg | Videos |
| 851 | Professor Jamaluddin Jompa | Videos |
| 852 | Professor Herawati Sudoyo | Videos |
| 853 | Smart Practices for BUMDes in Lendang Nangka Clean Water Management (Indonesian Version) | Videos |
| 854 | Talangagung Educational Landfill Tourism: A Smart Practice (Indonesian Version) | Videos |
| 855 | The Role of Research in the Policy Making Process (Indonesian Version) | Videos |
| 856 | Infographic Animation: Indonesian Science Fund (Indonesian Version) | Videos |
| 857 | Data Innovation for Policy Makers Conference 2014 | Videos |
| 858 | Four Scenarios for the Future of Indigenous Peoples 2025 (Indonesian Version) | Videos |

## D.	List of knowledge exchange activities in KSI Phase 2

This annex provides the list of knowledge exchange activities in KSI Phase 2.

Table D.1 provides a summary of the KSIxChange, KSI4RDI, Road to IDF, STI Series, and K2P Conference events between 2018 and 2022, and Figure D.1 shows the participant composition in the 42 KSIxChange events.

Table D.1.	Knowledge exchange activities in KSI Phase 2

| Type of event | 2018 | 2019 | 2020 | 2021 | 2022 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| KSIxChange | 6 | 11 | 14 | 9 | 3 | 42 |
| KSI4RDI | 0 | 0 | 12 | 7 | 0 | 19 |
| Road to IDF | 6 | 7 | 11 | 13 | 0 | 37 |
| K2P Conference | 0 | 0 | 0 | 0 | 1 | 1 |
| STI series | 0 | 0 | 0 | 6 | 0 | 6 |

Figure D.1.	KSIxChange Participation

List of knowledge exchange activities in KSI phase 2

KSIxChange, KSI4RDI, Road to IDF, and STI Series events that took place during KSI phase 2.

- Knowledge Exchange: KSIxChange (Open for public, managed by KSI)

| No | Date | Event/Activity Title | Number of Attendance (Zoom) | Views (YT/FB/IG) | Post-Livestream Link |
| --- | --- | --- | --- | --- | --- |
| 1 | Thursday, 02 August 2018 | KSIxChange: Inclusive Economic Development Index: Measuring Challenges of National Development Planning | 31 | 721 | https://www.facebook.com/iddevforum/videos/1078685155619489/ |
| 2 | Monday, 27 August 2018 | KSIxChange#2: Athena SWAN: Opportunities and Challenges for Gender Equality in Indonesia's Higher Education Sector | 49 | 111 | https://www.facebook.com/iddevforum/videos/2168458623250313/ |
| 3 | Wednesday, 19 September 2018 | KSIxChange#3: 'Swakelola Tipe III' Working Together to Deliver Services: Opportunities and Challenges for CSOs and Governments Part I (Introduction) | 55 | 118 | https://www.facebook.com/iddevforum/videos/235482027316623/ |
| 4 | Thursday, 27 September 2018 | KSIxChange#4: Book Launch: "Local Knowledge Matters: Power, Context, and Policymaking in Indonesia" | 38 | 508 | https://www.facebook.com/iddevforum/videos/337348867020258/ https://www.facebook.com/iddevforum/videos/458234178031374/ |
| 5 | Tuesday, 9 October 2018 | KSIxChange#5: 'Swakelola Tipe III' Working Together to Deliver Services: Opportunities and Challenges for CSOs and Governments Part II (Best Practices) | 42 | 206 | https://www.facebook.com/iddevforum/videos/155066242104169/ |
| 6 | Thursday, 13 December 2018 | KSIxChange#6: Advocating Your Issue to Policymaker | 31 | 97 | https://www.facebook.com/iddevforum/videos/207681506781038/ https://www.facebook.com/iddevforum/videos/363855477721942/ https://www.facebook.com/iddevforum/videos/316792438936472/ |
| 7 | Thursday, 17 January 2019 | KSIxChange#7: Making Research Inclusive: Listening to The Voices of People with Disability | 57 | 380 | https://www.facebook.com/iddevforum/videos/354715508593151/ |
| 8 | Friday, 22 February 2019 | KSIxChange#8: Women in the Bureaucracy: Affirmative Action vs a Merit System | 72 | 51 | https://www.facebook.com/iddevforum/videos/988706074663933/ https://www.facebook.com/iddevforum/videos/604859153320070/ |
| 9 | Tuesday, 26 March 2019 | KSIxChange#9: Evaluation of the National Health Insurance's Road Map | 80 | 0 | No link |
| 10 | Thursday, 02 May 2019 | KSIxChange#10: Improving The Impact of Your Research on Policy: Suggestions, Opportunities, and Challenges | 29 | 250 | https://www.facebook.com/iddevforum/videos/179733316244456/ |
| 11 | Tuesday, 07 May 2019 | KSIxChange#11: Linking Research Agenda with Cultural Progress | 51 | 219 | https://www.facebook.com/iddevforum/videos/665118507267766/ |
| 12 | Thursday, 20 June 2019 | KSIxChange#12:The Frailties of Indonesian Knowledge Production: A critical reflection of civil society and knowledge production during Orde Baru and Reformasi | 18 | 227 | https://www.facebook.com/iddevforum/videos/462173737876587/ |
| 13 | Tuesday, 24 September 2019 | KSIxChange#13: Doing Research: Assessing Social Science Research System in Indonesia | 55 | 305 | https://www.facebook.com/iddevforum/videos/385849415429619/ |
| 14 | Tuesday, 19 November 2019 | KSIxChange#14: Communicate Your Science! | 70 | 682 | https://www.facebook.com/iddevforum/videos/2449909175230956/ |
| 15 | Tuesday, 26 November 2019 | KSIxChange#15: Self-Managed Procurement Type III – Internal Socialization in Bappenas | 52 | 0 | No link |
| 16 | Friday, 13 December 2019 | KSIxChange#16: Multisector Collaboration to Support Policy-Based Research | 90 | 124 | https://www.facebook.com/iddevforum/videos/589560678280548/ |
| 17 | Wednesday, 05 February 2020 | KSIxChange#17: Behaviour-Based Intervention in Policy Formulation: Best Practices of the Directorate General of Taxes and Social Security Provider (BPJS Ketenagakerjaan) in Improving the Quality of Public Services | 52 | 148 | https://www.facebook.com/iddevforum/videos/197001851701384/ |
| 18 | Monday, 23 March 2020 | KSIxChange#18: COVID-19 and Social Economic Impacts for Marginalised Groups | 193 | 0 | https://www.youtube.com/watch?v=mgdQ6Eh6c_s |
| 19 | Tuesday, 31 March 2020 | KSIxChange#19: The Role of Think Tank in Handling COVID-19 | 191 | 207 | https://www.youtube.com/watch?v=QfN5UojAEFA&t=38s |
| 20 | Monday, 13 April 2020 | KSIxChange#20: Recommendations on the Implementation of Social Safety Net Policies for Marginal Groups Affected by COVID-19 | 490 | 5,529 | https://www.youtube.com/watch?v=SCr4xBP1c-4&t=1051s |
| 21 | Tuesday, 28 April 2020 | KSIxChange#21: Importance of Guarding the Personal Data Protection Bill | 201 | 659 | https://www.youtube.com/watch?v=0qTjgVlA5ks&t=733s |
| 22 | Thursday, 14 May 2020 | KSIxChange#22: COVID-19 Impact for Industrial Sector | 347 | 4,418 | https://www.youtube.com/watch?v=piC1kyUdfiE&t=250s |
| 23 | Thursday, 4 June 2020 | KSIxChange#23: Development Cooperation in the New Normal | 1328 | 7,024 | https://www.youtube.com/watch?v=iTh_r4IdgDM&t=6976s |
| 24 | Tuesday, 30 June 2020 | KSIxChange#24: Alignment of COVID-19 Pandemic Research for a Sustainable and Inclusive Policy Making Process | 509 | 196 | No link |
| 25 | Thursday, 23 July 2020 | KSIxChange#25: Challenges of Budget Transparency and Fiscal Policy Synchronisation in Tackling COVID-19 in Indonesia | 515 | 7,866 | https://www.youtube.com/watch?v=Bc-63Zov3JI&t=308s |
| 26 | Thursday, 30 July 2020 | KSIxChange#26: The Urgency of Institutionalisation and Implementation of Socio-Economic Policies for People with Disabilities in COVID-19 Pandemic Era | 170 | 392 | https://www.youtube.com/watch?v=FdIZKQljJFc&t=14s |
| 27 | Thusday, 27 August 2020 | KSIxChange#27: Data-Based Decision Making in Tackling COVID-19 | 674 | 7,552 | https://www.youtube.com/watch?v=fCx2Yo7vk34&t=2395s |
| 28 | Tuesday, 29 September 2020 | KSIxChange#28: Effectiveness of Rapid Research in Tackling COVID-19 | 282 | 5,370 | https://www.youtube.com/watch?v=cCFZVlF98KI&t=25s |
| 29 | Tuesday, 27 October 2020 | KSIxChange#29: Regeneration Challenges and Revitalisation Efforts in the Agricultural Sector Amid the COVID-19 Pandemic | 179 | 4,251 | https://www.youtube.com/watch?v=EItU9JzGMh0&t=19s |
| 30 | Wednesday, 02 December 2020 | KSIxChange#30: The Role of Disabled Persons Organisation in Post-COVID-19 Development | 143 | 5,505 | https://www.youtube.com/watch?v=AxTs_0NNQfc&t=6s |
| 31 | Tuesday, 09 March 2021 | KSIxChange#31: Challenges Women Researchers Face during the COVID-19 Pandemic | 192 | 439 | https://www.youtube.com/watch?v=B8nAgYRAi-U&t=29s |
| 32 | Tuesday, 23 March 2021 | KSIxChange#32: Challenges and Reality of COVID-19 Vaccination Policy in Indonesia | 181 | 2,179 | https://www.youtube.com/watch?v=82bYZf1m5Hk&t=534s |
| 33 | Tuesday, 25 May 2021 | KSIxChange#33: Challenges and Reccomendations in Communicating Social Science Research for Policy-Making Process | 155 | 6,066 | https://www.youtube.com/watch?v=Z6m2YM_54AU |
| 34 | Tuesday, 29 June 2021 | KSIxChange#34: Knowledge Collaboration Between Litbangjirap and Think Tanks in Social Science and Humanites | 195 | 473 | https://www.youtube.com/watch?v=eBtNO1JmUVQ&t=614s |
| 35 | Thursday, 26 August 2021 | KSIxChange#35: The Importance of Policy Innovation for Optimising Regional Potential | 165 | 3,455 | https://www.youtube.com/watch?v=tq3OCXQvNcI&t=153s |
| 36 | Tuesday, 21 September 2021 | KSIxChange#36: ALMI Scientist Series “How Humanities and Social Sciences Can Play a Role in Protecting the Vulnerable Groups During COVID-19 Pandemic?" | 160 | 436 | https://www.youtube.com/watch?v=VTmwJ4TwKHg&t=6s |
| 37 | Tuesday, 26 October 2021 | KSIxChange#37: A New Dimension of Partnership Between Government and CSOs: Lessons Learned from The Self-Managed Procurement Type III | 128 | 3,127 | Dimensi Baru Kemitraan Pemerintah & Organisasi Kemasyarakatan: Pembelajaran dari Swakelola Tipe III - YouTube |
| 38 | Tuesday, 16 November 2021 | KSIxChange#38: ALMI Special Scientis Series "Internalising GEDSI Perspectives and Institutionalising Research Ethical Clearance" | 203 | 2,434 | https://www.youtube.com/watch?v=oI6Eu2-uym4&t=12s |
| 39 | Thursday, 2 December 2021 | KSIxChange#39: Stregthening Disability Inclusion in Knowledge to Policy Process | 118 | 2,581 | https://www.youtube.com/watch?v=iVper0O3TYo&t=220s https://www.youtube.com/watch?v=OeiGpUDEfWM&t=250s |
| 40 | Thursday, 20 January 2022 | KSIxChange#40: Potential Collaboration Between Research Institute and Policymakers to Promote Evidence-Informed and Inclusive Policymaking Process | 227 | 2,356 | https://www.youtube.com/watch?v=DVGaELgE3qg&t=4331s |
| 41 | Tuesday, 08 March 2022 | KSIxChange#41: Breaking the Bias and Achieving Gender Equality | 300 | 418 | https://www.youtube.com/watch?v=xcO_o9w0mh4 |
| 42 | Thursday, 14 April 2022 | KSIxChange#42: The Launch of Development Planning Knowledge Management (MP3) | 404 | 553 | https://www.youtube.com/watch?v=-ghGtTJKmYI |

- Knowledge Exchange: KSI4RDI (Close invited-event & managed by KSI)

| No | Date | Event/Activity Title | Number of Attendance (Zoom) | Views (YT/FB/IG) | Post-Livestream Link |
| --- | --- | --- | --- | --- | --- |
| 1. | Wednesday, 6 Mei 2020 | KSI4RDI#1: Indonesian Diaspora Innovation Research Funding in the Socio-Economic Sector in Handling COVID-19 Pandemic | 226 | 0 | No link |
| 2. | Wednesday, 20 May 2020 | KSI4RDI#2: Enriching Innovation Research Ideas with Integrated Socio-Ecological Aspects in Handling COVID-19 Pandemic | 30 | 0 | No link |
| 3. | Tuesday, 28 July 2020 | KSI4RDI#3: Serial Discussions of the COVID-19 Pandemic Research, Cluster 1: Development of the National Health System | 44 | 0 | No link |
| 4. | Tuesday, 19 August 2020 | KSI4RDI#4: GESI Streamline: Why is the Gender Equality approach Important in Research? (1st Session) | 78 | 314 | https://www.youtube.com/watch?v=Sp2BU8xbBE4&t=1s |
| 5. | Monday, 24 August 2020 | KSI4RDI#5: Serial Discussions of the COVID-19 Pandemic Research, Cluster 2: Improving the Quality of Education and Religious Services in Response to the Impact of COVID-19 | 66 | 0 | No link |
| 6. | Friday, 2 September 2020 | KSI4RDI#6: GESI Streamline: Why is the Gender Equality Approach Important in Research? (2nd Session) | 94 | 264 | https://www.youtube.com/watch?v=AzjMtKn9SWQ&t=11s |
| 7. | Tuesday, 22 September 2020 | KSI4RDI#7: GESI Streamline: Practical Tools in Incorporating GESI Perspectives in Research (3rd Session) | 76 | 56 | https://www.youtube.com/watch?v=58v9v0CRG_Q&t=11s |
| 8. | Wednesday, 30 September 2020 | KSI4RDI#8: Serial Discussions of the COVID-19 Pandemic Research, Cluster 2: Reviewing the Implementation of Curriculum in Special Conditions in Education Units | 124 | 0 | No link |
| 9. | Thursday, 8 October 2020 | KSI4RDI#9: Serial Discussions of the COVID-19 Pandemic Research, Cluster 1: Community Empowerment in the National Health System (SKN) Aspect in the Pandemic Era | 52 | 0 | No link |
| 10. | Wednesday, 9 October 2020 | KSI4RDI#10: Serial Discussions of the COVID-19 Pandemic Research, Cluster 3: National Health System Knowledge Management for COVID-19 Data Analysis | 66 | 0 | No link |
| 11. | Wednesday, 4 November 2020 | KSI4RDI#11: Following Up the Job Creation Law in the Context of Planning and Development | 49 | 0 | No link |
| 12. | Thursday, 19 November 2020 | KSI4RDI#12: GESI Streamline: Formulation of Lessons Learned and Practical Guide to Incorporating GESI Perspectives in Research (4th Session) | 37 | 42 | https://www.youtube.com/watch?v=-XCm3eG7RQY |
| 13 | Tuesday, 18 March 2021 | KSI4RDI#13: GEDSI Coalition: Sustainability Strategy to Mainstream GEDSI Perpective in Research and Community Services | 23 | 0 | No link |
| 14 | Friday, 23 April 2021 | KSI4RDI#14: GEDSI Coalition: Sustainability Strategy to Mainstream GEDSI Perpective in Research and Community Services | 20 | 0 | No link |
| 15 | Friday, 28 May 2021 | KSI4RDI#15: GEDSI Coalition: Sustainability Strategy to Mainstream GEDSI Perpective in Research and Community Services | 13 | 0 | No link |
| 16 | Thursday, September 30, 2021 | KSI4RDI#16: Extreme Poverty from Low-Carbon Development Aspects (with PAKK Bappenas) | 19 | 0 | No link |
| 17 | Friday, October 15, 2021 | KSI4RDI#17: Optimalisation The Role of JFAK in Bappenas | 15 | 0 | No link |
| 18 | Thursday, November 4, 2021 | KSI4RDI#18: Optimalisation The Role of JFAK in Bappenas | 15 | 0 | No link |
| 19 | Thursday, November 11, 2021 | KSI4RDI#19: Optimalisation The Role of JFAK in Bappenas | 21 | 0 | No link |

- Knowledge to Policy Conference (Open for public, managed by KSI)

| No | Date | Event/Activity Title | Number of Attendance (Zoom) | Views (YT/FB/IG) | Post-Livestream Link |
| --- | --- | --- | --- | --- | --- |
| 1 | Tuesday, March 22 – Wednesday, March 23, 2022 | Knowledge to Policy Conferece | 768 | 4,586 | https://www.youtube.com/playlist?list=PLaIynhfvv0kjGznCzcdaQdP-zpo0jCXfm |

- Road to IDF (Open for public, managed by Bappenas & supported by KSI)

| No | Date | Event/Activity Title |  | Number of Attendance (Zoom) |  | Views (YT/FB/IG) |  | Post-Livestream Link |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Tuesday, May 8, 2018 | RIDF 2018: Growth Centers Development: Challenges, Good Practices, and Basic Services Improvement to Reduce Economic Gaps and Optimize Development Funding |  | 53 |  | 0 |  | No link |  |
| 2 | Tuesday, May 22, 2018 | RIDF 2018: Innovation in Governance and Regional Development |  | 135 |  | 0 |  | No link |  |
| 3 | Wednesday, May 30, 2018 | RIDF 2018: Growth Centers Development: Challenges and Good Practices of Governance and Regional Development Innovation to Strengthen Indonesian Connectivity |  | 193 |  | 0 |  | No link |  |
| 4 | Thursday, May 31, 2018 | RIDF 2018: Efforts to Reduce The Disparity of Disadvantaged Areas and Borders, Strengthening Indonesian Connectivity as an Archipelago, Improve Basic Services To Reduce Regional Gaps |  | 172 |  | 0 |  | No link |  |
| 5 | Tuesday, May 8, 2018 |  | RIDF 2018: FKP: Towards More Inclusive Development of South Sulawesi |  | 0 |  | 0 |  | No link |  |
| 6 | Tuesday, May 8, 2018 |  | RIDF 2018: Diskusi Lingkar Temu Kabupaten Lestari (LTKL) |  | 0 |  | 0 |  | No link |  |
| 7 | Thursday, February 21, 2019 |  | RIDF 2019: TVET Reform Seminar for Future Work and Improve the Investment Climate for Job Creation |  | 58 |  | 0 |  | No link |  |
| 8 | Thursday, March 21, 2019 |  | RIDF 2019: Accelerate Economic Structural Transformation Seminar for TVET Reform, Create Inclusive Employment Opportunities, and Foster Social Enterprises |  | 141 |  | 0 |  | No link |  |
| 9 | Wednesday, April 24, 2019 |  | RIDF 2019: Improving the Investment Climate for Job Creation, Developing Global Competitive MSMes, Fostering Social Enterprises, and Developing Local Talents and Markets |  | 154 |  | 0 |  | No link |  |
| 10 | Thursday, May 23, 2019 |  | RIDF 2019: Discuss Regional Policy Issues for IDF 2019 |  | 46 |  | 0 |  | No link |  |
| 11 | Saturday, June 22, 2019 |  | RIDF 2019: Room E: The Future is Us |  | 52 |  | 0 |  | No link |  |
| 12 | Tuesday, June 25, 2019 |  | RIDF 2019: Matchmaking with Saraswati |  | 70 |  | 0 |  | No link |  |
| 13 | Wednesday, June 26, 2019 |  | RIDF 2019: Creating Common Benefits for Healthier Future |  | 51 |  | 0 |  | No link |  |
| 14 | Friday, May 29, 2020 |  | IG Live RIDF 2021: Potential and Challenges of the Fashion Industry in Supporting IKM and Creative Economy with Didiet Maulana |  | 487 |  | 113 |  | https://www.instagram.com/tv/CAJ_x_7HP0E/ |  |
| 15 | Wednesday, July 29, 2020 |  | RIDF Webinar 2021: Prospects for Industrial Recovery With Levers of Superior Industrial Subsectors and Industrial Zone Development |  | 786 |  | 5,000 |  | https://www.youtube.com/watch?v=4pe7nmL-ezE |  |
| 16 | Tuesday, September 8, 2020 |  | RIDF Webinar 2021: The Prospect of Economic Recovery of Small and Medium Industrial Sectors (IKM) |  | 762 |  | 3,580 |  | https://www.youtube.com/watch?v=FGrBfaPVHM0 |  |
| 17 | Thursday, September 10, 2020 |  | IG Live RIDF 2021: The Role of Research for Industrial Revitalization In The Middle of The Pandemic With Edbert Gani |  | 490 |  | 1,004 |  | https://www.instagram.com/tv/CE9LUh-BLHQ/ |  |
| 18 | Wednesday, September 23, 2020 |  | Talkshow #1 Road to IDF 2021: Industry Revitalization for Pandemic Mitigation |  | 0 |  | 1,101 |  | https://www.youtube.com/watch?v=jAUStqo6PRM |  |
| 19 | Thursday, September 24, 2020 |  | IG Live RIDF 2021: Encouraging Small Medium Industries Up Class Through Crowdfunding with Heinrich Vincent |  | 150 |  | 372 |  | https://www.instagram.com/tv/CFgvhzwlYul/ |  |
| 20 | Wednesday, October 14, 2020 |  | RIDF Webinar 2021: Prospect of Economic Recovery of the National Automotive Industry Sector |  | 374 |  | 1,800 |  | https://www.youtube.com/watch?v=psPeJPYQ3VY |  |
| 21 | Monday, November 23, 2020 |  | IG Live RIDF 2021: Automotive Modification Industry Strategy In Dealing With The Pandemic Impact With Andre Mulyadi |  | 270 |  | 264 |  | https://www.instagram.com/tv/CH7ptw7FZ_U/ |  |
| 22 | Tuesday, November 24, 2020 |  | RIDF Webinar 2021: Inovasi Industri dalam Mendorong Pemulihan Ekonomi Nasional |  | 264 |  | 849 |  | https://www.youtube.com/watch?v=dje4LZECbYQ |  |
| 23 | Friday, November 27, 2020 |  | Talkshow #2 Road to IDF 2021: Industrial Innovation In Encouraging The Recovery of The National Economy |  | 0 |  | 4,103 |  | https://www.youtube.com/watch?v=YJfxjVph1AQ |  |
| 24 | Wednesday, December 16, 2020 |  | University Lecture #1 Road to IDF 2021: The Important Role of Indonesian Young Entrepreneurs in Encouraging Economic Recovery |  | 400 |  | 443 |  | https://www.youtube.com/watch?v=a04493taaZ0 |  |
| 25 | Thursday, January 14, 2021 |  | Instagram Live #5 Road to IDF 2021: The Role of Industrial Technology Innovation In Indonesia |  | 0 |  | 1,276 |  | https://www.instagram.com/tv/CKBbRoXsoem/?utm_medium=copy_link |  |
| 26 | Friday, April 16, 2021 |  | Youtube Series: Meet the Leader Marthella Sirait: Inclusive Indonesia |  | 0 |  | 1,131 |  | Youtube Series Meet the Leader: Marthella Sirait - Koneksi Indonesia Inklusif - YouTube |  |
| 27 | Wednesday, April 28, 2021 |  | Bincang Santai IDF: Get to Know of IDF |  | 350 |  | 658 |  | No link |  |
| 28 | Wednesday, May 5, 2021 |  | University Lecture #2 Road to IDF 2021: Industrialization Strategies to Encourage Economic Transformation |  | 500 |  | 2,219 |  | https://youtu.be/Q1ozGapXo9c |  |
| 29 | Tuesday, June 29, 2021 |  | IDF 2021 Inspiring Session |  | 1,168 |  | 2,733 |  | https://youtu.be/uk6_Y3FpiEo |  |
| 30 | Thursday, July 22, 2021 |  | University Lecture #3 Road to IDF 2021: Industrial Zone Development Strategies and Special Economic Zones to Encourage Equal Distribution of New Economic Centers |  | 767 |  | 1,690 |  | https://youtu.be/vi0yJDfFcYM |  |
| 31 | Tuesday, September 28, 2021 |  | Road to IDF 2021: Kick Off Workshop SEED Policy Lab for Sustainable Procurement (PLSP) |  | 91 |  | 188 |  | No link |  |
| 32 | Tuesday, October 5, 2021 |  | Road to IDF 2021: Workshop SEED Policy Lab for Sustainable Procurement (PLSP) Day 1 |  | 56 |  | 0 |  | No link |  |
| 33 | Wednesday, October 6, 2021 |  | Road to IDF 2021: Workshop SEED Policy Lab for Sustainable Procurement (PLSP) Day 2 |  | 64 |  | 0 |  | No link |  |
| 34 | Thursday, October 7, 2021 |  | Road to IDF 2021: Workshop SEED Policy Lab for Sustainable Procurement (PLSP) Day 3 |  | 53 |  | 0 |  | No link |  |
| 35 | Monday, October 18, 2021 |  | Road to IDF 2021: Hackathon Co-Creation Workshop SEED Policy Lab for Sustainable Procurement (PLSP) |  | 54 |  | 0 |  | No link |  |
| 36 | Wednesday, November 17, 2021 |  | Road to IDF 2021: Webinar Launch Book of Indonesian Manufacturing Study 2021 |  | 155 |  | 519 |  | No link |  |
| 37 | Wednesday, December 8, 2021 |  | Road to IDF 2021: Gender Insights and Digital UMKM Capabilities in Indonesian E-Commerce Use |  | 124 |  | 252 |  | No link |  |

- STI Policy Lecture Series (Open for public, managed by BRIN, KSI)

| No | Date | Event/Activity Title | Number of Attendance (Zoom) | Views (YT/FB/IG) | Post-Livestream Link |
| --- | --- | --- | --- | --- | --- |
| 1 | Tuesday, 12 October 2021 | Seri I ¦ STI Policy Lecture Series 2021 "Public Policy: Theory and Practice " | 756 | 1,399 | https://www.youtube.com/watch?v=N0cSo3ZJh9g&t=267s |
| 2 | Tuesday, 26 October 2021 | Seri II ¦ STI Policy Lecture Series 2021 "The Concept of Science And Technology Policy" | 594 | 638 | https://www.youtube.com/watch?v=lEarTa_q46I&t=26s |
| 3 | Tuesday, 9 November 2021 | Seri III ¦ STI Policy Lecture Series 2021 "Evidence-Based Policy Formulation" | 464 | 450 | https://www.youtube.com/watch?v=1QFbuPPE6V0&t=8772s |
| 4 | Tuesday, 23 November 2021 | Seri IV ¦ STI Policy Lecture Series 2021 "Practices Of Science and Technology Policies In Malaysia and Indonesia" | 349 | 1,148 | https://youtu.be/BiDNeOao5X4 |
| 5 | Tuesday, 7 December 2021 | Seri V ¦ STI Policy Lecture Series 2021 "Industrial Innovation Practices In The United States And Indonesia" | 211 | 294 | https://www.youtube.com/watch?v=JI_SaWrYVU8&t=4069s |
| 6 | Tuesday, 21 December 2021 | Seri VI ¦ STI Policy Lecture Series 2021 "Innovation Ecosystem In The UK and Indonesia" | 379 | 1,785 | https://youtu.be/ZHZvQnyNMCk |

## E.	List of PR Value from media engagement activities

This annex provides the list of media engagement activities (i.e. articles, infographics, op-eds, etc.) by date, with the type of media engagement, author, the headline and URL link, and the public relations (PR) value..

Table E.1 provides a summary by year of the media engagement activities, and their total PR Value. Between January 2019 and April 2022, the generated PR Value is estimated to be IDR 52.92 billion.

Table E.1. 	KSI media engagement activities, 2019–2022

| Type of media |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| engagement activity | # | PR Value | # | PR Value | # | PR Value | # | PR Value | # | PR Value |
| Article | 3 | 180.00 | 64 | 3,555.54 | 34 | 2,026.00 | 0 | 0 | 101 | 5,761.54 |
| Article/ Newsjacking | 0 | 0 | 0 | 0 | 18 | 870.00 | 0 | 0 | 18 | 870.00 |
| Infographic | 5 | 300.00 | 5 | 300.00 | 3 | 180.00 | 0 | 0 | 13 | 780.00 |
| Microsite / Longform | 1 | 60.00 | 1 | 60.00 | 2 | 120.00 | 0 | 0 | 4 | 240.00 |
| News Coverage | 84 | 4,273.98 | 60 | 2,840.88 | 295 | 13,571.55 | 444 | 18,829.38 | 883 | 39,515.79 |
| Op-Ed | 6 | 1,706.16 | 13 | 2,205.80 | 6 | 791.25 | 0 | 0 | 25 | 4,703.21 |
| Public Event | 1 | 60.00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 60.00 |
| Special Report | 0 | 0 | 1 | 828.00 | 0 | 0 | 0 | 0 | 1 | 828.00 |
| Video | 0 | 0 | 1 | 163.08 | 0 | 0 | 0 | 0 | 1 | 163.08 |
| Total | 100 | 6,580.14 | 145 | 9,953.30 | 358 | 17,558.80 | 399 | 18,829.38 | 1,047 | 52,921.62 |

PR values in IDR millions

## F.	Infographics of high-level webinars

## G.	List of policy changes influenced by PRIs (2018-2021)

2018

- Article 33 - Relaxing of a moratorium to enable more teachers to be hired

- AKATIGA – Head of National Public Procurement Agency No 8/ 2018 on self-managed procurement

- KPPOD – Ministry of Workforce Regulation No. 106/2018 on National Competency Standards for Policy Analysts

- KPPOD – State Administration Agency’s Policy Quality Index (Indeks Kualitas Kebijakan, IKK)

- SMERU - Bappenas’ Inclusive Economy Index*

- SurveyMETER - Bali Regional Regulation (Perda) 11/2018 mandating the provincial and district governments in Bali to establish elderly friendly areas*

2019

- PSHK - Law No.15/ 2019 on how regulations are made in Indonesia

2020

- IRE – Village law implementation in RPJMN 2020-2024

- KPPOD – The Job Creation Act No 11/ 2020 on the division of national and sub-national roles related to business licencing.

- PSHK – Regulatory reform in RPJMN 2020-2024

- PUSAD Paramadina - Database of Religious Harmony Forum adopted by Ministry of Religious Affairs*

- PPIM UIN – Decree of the Minister of Education and Culture Number 958/P/2020 concerning Learning Achievement for Primary and Secondary Education

- SMERU – inclusive development included as a priority in the RPJMN*

- SMERU - Minister of Education Regulation No.719/ 2020 on Guidance of Curriculum Implementation during Special Times*

- SurveyMETER – Nganjuk District Head Regulation No. 3/ 2020 supporting the APBDes to fund roll-out of stunting database in 20 Sub Districts*

2021

- KPPOD – Government Regulation No. 6/ 2021 on Implementing Business Licensing in the Region*

- KPPOD – Government Regulation No. 5/ 2021 on Implementing Risk Based Business Licensing and

- KPPOD – Government Regulation No. 10/ 2021 on Regional Tax and Regional Retribution for ease and services for business licensing in the region

- IRE - Sindangagung village budget allocation for women’s group*

- IRE – Karangrejo village budget allocation women and spices farmer groups*

- IRE – Regional Regulation No.4/ 2021 on RPJMD Gunung Kidul

- IRE – Regional Regulation No. 3/ 2021 on RPJMD Sleman

- PKMK – PKMK’s website embedded in the Ministry of Health‘s Crisis Centre website

- ELSAM – President Regulation No. 53/ 2021 on National Action Plan on Human Rights*

- FITRA – South Sulawesi Government fund CSOs to conduct research activity through Swakelola Tipe III procurement model.

- PPIM – National Education Standards Agency’s Islamic Religious Education Learning Focus guideline

- PPH Atma Jaya – Jakarta Health Office‘ Head Decision of No 609/2021 on Technical Guideline of Mental Health Service Management*

- AKATIGA – Kebumen District Head Regulation No 152/ 2021 on Fair Usage of Village Treasury Land*

- AKATIGA – Jatimulyo village Regulation No 3/ 2021 on Usage of Village Treasury Land*

- SurveyMETER – Revision of 2021 regional budget allocation in Yogyakarta for implementation of early childhood curriculum*

- Article 33 Indonesia – Standar Operating Procedure on Health Services for people with disabilities during the Pandemic in the Wajo District, South Sulawesi*

- SMERU - Revision of Implementation Guideline of Family Hopeful Program*

2022

- SurveyMETER – Decision Letter of Sleman Health Office No. 188/031/DKS/I/2022 on increased range of health screening and in addressing dementia for senior citizen*.

Note: (*) – Policy changes related to GEDSI issues

## H.	List of KSI Phase 2 evaluations, with summaries of findings

Over the course of KSI Phase 2, a total of 14 evaluations have been done. The table below indicates which EOPO or initiative these evaluations were connected to, the title of the evaluation, who or which company implemented it, what period the evaluation related to, and when the report was submitted.

| No | EOPO | Title of Evaluation | Sub-Contractor/ Consultant | Period of evaluation | Year of Reporting |
| --- | --- | --- | --- | --- | --- |
| 1 | EOPO 3 | Evaluation of the Indonesia Development Forum 2018 | Praxis | 2018 | 2019 |
| 2 | EOPO 1 | Bureaucratic Reform in Indonesia: Policy Analyst Experiences | ANU | 2015-2019 | 2020 |
| 3 | EOPO 1 | Evaluating the Use of the ‘Swakelola Tipe III’ Procurement Mechanism | Solidaritas | 2019 | 2020 |
| 4 | EOPO 3 | Evaluation of the Indonesia Development Forum (IDF) 2019 | Migunani | 2019 | 2020 |
| 5 | EOPO 5/ DFAT | Supporting the RPJMN: Approaches to strengthen evidence-informed policymaking | Karry McLaughlin |  | 2020 |
| 6 | EOPO 1 | Evaluating the use of the Swakelola Tipe III procurement mechanism in 2020 | Solidaritas | 2020 | 2021 |
| 7 | EOPO 2 | Evaluating the utilisation of GEDSI-sensitive research grant guidelines in universities | Isma Novitasari Yusadiredja | 2017 – 2020 | 2021 |
| 8 | EOPO 4 | Review KRISNA | Umi Hanik and Daan Patinassarany | 2021 | 2021 |
| 9 | EOPO 1 | Swakelola Tipe III – round 3 | Danang Widoyoko | 2021 | 2022 |
| 10 | EOPO 1 | Impact Study: JFAK Roles and Function in evidence-based policymaking | Nugroho Ananto and Narendra Prataksita | 2022 | 2022 |
| 11 | EOPO 3 | 2021 IDF Evaluation | Migunani | 2021 | 2022 |
| 12 | EOPO 5 | PRI Evaluation | OTT and Solidaritas | 2018 – 2021 | 2022 |
| 13 | Cross Cutting | K2P Pilot | Derry Pantjadarma and M. Nehru Sagena | 2022 | 2022 |
| 14 | Cross Cutting | Public Discourse | Astramaya | 2022 | 2022 |

In the sections below, summaries of the main findings of the independent evaluations are provided.

H.1 Evaluation of the Indonesia Development Forum (IDF) 2018

Completed in 2019

The main purpose of the evaluation was to assess the effectiveness of IDF2018 in achieving its expected outcomes. The evaluation adopted a mixed methods approach – utilising multiple qualitative methods alongside quantitative survey and social network analysis, to determine the effectiveness of IDF 2018 in achieving its objectives. Data collection and analysis took place in 2 phases, with cross-fertilisation and triangulation of findings across individual data collection methods.

The evaluation found strong evidence of contributions to knowledge-sharing between like-minded participants and across the sectors represented at the conference. There was some evidence of IDF 2018 contributing to collaboration across and within sectors including at the sub-national government level, in line with the theme of the conference. However, there was more evidence of IDF 2018 contributing to practice-based rather than policy outcomes at this level. Important gains were made by the conference organisers in terms of the number and diversity of participants at IDF 2018; and in terms of extending the reach of the conference to regional Indonesia and overseas. A total of 1,799 participants attended IDF 2018, which was an increase of around 25% from 2017. Only 17% of the domestic participants were from Jakarta, with the rest from across Indonesia, including 25% from sub-national government. 14% of participants were from international agencies.

During the Road to IDF events and at the conference, the organising committee through careful planning, abstract and speaker selection, managed to balance the agenda well and created a rich and diverse discussion environment. This created a dynamic of not only learning from others but also inspiration for participants to do better and replicate innovations across the country. 60% of participants surveyed at the conference and most participants interviewed subsequently, felt that they had gained new knowledge by attending IDF 2018.

Many respondents suggested that it was the cross-sector knowledge-sharing that made the conference a unique and beneficial experience. While some speakers and sessions were more popular than others, the diversity and range of participants, speakers, and topics meant that diverse expectations could be met. The participant survey showed that 68% of respondents agreed or strongly agreed with the statement: ‘the IDF was effective in enabling engagement between key players in the knowledge sector’.

The conference organisers also made positive efforts to make IDF2018 participatory and inclusive. Data and responses consistently suggested participants valued the participatory processes, particularly the panel-style presentations, used at the conference. KSI made valuable contributions in terms of promoting gender and disability inclusion. Slightly over one third of the participants were female and a similar proportion of speakers were women. The conference agenda included sessions on disability inclusive development, which were positively rated by participants.

Presentations on themes of innovation, digital economy, local governance and addressing regional inequality, were positively rated by participants at the conference; and there was considerable recall of these themes during Phase 2 of the evaluation, 6 months later.

There was evidence that IDF 2018 provided momentum to the interaction between likeminded participants and across stakeholder groups. All 33 sessions evaluated by facilitators indicated that participants were engaged, attentive to the speakers, and interested to dialogue on issues raised. The survey and SNA data showed strong evidence of cross-sector interaction at the conference and useful lessons for the future. Participants from the private sector were found to be more likely to build collaborations outside their sector than within their sector. However, university researchers, civil society organisations, and government individuals were more likely to build collaborations within their sector than with others.

Different session types contributed to different patterns of interaction between participants. For instance, some of plenary sessions successfully showcased innovations and inspirational speakers, many from local government. Whereas, the market place tended to encourage one-on-one interaction between speakers and presenters.

Post-conference, there were indications of participants following up on their intent to contact people they had met at IDF 2018. Sixty per cent of the participants interviewed indicated that they had contacted or been contacted by IDF participants, and this included existing colleagues as well as new people. The data suggests successful follow-ups were determined by the ability to make direct contact with participants at the conference; or draw on existing relationships to facilitate follow-up.

The evaluation found more evidence of knowledge-sharing and collaboration through IDF 2018 contributing to practice-based rather than policy outcomes. These practical outcomes included increased understanding of the need for collaboration resulting in changes in workplace practices, joint projects between participants, and the exchange of innovative products and technologies.

Benefits from IDF 2018 have included the successful showcasing of innovations and inspirational speakers, with evidence of uptake of the ideas presented. IDF 2018 successful identified and showcased ‘champions’ – particular individuals and innovations that were popular at the conference, and received further attention and validation from participants across sectors after the conference.

Successful engagement by the organising team of different Directorates within Bappenas contributed to further interaction within Bappenas on conference outcomes; and some evidence of further interaction (including with local government) was found within other line ministries.

Recommendations

- Strengthen data collection and monitoring through improved systems for collecting and storing participant data; and mobilisation of additional resources for participant survey and interviewing.

- Focus on continuity and learning in present IDF organisational structures, such as having at least 2 members from the previous IDF organising committee to provide institutional memory and advice (not necessarily in key organising roles), for the next team.

- Continue to resource Road to IDF events and strengthen synergies between these events and the main conference, including speaker selection.

- Strengthen the Call for Ideas/Papers campaign through more targeted publicity and communication content particularly in relation to universities and research institutes.

- Maximise gains from media coverage and contacts made over 2018 by continuing to share information via the IDF website and social media.

- Continue to emphasise gender, disability and sub-national representation irrespective of the conference theme, to maximise gains in terms of conference reach and influence.

- Review session formats to optimise the balance between knowledge sharing and relationship building, including appropriately facilitated ‘Initiate’ sessions on Day 2.

- Provide more information at the conference to enable all participants, including junior researchers or public servants to benefit from the full conference experience

- Create collaborative ‘spaces’ during and post-conference for IDF to have its desired impact on policy and cross-sectoral dialogue; and for participants to work through the sheer volume of input and implement more specific ideas or projects

- Develop strategies for private sector engagement such as private sector participants being part of panel presentations and contributing to conference follow-up plans.

- Build on the IDF2018 evaluation to track IDF’s ongoing influence including a participant survey at the next conference and follow-up interviews – of both IDF 2018 and IDF 2019 participants.

H.2 Bureaucratic Reform in Indonesia: Policy Analyst Experiences

Completed in 2020

This evaluation reviewed the recent experiences of different policy analyst cohorts since the role’s creation in 2015. It investigated these experiences to better understand the extent to which policy analysts were playing the role intended for them, and the factors enabling or inhibiting this. Consultations were held with 51 people in late 2018. They were policy analysts and supervisors across 20 government ministries and agencies, along with observers. The report also drew on a survey of the first cohort of trainees for the policy analyst position in 2015.

LAN played an active role in championing the creation and implementation of new policy analyst roles since early discussions regarding the position in 2014. As of 10 June 2019, there were 356 active policy analysts across 14 ministries, 13 government agencies and 30 local governments. More analysts have been trained and have met the criteria for appointment when positions become available or allocations are granted by KemenPAN-RB. Occasionally, trained policy analysts did not go on to take up appointments. For example, between late 2014 to October 2018, 21 analysts (or 10% of those trained at the time) did not continue because they switched back to structural positions, switched to other functional positions, pursued postgraduate study, or resigned from the civil service.

Recommendations

Based on respondents’ comments, the report made a number of recommendations for both KSI and LAN. Key recommendations (others are provided in the report) can be summarised as follows:

For LAN:

- Scale up planned coordination processes between LAN and the home agencies/ministries that build awareness and better understanding of policy analyst roles

- Facilitate or scale up further training for policy analysts once appointed

- Increase networking opportunities for policy analysts at the sub-national level

- Continue to support AAKI so it is better positioned to support policy analysts

- Continue to strengthen supervisors’ understanding of the new roles, including the importance of the credit system

- Run in-house training for supervisors, planning units and human resource units within workplaces.

For KSI:

- Continue to support LAN in the provision of further training for analysts, drawing on KSI’s own networks

- Support AAKI to provide: ‘fun’ social and learning activities for its current membership to build networks with external stakeholders; and to provide mentoring, short courses, information evenings and other informative seminars

- Support increased multi-disciplinary collaboration among policy analysts who work on similar policy issues, both at national and sub-national levels

- Support LAN to scale up the Policy Analysis for Indonesia (Analis Kebijakan Untuk Indonesia) awards system for policy analysts, co-hosting networking events in which the ceremonies are held

- Support LAN to distribute a newsletter or circular that showcases the work of policy analysts, for example a bulletin, online forum, etc.

- Support training for policy analysts’ supervisors in change management.

For LAN and KSI:

- Continue to focus on setting competency standards to create accurate ‘benchmarks’ for the role across the country. For example, organisations such as the Regional Autonomy Implementation Monitoring Committee (Komite Pemantauan Pelaksanaan Otonomi Daerah or KPPOD), the Centre for Strategic and International Studies (CSIS), the SMERU Research Institute, Synergy for Change (Pattiro) and AAKI are working on this through the Indonesian National Job Competency Standards (KKNI). LAN and KSI can assist with the mapping of this document and later the mainstreaming of it across the civil service.

H.3 Evaluating the Use of the ‘Swakelola Tipe III’ Procurement Mechanism

Completed in 2020

The Swakelola Tipe III (“self-management type III”) procurement mechanism was introduced in Peraturan Presiden nomor 16 tahun 2018 tentang Pengadaan Barang/Jasa Pemerintah (Presidential Decree number 16/2018 about government procurement of goods and services, hereafter ‘Perpres 16/2018’). This mechanism enables governments to directly contract organisasi kemasyarakatan (civil society organisations, hereafter “ormas”) to carry out activities. The inclusion of this mechanism in Perpres 16/2018 was at least in part due to advocacy by KSI together with a number of its partner PRIs. To understand the extent to which Swakelola Tipe III was being used and to learn from existing examples to improve socialisation and advocacy efforts related to procurement, in December 2019 KSI commissioned SOLIDARITAS to conduct an evaluation of existing Swakelola Tipe III data and known cases.

The evaluation was able to identify and confirm several cases of Swakelola Tipe III in 2018 and 2019. These included:

At least 8 Swakelola Tipe III contracts signed between PRIs affiliated with KSI (SMERU, IRE, ARTICLE 33, and CIPG) and various government institutions;

Four contracts between Yayasan Nusantara Sejati (YNS) and government institutions in Papua;

15 contracts between Universitas Gunadarma (a private university managed by a foundation) and various ministries and state agencies;

Four contracts between the Association of Indonesian Architects (Ikatan Arsitek Indonesia, AIA) and government institutions;

Multiple contracts between Kemendes PDTT (the Ministry of Villages, Development of Disadvantaged Regions, and Transmigration) and 2 different community organisations (Fatayat NU and Yayasan Alfa Omega) for the delivery of skills training in approximately 20 disadvantaged regions; and

Contracts between Lembaga Pendidkan dan Pelatihan Gurindam (an ormas based in Kepulauan Riau province) and 4 different government institutions for the provision of procurement training.

A limited number of Swakelola Tipe III activities planned for 2020 were also identified; however, these seem to have been significantly affected by the COVID-19 situation and are unlikely to proceed as planned.

The evaluation found that, based on the case studies, the main benefit of the Swakelola Tipe III mechanism has been to formalise and legitimise collaborative relationships between governments and ormas. For governments, Swakelola Tipe III provides a fit-for-purpose mechanism which can create time and cost efficiencies in comparison to the other methods available for contracting third parties prior to PerPres 16/2018.

The evaluation found that there were clear contributions by LKPP and KSI to all 4 of the cases investigated, and that LKPP and KSI provided support in 3 main ways: (1) by conducting socialisation events, (2) by providing general reference materials, and (3) by providing specific guidance/templates. The various socialisation events have increased awareness and knowledge of the mechanism, especially among PRIs, further complemented by the AKATIGA general reference materials.

The evaluation found that understanding the decision-making process the parties undertake when agreeing to Swakelola Tipe III contracts was key. Both the government institution and the ormas (informally) identify positives and negatives, consider their significance, and weigh them against each other. The Swakelola Tipe III contract will only go ahead if both parties conclude that the potential positives are likely to outweigh the potential negatives

The evaluation identified ways KSI and LKPP could further support the successful use of Swakelola Tipe III by focusing on:

- Improving and better targeting socialisation efforts

- Updating and expanding existing guidance for Swakelola Tipe III contracts and

- Developing a support system for organisations undertaking Swakelola Tipe III.

Recommendations

            - LKPP (with support from KSI and KSI’s PRI network as relevant) should: (a) develop a revised set of guidance documents (including examples of good practice and answers to frequently asked questions), (b) involve other relevant stakeholders, e.g. the Ministry of Finance and/or BPK in the development of the guidance to obtain their endorsement, and (c) consider how best to provide consultation services to parties with questions regarding the use of Swakelola Tipe III.

            - LKPP (with input from other government entities as relevant) should specify acceptable references for: (1) labour costs for ormas and (2) institutional fees to cover overhead costs within the Swakelola Tipe III guidance documents related to budget development. These references should reflect the actual or reasonable labour and overhead costs Indonesian ormas would incur when undertaking contracts for the government.

            - LKPP should update the Swakelola Tipe III guidance to clarify whether deliverables may be used as the basis for payments and what financial and administrative documents are necessary to support payment; to mitigate audit-related risks, such guidance should be developed in consultation with key stakeholders such as the Ministry of Finance (Directorate General of the Treasury) and BPK.

            - KSI and LKPP can use the organisational characteristics and the understanding of the potential positive and negative aspects of Swakelola Tipe III to better target and tailor socialisation efforts to focus on those organisations that are most likely to be interested in and have the ability to successfully carry out a Swakelola Tipe III contract.

            - KSI should support LKPP to map out the relevant business processes under 2 potential Swakelola Tipe III pathways (where the activity is collaboratively planned in the year prior to implementation, and where the government plans the activity without formal input from the ormas and only identifies a suitable ormas after plans for the activity have been approved) and provide appropriate guidance for both.

            - LKPP (with support from KSI) should develop additional guidance on (1) the level of justification required for direct appointments and (2) how to conduct a sayembara process (including timeline), with a focus on selecting proposals that represent the best value for money. This could include further consideration of whether a sayembara process should be mandatory above a certain proposed contract value.

            - LKPP (in coordination with other government entities and with support from KSI as relevant) should provide practical guidance to contracting parties on how to proceed in the event that implementation cannot be completed by the end of the financial year, including implications for payments and acquittal.

            - LKPP should clarify the role of the UKPBJ to include responsibility for providing technical advice and coordination of Swakelola Tipe III contracts, noting that this may involve additional assistance related to Swakelola Tipe III to ensure UKPBJ are able to play such a support role. KSI can support this process by identifying, documenting, and sharing examples of UKPBJ which play a role as a “center of excellence” in support of Swakelola Tipe III contracts.

            - In order to identify planned or actual cases of Swakelola Tipe III, LKPP and KSI should conduct follow-up data collection with participants of socialisation events (using contact information collected from participants), noting that this has the added benefit of keeping open lines of communication for consultation / further support. Additionally, KSI and/or LKPP should maintain a list of cases of Swakelola Tipe III (or a list of organisations that are using Swakelola Tipe III) similar to the example provided in Annex 4.

            - Where there is desire to improve SiRUP related to Swakelola Tipe III, LKPP could:

- clarify expectations related to the input of procurement packages planned to be implemented through Swakelola Tipe III

- modify the SiRUP data format specifically for Swakelola Tipe III to require the input of the name of the ormas (in the case where ormas are involved in the procurement planning stage) OR to specify that a particular ormas has not yet been identified (in the case where the government plans without input from the ormas, but intends to identify a suitable ormas as part of the preparation stage)

- add or modify SiRUP business processes to include a step to verify or spot-check data entry for Swakelola Tipe III.

            - KSI (together with its network of PRIs) should consider longer term advocacy related to the opening up of public procurement to ormas, including by sharing both international practice and the experience and perspectives of Indonesian CSOs.

H.4 Evaluation of the Indonesia Development Forum (IDF) 2019

Completed in 2020

The Indonesia Development Forum (IDF) is a platform for development practitioners in the public, private, and non-profit sectors to meet and exchange ideas. IDF has been convened annually by Bappenas since 2017 with support from the Knowledge Sector Initiative (KSI). The third IDF was launched on 29 January 2019 and was conducted on 22 – 23 July 2019 in Jakarta. The theme was Mission Possible: Seizing the Opportunities of Future Work to Drive Inclusive Growth.

At the IDF itself, the following achievements were documented:

- A clear majority of the participants (84%) reflected strong satisfaction with the event and appreciated the opportunity to engage with a range of actors linked to policy processes. In particular, nearly 3 out 4 participants (73%) showed satisfaction with the quality and relevance of research and evidence presented.

- A combination of interview data, case studies, surveys and observation by the evaluators show that GEDSI perspectives were operationalised and presented. This finding on GEDSI is acknowledged by all the respondents from organisations for people with disabilities.

- A positive perception on the value for money of the IDF was also reported by participants from different groups. A follow-up survey with the participants reported that almost all of the respondents (94.7%) are planning to attend IDF 2020.

- Both the participants and media coverage agree that IDF is growing steadily as a premiere development event in Indonesia. Media coverage by substance in 2019 is significantly higher than IDF 2018 (60% compared with 40% in 2018).

These all have contributed to high optimism by 89% of the participants on the potential to collaborate with other stakeholders. Follow-up interviews with participants after the IDF also show that a number of collaborations are happening, although some of them are still in early stages. In addition, as detailed in the case studies, IDF has contributed to policy processes through expanding policy capacities and broadening policy horizons; it is unrealistic to expect this two-day event to directly influence the content of policy as it is currently designed. However, there was some sense more could have been done after the IDF to facilitate exchange across interest groups and strengthen the dynamics between government, CSOs, and the business community that might lead to concrete collaborations.

Recommendations for improvement:

- Measuring policy uptake of the research and evidence presented during IDF.

- The evaluation proposed a framework for a systems perspective on measuring policy influence that factor in the policy processes that includes expanding policy capacities and broadening policy horizons as central contributions to policy processes. At the outcome level, while affecting policy regimes is an important form of knowledge uptake, the evaluation proposed to expand measurement to consider expanding policy capacities and broadening policy horizons as 2 other key dimensions of policy impact (Carden 2009).

- The strategic direction and purpose of the IDF and its targeting strategy need to be re-considered and communicated more effectively to potential attendees.

The evaluation suggested some alternative structures for the IDF that address not only the multiple agendas and interests in the IDF but also addresses the challenges of big, centralised events, for health, carbon footprint and economic as well as logistical reasons. They also help address the issues raised in our interviews around the importance of pre- and post-IDF or follow-up events. This recommendation assumed that provincial Bappeda would play a leading role but urge that broader engagement in the selection of topics, design of the events and delivery of the RIDF.

- Curation of participants, not only in terms of the private sector, but more broadly, would greatly assist the development of the IDF into a premiere event.

There is evidence across the knowledge sector that more pre-planning and curation of participants would strengthen the value of the IDF. This includes not only who engages from the private sector and CSO community but what technical ministries – and from what levels – are needed to ensure sustainability and value in the contributions of IDF to policy processes. For the next IDF to be more strategic in facilitating collaboration and policy influence, more pre-planning and curation are needed, both in the knowledge-to-policy process as well as the private sector business matchmaking events (curation of start-ups and potential investors).

- Preparation and follow-up are crucial and would be significantly aided by strong cross-sectoral participation in the design and delivery of the IDF.

Short timeframes created multiple challenges. Importantly a more participatory approach (across the knowledge sector actors i.e. PRIs, technical ministries, and sub-national governments) to planning, delivery and follow-up, would greatly enhance the value of the event and the potential for IDF to contribute to the policy process.

- The role of the facilitators is important to ensure that quality knowledge is presented strategically and effectively. In this regard, these facilitators should be actively involved from the beginning so that it is quickly apparent if they are suitable.

- Multidimensionality of IDF sustainability. IDF’s sustainability could be viewed not only from its continuation as an event, but also from its vibrancy where all actors in knowledge sector, both at national and sub-national levels actively participate and benefit. The IDF has achieved many successes to date and has built on the complementarity of skills of Bappenas and KSI. That it has strong support from Bappenas, support from a development partner that is appreciated, and has clearly built the skill to generate good media coverage, are extremely important to the future of the Forum and create an excellent foundation for follow-up on these recommendations.

H.5 Supporting the RPJMN: Approaches to strengthen evidence-informed policymaking

Completed in 2020

This study examined the approaches that DFAT has taken to support evidence-informed policymaking in the RPJMN. Indonesia’s National Development Planning Body (Bappenas) is responsible for the development of the National Medium-Term Development Plan (Rencana Pembangunan Jangka Menegah Nasional RPJMN). Given the strong history of collaboration and support with Bappenas to respond to requests for background studies to inform the RPJMN. In addition, support for RPJMN background studies presents an opportunity to support policy development based on evidence. With the goal of ensuring that work is as effective as possible, this study seeks to understand the relative strengths and weaknesses of the approaches taken in developing them, based on the sample of DFAT-funded background studies.

In addition to examining the approaches and processes undertaken in the development of background studies in each of the above cases, 3 cases (Education, Political Party Financing and Regulatory Reform) were selected for follow-up to determine the extent of their impact. The case studies were based on interviews and group discussions with the teams that developed them, organisations involved in the process, and their Bappenas and DFAT counterparts. Key findings include:

Focusing on the RPJMN alone is not a meaningful stand-alone goal, but is an important element in contributing to policy change. All DFAT-funded teams interviewed for this study saw successful contribution to the RPJMN as critically embedded in a broader set of work. Similarly, Bappenas counterparts recognised not only the value of the RPJMN as a stand-alone document, but were often keen to use the process of its development to raise issues in the political space or gather deeper knowledge on particular technical issues.

This finding, in turn, means that the notion of “contributing” of the RPJMN must be broadened beyond a purely textual interpretation. Making links from evidence to the text RPJMN is not enough to determine if policy is really changing. A broader conception of contribution allows for a more careful consideration of what possible improvements to policy development might look like, including a consideration of Bappenas’ approaches to sourcing and using evidence as well as building the relationships and structures to do so.

Broader notions of contribution are consistent with those found in the cases examined in more depth. For example, one of the more powerful examples of (textual) influence, changes to the Education indicators, were able to be made in part due to the fact that discussions covered not only the RPJMN but Ministerial plans (RENSTRA), allowing Bappenas to negotiate between the documents, and thus gain more flexibility.

While approaches to support evidence-informed policymaking need to be tailored to the needs of individual stakeholders, early dialogue and clear processes for discussing Bappenas’ RPJMN needs can help them to understand and define key issues. While it is difficult to change the process for identifying topics for exploration once Bappenas has submitted a request for assistance, more input is possible if discussions start early. It is also important that those undertaking the work have a fairly deep knowledge of their area so that they can discuss in detail with Bappenas counterparts to define key issues from the beginning.

Challenges around data and analysis run through the RPJMN background paper process. Quality analysis depends to a large extent on quality data. For the purposes of the RPJMN, this can include both primary data as well as quality program evaluations. However, challenges remain in data quality and availability, as well as capacity to undertake analysis. The ability of partners to assist fill analytical gaps depends in part on their ability to afford or access data.

Consultation and coordination are key elements of the RPJMN process, presenting opportunities to connect key partners and ensure that policies are carried from general discussions into more detail. In the cases reviewed for this study, there were a number of good examples of partners holding consultations that were tightly focused and well facilitated. Engaging implementing ministries throughout the RPJMN background paper process is a good practice that allows them both to shape and operationalise the policy vision set out in the medium-term plan.

Clearly communicated recommendations support discussion and potential uptake. Recommendations were well communicated in both the Education and Social Protection cases, including not only clear concise papers, but power points, infographics, etc.

The strength or weakness of any particular approach is dependent on how well it responds to the particular combination of needs presented by Bappenas and other stakeholders. There is no single approach that DFAT can adopt to respond to request for background papers. This is due to a range of factors: approaches to the preparation of background papers vary across directorates, dependent largely on the requests from individual Directors; different constellations of stakeholders with different appetites for engagement; and differences in the scope and role of the background papers themselves.

H.6 Evaluating the use of the Swakelola Tipe III procurement mechanism in 2020

Completed in 2021

This evaluation was a follow-on to a first evaluation of the Swakelola Tipe III (SW III) procurement mechanism conducted by Solidaritas in 2020. The purpose of this evaluation, also conducted by Solidaritas, was to understand the extent to which SW III is being used, and to learn from existing examples to improve socialisation and advocacy efforts related to procurement.

The evaluation found that 77% of CSOs and government agencies learned about SW III primarily through socialisation events supported by LKPP, KSI or other organisations. Of those that attended such events, 94% rated them as relevant, and 97% stated that the events helped increase their understanding of SW III. Even though the evaluation team did not have access to LKPP data on SW III, the data it did obtain showed that SW III was being successfully used for a range of purposes, including research. The advantages for government agencies of using SW III are better quality decision making/service delivery and value for money. The advantages for CSOs are that it to the mission of the organisation, and develops/strengthens its relationship with government.

As SW III is relatively new, there are some challenges, both prior to the signing of the contract, and during implementation. Challenges prior to contract signing include insufficient knowledge of the mechanism among key government stakeholders, lack of willingness in the government to use the mechanism, low information among CSOs on the availability of SW III opportunities, and high overheads. Challenges during implementation include difficulties by CSOs to meet the government reporting standards; cash flow problems for CSOs, as the contract payment may be a lump sum at the end of the contract; confusion on the tax reporting status of the CSOs; and limited time for implementation. There were also some challenges specific to the COVID-19 pandemic. Data collection became more difficult and budgets allocated for SW III were diverted to pandemic response.

The study made 10 recommendations to improve the sustainable use of SW III:

- KSI and LKPP should collaborate with the department of the Director General of Budgeting to provide written guidance on the acceptable range of institutional fees for CSOs; the financial and administrative documents necessary to process payments; how to proceed if implementation cannot be completed before the end of the financial year, and the implication for payment; and the level of justification the government agencies need to provide to justify the selection of the CSOs.

- KSI should consider working with a government department to propose a payment standard specifically for SW III as an alternative to Standar Biaya Masukan (SBM).

- LKPP (with KSI support) should update socialisation and guidance materials, advising governments to prepare justification for why goods or services procured through SW III either (a) cannot be delivered by the private sector or (b) are more effectively or efficiently procured from CSOs.

- LKPP (with support from KSI) should identify the most appropriate way for LKPP to monitor use of SW III in the future.

- LKPP, in accordance with the agency’s mandate, should monitor SW III cases in 2021 to check whether the eligibility criteria are sufficient to ensure that only capable CSOs can fulfil them, potentially revising the criteria if needed.

- To promote transparent and proper use of the mechanism, the government or LKPP could consider (a) creating a value threshold, above which government departments must provide evidence of a competitive process or (b) adding additional criteria requiring CSOs to present their experience and capacity to manage similar contracts to the one being procured through SW III.

- LKPP should focus on mass socialisation to the government, particularly targeting decision makers (focused on providing general information on the mechanism and the benefits of working with CSOs), as well as technical teams, representatives from Pejabat Pembuat Komitmen (PPK), Unit Kerja Pengadaan Barang/Jasa (UKPBJ), and the finance and inspectorate (focused on the operational aspects of the mechanism).

- LKPP should expand socialisations to also include consultations with governments and their potential CSO partners, to enable both parties to ask questions and troubleshoot any issues that arise during the contract.

- LKPP should clarify the role of UKPBJ to include responsibility for providing technical advice and coordination of SW III contracts.

- LKPP (with KSI support) should expand existing guidance documents to include answers to frequently asked questions, examples of good practice, as well as templates for key administrative documents. This information should be made available on the SIPRAJA website.

H.7 Evaluating the utilisation of GEDSI-sensitive research grant guidelines in universities

Completed in 2021

The main purpose of the study was to assess the extent to which the revision of the Buku Panduan Penelitian dan Pengabdian Kepada Masyarakat Edisi XII (2018)/XII edition of the Research and Community Service Handbook) has encouraged GEDSI mainstreaming in research and community service conducted by universities.

The study found that, in general, an increasing number of proposals contain GEDSI elements (from 6.1% in 2017 to 7.4% in 2019). As for the gender of the researchers, it was noted that the number of female researchers who applied for grants and received funding was increasing every year (to 47% in 2019).

The study identified several factors that might support GEDSI-based research. First, policies that strongly encourage sustainable and equitable development as stated in the Long-Term Development Plan (RPJP), the National Medium-Term Development Plan (RPJMN) and the government’s commitment to the Sustainable Development Goals through the National Action Plan for Sustainable Development Goals (SDGs). Second, the university’s internal policies, such as the Higher Education Research Master Plan, which has a science and technology perspective and a social inclusion framework, as well as the establishment of several Centers for Sustainable Development Goals (SDG Centers). Personal experience can also encourage researchers to conduct GESDI-related research.

Besides the driving factors, there are also several challenges that can prevent researchers from conducting more GEDSI-based research. One challenge is that there is often a lack of understanding or awareness of GEDSI from reviewers. Research is still seen only as research itself and has not applied the principles of inclusion and participation from all parties. In addition, the existence of several university policies that are not yet GEDSI friendly was also identified as one of the inhibiting factors for the mainstreaming of GEDSI. Apart from the above, there are also challenges that arise from researchers or academics themselves. Female researchers are more interested in researching GEDSI issues than men (53% vs. 47%). Sometimes there is also a fear that including GEDSI perspectives will reduce the value of the research itself.

The evaluation concluded that, although much progress has been made, the mainstreaming of GEDSI policies still faces various challenges. First, government policies are still interpreted differently by universities and researchers as knowledge producers. Second, GEDSI has not been interpreted as a complete framework for the research itself. Research is still seen as a mere research activity, even though it is hoped that research could lead to more inclusive development that might reduce inequality. The evaluation found that efforts to mainstream GEDSI in higher education through manuals or other institutionalisation would struggle to have a significant impact without also advocating for changes in social norms. The perception of ableism encourages universities to be more open, and encourages the academic community to use more critical studies based on the human rights approach.

The evaluation made several recommendations for the different stakeholders:

For MoECRT, as policymakers.

- Pursue a policy of affirmative action for GEDSI research as women researchers and researchers with a disability still experience inequality in opportunities for accessing grants.

- Develop a more binding and detailed handbook. To operationalise GEDSI in research, guidebooks for research and community service should contain a special chapter on the importance of GEDSI in development, awareness of the importance of reducing GEDSI inequality, and how to distinguish GEDSI as a perspective or as a mere object.

- Introduce assessment instruments in grant proposals. Researchers should be provided with self-assessment tools to check if the research or community service is related to, or accommodates, social inclusion.

- Integrate GEDSI as one of the components in the accreditation of universities.

- Introduce a ranking of universities based on GEDSI indicators.

- Use GEDSI as one of the indicators in the review of articles submitted for publication in national academic journals.

- Build communication with universities to promote GEDSI lens in research and community development works.

- Utilising social media to better inform the researchers (especially the young researchers) on the research grants procedures and mechanism.

For the universities:

- Make the Research Master Plans GEDSI sensitive.

- Include gender equality and social inclusion curricula in special courses or integrated with related courses, preferably in the first year of study.

- Encourage researchers to collaborate not only with industrial partners, but also with marginalised/vulnerable communities as part of the research team, without compromising the quality of the results in the research.

- Strengthen the synergy between gender study centres or disability service study centres and SDG Centers.

- Strengthen the function of the Institute for Research and Community Service (LPPM) as a catalyst for mainstreaming GEDSI in universities.

- Equip reviewers of research proposals with assessment tools, so that they can assess the level of relevance of research proposals from a GEDSI perspective.

- Encourage research ethics committees/Institutional Review Boards (IRBs) in universities to ensure that the GEDSI perspective is used by researchers, especially for research involving human subjects, and on both health and non-health topics.

For the knowledge intermediaries:

- Establish close networks not only regarding research through the Directorate of Research, Technology and Community Service at MoECRT but also with other directorates under the Directorate General of Higher Education and Research such as the Directorate of Resources and the Directorate of Research and Development.

- Collaborate and advocate the importance of mainstreaming GEDSI with other national grant funders such as the Education Fund Management Institute (LPDP), the Indonesian Science Fund (DIPI) or directorates at BRIN that have grant schemes accessible to universities, especially those related to national flagship research.

- Strengthen the GEDSI Network by tying it into larger networks, not only involving GEDSI activists from universities, but also involving practitioners or figures/activists who are vulnerable people so that the resulting evidence base becomes more inclusive.

- Further advocate the GEDSI issues to universities and wider communities.

For the GEDSI Network:

- Strengthen the network not only with fellow researchers, but also with networks that involve the general public, especially the vulnerable as part of the principle of inclusiveness and empowerment itself.

- Expand the network to involve many other researchers, especially university researchers who came from remote or disadvantages regions, or from universities with an undeveloped research atmosphere.

- Disseminate study results on mainstream or more popular platforms, so that they can be accessed more broadly.

For DFAT:

- Bring GEDSI mainstreaming to every component the research ecosystem itself, i.e. to knowledge producers, knowledge enablers, knowledge users and knowledge intermediaries.

- GEDSI mainstreaming is a process and is not the end goal. Given that there are still very limited perceptions and insights about GEDSI in the research/university ecosystem, DFAT might consider implementing a special program on mainstreaming GEDSI in universities in Indonesia in the future.

H.8 Review KRISNA

Completed in 2021

This evaluation answered 4 evaluation questions:

      - Benefit of KRISNA. KRISNA has contributed to a more effective and efficient planning and budgeting process. The majority of survey respondents confirmed that KRISNA shortened the planning and budget process, increased transparency and accountability in comparison with the previous planning and budgeting process.

      - Compatibility and interconnection challenge with other planning and budgeting systems. The evaluation confirmed that KRISNA has interoperability with other applications such as Kerangka Pendanaan Jangka Menengah (KPJM) that is managed by the Ministry of Finance; and Sistem Informasi Rencana Umum Pengadaan (SIRUP) that is managed by the Government Procurement Agency (LKPP).

      - Suitability of implementation of KRISNA. More than 90% of respondent confirmed that KRISNA was a simple and user friendly platform. The evaluation found that the majority of KRISNA users, both at national and regional levels, have interest to use KRISNA data for program analysis, however only around 55% of the respondents have ever done the analysis.

      - Supports and ownership of KRISNA. The evaluation found that the ownership of KRISNA was still low for almost all types of respondents.

H.9 Evaluating the use of the Swakelola Tipe III procurement mechanism (Round 3)

Completed in 2022

The Swakelola Tipe III procurement mechanism was introduced in Presidential Decree 16/2018 on government procurement of goods and services, hereafter ‘Perpres 16/2018’. This mechanism enables government to directly contract Civil Society Organisations (CSOs) to carry out activities. KSI and its grantees were involved in the advocacy of the inclusion of this mechanism in the Perpres 16/2018. To understand the extent to which Swakelola Tipe III was being used and to learn from existing examples to improve socialisation and advocacy efforts related to procurement, KSI commissioned the round 3 of evaluation of Swakelola Tipe III.

Findings

- How has awareness of Swakelola Tipe III mechanisms developed among users? Has there been any change, either negative or positive, in the awareness (perception) among users of this mechanism?

- Swakelola Tipe III started to be widely used by the government, both at the national and local governments. For ministries with limited number of human resources, using Swakelola Tipe III is good option to implement program. For instance the Ministry of Women’s Empowerment and Child Protection where number of personnel is only about 300 people and does not have a representative in regional level. These limited resources became a motivating factor for KPPA to work together with other parties, in particular CSOs, to reach out to the communities, especially women and children communities. Prior to the regulation on Swakelola Tipe III, KPPA cooperated using a type 1 swakelola mechanism.

- The Provincial Government of South Sulawesi, particularly Bappelitbangda was also using the mechanism. One of the important approaches of the South Sulawesi Provincial Government is collaboration with the community. Through Swakelola Tipe III, collaboration with the community is no longer just a jargon, but becomes a real practice of cooperation between the government and the community in development.

- One of the reasons for using Swakelola Tipe III is because not all services required by the government attract the interest of consulting service companies, not all projects attract contractors/consultants and not all contracts have human resources capable of working on programs that are close to the community.

- To what extent has Swakelola Tipe III been used by the government and CSOs, both KSI partners and non-KSI CSO partners?

- Information on the use of Swakelola Tipe III is not available so far. In the case of LKPP, the data only sorts out tenders and non-tenders and not separated between type III or other types of swakelola.

- Swakelola itself is interpreted as cooperation between the government and the community directly. From an online survey with 125 respondents conducted by KSI, there are 15 Swakelola Tipe III contracts. Of the 15 contracts, 11 were research contracts and 4 were for other work.

- Likewise, the value of the Swakelola Tipe III contract is not known with certainty and the amount varies. The information on the contract value for 2021 that has been collected shows that the size of the contract depends on the fiscal capacity of the government agency. Ministries at the central level that hold large budgets tend to allocate large amounts of funding. For example, the Partnership received a contract from the Ministry of Home Affairs to evaluate the Regional Government Implementation Performance Evaluation (EKPPD) methodology and received a contract of Rp. 1.4 billion in 2021. Meanwhile, the Election and Democracy Association (Perludem) only received a contract of Rp. 20 million from the South Nias KPU for the evaluation of the regional elections in 2021. In 2020, Needdem received Rp. 300 million from the Ministry of Home Affairs for the evaluation of the Pilkada from a funding aspect. The large fiscal capacity of the Ministry of Home Affairs is also evident in the Swakelola Tipe III contract awarded to CSIS to conduct a Pilkada study with a Papua case study amounting to Rp. 600 million by 2020.

- What motivates the government and CSOs to use Swakelola Tipe III and what are the perceived benefits of using this mechanism?

- The reasons of using Swakelola vary, ranging from making it possible to collaborate with the community to make easy to reach the beneficiary of community groups.

- Meanwhile, for mass organisations, working with the government provides an opportunity to be directly involved in the formulation of public policies. They see Swakelola Tipe III not only as a matter of funding, but as a mechanism to work together and be directly involved in public policy.

- Any challenges using Swakelola Tipe III? What progress has been made to improve the mechanism? How can the use of the mechanism be further increased?

- One of the challenges is to encourage an open and competitive process so that CSOs with experience, skills and capacities can participate. If the process is still being appointed, then the mechanism will not provide the best service provider for the government other than limiting other potential service providers. But at the same time, there is not enough information on CSOs accessible to government if another challenge.

- The difference in understanding on the mechanism, not only between ministries and agencies, but also between different units within the same ministry in term of technical implementation (e.g. administrative matters, tax).

- To what extent has the use of Swakelola Tipe III been increased?

- There is currently no information available regarding the use of the mechanism from LKPP. The system managed by LKPP has documented Swakelola Tipe III and is not yet accessible to the public.

- In general, the use of the mechanism has increased from previous years. Likewise, the value tends to increase. In some projects, the value of the work contracted is quite large. One of the factors driving the increased use of Swakelola Tipe III is the abolition of the 3-year financial audit requirement. For many non-profit organisations, financial audits are difficult and expensive. Therefore, the abolition of this rule has enabled many CSOs and non-profit organisations to fulfil the requirements for obtaining self-managed contracts.

- What are the prospects for the continued use of the mechanism in the future and how can the sustainability be improved?

- In general, Swakelola Tipe III provides benefits for both the government and mass organisations. For the government, Swakelola Tipe III provides an alternative service provider from mass organisations and organisations with non-profit legal entities.

- Swakelola Tipe III can also be less expensive because non-profit organisations are not for-profit like consulting firms.

- There is great interest from the government and CSOs to work together using the Swakelola Tipe III mechanism. The challenge is to carry out socialisation to reach out and provide information, both to the government and mass organisations to start using Swakelola Tipe III.

- How has the Swakelola Tipe III mechanism contributed to the development of evidence-based policymaking?

- One of the aims of Swakelola Tipe III utilisation is for funding research. From a number of Swakelola Tipe III contracts that have been identified, there are several research activities that are used to formulate public policies.

Conclusion

- The mechanism is widely known and used by different actors. More K/L and Local Governments are using it. Based on interviews and surveys, many respondents from the government and mass organisations are interested in using Swakelola Tipe III. Although there is confusion about administrative procedures and processes, ministries such as KPPA and Ministry of Home Affairs have taken the initiative to use Swakelola Tipe III to implement their programs in 2021, both in the form of policy research as well as for empowerment and technical guidance.

- Challenges are still there. Administrative practice is still input and output oriented which in the end burdens mass organisations that get contracts. LKPP feels that it does not have sufficient authority to make changes because some of these changes, such as indirect costs or tax provisions, require a policy from the Ministry of Finance. This unfinished agenda needs attention and joint work.

- In terms of regulations, LKPP accommodates various suggestions and continuously works to improve the mechanism.

Recommendation

- Encourage dialogue between CSOs, LKPP and the Ministry of Finance to share perceptions about swakelola and the meaning of “at cost” spending. Most of the government bureaucracy, even staff from LKPP, interprets swakelola as spending at cost so they cannot finance institutional costs and indirect costs. Whereas contracting with institutions is certainly different from contracting with individuals. Cooperating with the organisation basically has to finance all the needs of the organisation to run the contract, including institutional costs and indirect costs.

- Dialogue is still needed to resolve various financing issues. In addition to encouraging the government to finance institutional costs and indirect costs, there are problems in terms of taxation. The government directly collects taxes from the costs transferred to the implementers of Swakelola Tipe III and has the potential to generate double taxation.

- There is still a need for wider socialisation, especially for ministries, institutions and local governments.

- One important professional organisation that has not been widely involved is the Indonesian Procurement Experts Association (IAPI). IAPI members are people who have been consultants or trainers for the certification of goods and services procurement. By conducting socialisation to IAPI, information about Swakelola Tipe III and clarity of administrative procedures can be conveyed to K/L and Local Governments.

- Socialisation is also needed for staff who manage SPSE in government work units. One of the obstacles to open access to the public for Swakelola Tipe III data is the large number of recording errors. This indicates that there is a knowledge gap between LKPP and staff assigned to government work units regarding the mechanism detail.

- To equalise perception, LKPP needs to provide a help desk for consultation. So far, the practice of consulting is carried out by inviting staff from LKPP. This process can be institutionalised by establishing a help desk which can be a call center or a channel for communication and consultation.

H.10 Evaluation of the role and function of policy analysts

Completed in 2022

In 2014, KSI and LAN started an initiative to support the development of the functional position of policy analyst (JFAK). The collaboration was to support LAN in improving the capacity of policy analysts to produce high-quality policy analysis within the bureaucracy. The LAN–KSI collaboration continued the following year with KSI providing technical assistance and catalytic work, such as the development of training modules; technical assistance for the Indonesian Policy Analysts Association/Asosiasi Analis Kebijakan Indonesia (AAKI); support for the establishment of a policy analyst knowledge management system; the development of competency standards for the policy analyst profession; and improving the Policy Quality Index/Indeks Kualitas Kebijakan (IKK) as an instrument for assessing the quality of government policies, a guideline for ministries and other government agencies to improve their understanding of policy analysts and how to recruit them.

The purpose of the evaluation was to assess the progress achieved through the above collaborations between KSI and LAN, and to find out whether policy analysts have played their intended role and function. This evaluation was closely coordinated with LAN so that it was fully on board from the start, and to enhance the likelihood that LAN will use the findings of the evaluation.

Key findings

The findings indicate that there are still gaps in components that make up the role and functions of JFAK. In order to optimise the role and functions of JFAK in the future, important and critical things that are necessary conditions to close the gap are offered, as well as capacity developments needed to have professional JFAK, which is very much needed in the transformation and development process.

- The need still to seek for strategic pathways to optimise the 8 roles of JFAK in ministries, institutions, and local governments.

- Factors that act as ‘key elements’ or ‘necessity conditions’ to be able to close the gap, as well as strengthen JFAK capacity, are as follows:

- For optimizing the role of JFAK, there are gaps in the 8 components in realising the role, specifically, it can be stated that the important and critical things for optimizing the achievement of the role of JFAK are in: (1) identifying problems and setting the agenda, and; (2) a role in conducting ‘evaluations’.

- For optimizing the JFAK performance over the Scope of Work, there are gaps in the 19 components. Although nothing important and critical was found, attention must still be paid and concrete steps must be taken to close the gap, as well as capacity strengthening related to the ‘key elements’ that act as ‘necessary conditions’.

- To optimise the performance over JFAK scientific Scope of Work, there are gaps in the 4 components. Ways to address this include: (1) capacity in the formulation of ‘policy papers’, and; (2) capacity in the formulation of ‘policy briefs or policy notes’.

- On the basis of the above, the role of coaching carried out by LAN and the role of facilities by KSI in an effort to increase JFAK’s competence and capacity is very strategic, especially in creating a professional JFAK capable of supporting the realisation of the bureaucratic transformation process towards the modernisation of public management in Indonesia.

Recommendations

- Conduct further exploration to be able to find room for improvement (opportunity for improvement/OFI) that has optimal leverage, and then formulate corrective action steps (action for improvement/AFI) which are considered the most appropriate and provide optimal impact;

- Open a wide ‘learning space’ in various forms, including: (1) assignment/delegation, (2) simulation/internship/work practice, (3) education and training, and (4) independent learning, in various approaches among others, (1) face-to-face, (2) virtual, and (3) lifelong independent learning in the concept of lifelong learning;

- Giving awards (calculation of credit points) proportionally for all efforts to develop competence and increase capacity carried out by individuals, groups, and institutions;

- The above matters are followed up with the preparation of structured and systematic programs and activities that can be carried out with a measurable division of roles to be carried out by LAN, JFAK placement institutions, direct supervisors as technical advisors, and individual JFAK stakeholders;

- To formulate instruments for monitoring and controlling the implementation of the programs and activities mentioned above, as well as making them part of efforts for continuous improvement or development.

H.11 Evaluation of the Indonesia Development Forum

Completed in 2022

To understand the cumulative achievements, learning and readiness of IDF as a premier self-managed development forum, KSI assigned independent evaluator to conduct an evaluation, to support KSI and Bappenas in their continuing efforts to improve the quality and relevance of the Forum, and to enhance its sustainability. The evaluation employed a qualitative approach using key informant interview (KII) and Focus Group Discussion (FGD) methods to collect primary data. To complement the primary data, the evaluation used a meta-evaluation approach to analyse how the IDF has evolved as an influential forum for knowledge-to-policy processes.

Key findings

- On convening capacity, IDF has evolved as a massive national gathering.. Participants were distributed relatively evenly across the 4 knowledge sector actors (producing, intermediary, developing policy, and implementing policy). IDF managed to attract high-level policymakers (minister, echelon 1 and 2), competent researchers and experienced practitioners, but there is the perception that IDF missed some critical actors from the everyday policymaking process, i.e. the echelon 3 bureaucrats and officials from the Ministry of Finance.

- In all IDFs, participants in general acknowledged the contribution of IDF in expanding their understanding of the information, the landscape of policymaking actors and ideas on what works. Each year, IDF selected a different theme based on priorities of the Indonesian government and Bappenas’ development strategy, however, what remained the same was the focus on derivatives of economic development themes.

- The IDF 2018 and 2019 evaluation reports documented high satisfaction and agreement on the quality and relevance of the knowledge presented at the IDF.

- In recognising the need for different forms of knowledge in policy process, IDF intentionally provided space for interactions between the 3 forms of knowledge (scientific/research, professional, and local knowledge). However, it is interesting to note that the retention and relevance of the knowledge presented at the IDF were more related to professional and local knowledge, rather than evidence generated from scientific research (scientific knowledge).

- IDF has provided a space for engagement among the participants to identify and explore opportunities for collaboration. However, IDF was not designed to nurture relationships after the event. IDF is more about a marketplace platform to serve on-the-spot interactions.

- IDF was perceived as a knowledge-sharing and collaboration event, rather than aiming to achieve certain policy outcomes. IDF had influence on the facilitating factors and mechanisms to influence policies i.e. through expanding policy capacities and broadening policy horizons, but stays largely clear of policy content. Since IDF is not legally positioned in Bappenas’ formal policymaking process, nor a mandated forum by the president such as the Sustainable Development Goals (SDG) Forum, the uptake works through informal pathways, i.e. through increasing awareness, or as referred to in the 2019 evaluation “policy literacy” and “policy attitude” instead of a direct uptake into policy content.

- Awareness and intentional attention to GEDSI were clearly reflected in all editions of the IDF since 2017 and became even more evident in 2019. In the 2022 design, informants from KSI and Bappenas confirmed a commitment to deepening GEDSI in proceedings, participants, and sub-themes.

- Bappenas has mechanisms in place to monitor and evaluate their activities. For each forum, since 2017, Bappenas organised a reflection session within 3 months after the event. Bappenas acknowledged the importance of technical evaluation and expressed their appreciation for the learning and feedback provided by KSI. However, changing the existing MEL methodologies is still challenging for the IDF committee because: 1) The key determinant of success for an event/activity managed by Bappenas is the fact that it happened as planned, and; 2) There are disincentives to employ rigorous MEL. Employing rigorous MEL may result in findings that are considered sensitive as it involves making a judgment about the distribution and use of resources as well as the performance of the implementing unit.

- Financing IDF seems not to be an issue for Bappenas because there is a consensus among the leadership that Bappenas needs to organise IDF on an annual basis. While the existence is secured, the amount (how much) faces some degree of uncertainty. In terms of human resources (people), Bappenas reported their confidence to manage IDF in the future. Continued commitment among Bappenas leadership (the minister and echelon 1 staff) has increased this confidence, along with experience with KSI since 2017 in co-managing IDF. Specifically, they are confident in knowing which areas they can directly manage and which processes they need assistance (and which are therefore outsourced). Some works, however, were identified as areas that need support or collaboration with external parties. For example, on the managing and curating of the research and evidence to be presented in IDF.

- From the IDF 2019 to the end of 2021, there is no significant progress in the institutionalisation of IDF governance in Bappenas. While strong enthusiasm for continuing the IDF as an annual event is evident at all levels in Bappenas along with a dedicated budget item for IDF and adoption of SOP, the establishment of a permanent secretariat to plan and manage IDF as a regular annual event and a Ministerial decree are still in process of review by the Legal Bureau. Bappenas is preparing an option if this institutionalisation process is still uncertain; a unit in Bappenas (PAKK-Pusat Analis Kebijakan dan Kinerja-Center for Policy and Performance Analysis) may take over the governance.

Recommendations for Bappenas

- Uptake of IDF. There is a need to clarify on which dimensions of “shaping the development agenda” that the IDF can realistically achieve results, i.e. what success looks like in terms of knowledge uptake or policy influencing. A framework for measuring policy influence is recommended both for informing the design and format of the sessions and interaction, and for evaluating the success of IDF.

- Reputation. Provide a mechanism for co-arrangement of IDF to increase participation and ownership. The limited role of academic institutions (one of the suppliers of knowledge) and technical ministries (users) in the IDF can result in passive participation, which is a risk and can diminish the reputation of IDF as a premier knowledge-to-policy platform. Mechanisms could be created for better co-design and co-delivery to be a truly knowledge sector event. Being seen as an event of one agency limits the interest and commitment of others.

- GEDSI. The positive GEDSI atmosphere in all IDFs is an aspect of IDF that could be built on going forward. Being intentionally GEDSI-sensitive, especially in breaking the vicious cycle of social exclusion, especially among people with disabilities is recommended.

- Relationship. The low participation from other ministries and from the technical level of ministries was perceived as a signal that IDF is more about Bappenas. More substantive participation (not only representation) of sub-national actors and technical ministries would enhance the inclusiveness of the IDF.

- Knowledge. In terms of the types of knowledge presented in IDF there was a trend where practical knowledge in the forms of “what worked” initiatives are getting more attention from the majority of the participants. If this trend continues, IDF could be perceived as an exhibition of good practices (or, as it is called in Indonesia, a “pameran pembangunan”)—a typical government showcase exhibition to show how great is the government in administering development. While this type of knowledge is important, the right balance between scientific, professional, and local knowledge to be exchanged in IDF should be managed strategically.

- Monitoring, evaluation and learning. Bappenas’ monitoring and evaluation system is adequate to inform questions around IDF’s output and accountability. However, questions related to IDF’s outcome are beyond the mandate of the IDF steering committee or the Bappenas’ unit that is responsible for monitoring and evaluation. We recommend Bappenas to explore collaborations with external entities to design a specific monitoring, evaluation and learning system and integrate it in IDF’s steering committee Scope of Work.

Recommendations for DFAT and other development partners

- Sustainability of IDF. If sustainability of IDF is defined as a continuation of IDF by Bappenas with its own budget, the inclusion of IDF in the 2 Bappenas planning documents namely Strategic Plan 2020-2024 and the annual work plan and budget (RKA) is critical. It is recommended that DFAT or other development partners initiate a dialogue with Bappenas on inclusion of IDF in Bappenas’ RKA. To create an enabling environment for Bappenas to include IDF in their work plan and budget, an advocacy initiative to include IDF in the formal government’s development planning process (through presidential regulation or similar regulations) is recommended.

- Reputation. DFAT and other development partners could intentionally link their supported knowledge events, research, and evaluation to IDF. This will improve the reputation and legitimacy of the IDF.

- Monitoring, evaluation and learning. While Bappenas may focus on the evaluation of the event (process evaluation), DFAT and other development partners could support Bappenas to expand the scope of the evaluation beyond event and complement with outcome evaluation to make a case if and how IDF works in shaping Indonesia’s development agenda.

H. 12 Evaluation of PRI progress

Completed in 2022

This evaluation reviews the effectiveness of the Knowledge Sector Initiative (KSI)’s support to 16 Policy Research Institutes (PRIs) over its 2 phases of operation, taking place between 2013 and 2022. The review focuses on 4 areas of support to PRIs: research quality; network and profile; engagement and influence and; financial sustainability.

Research quality: by 2015, all PRIs conducted internal quality control processes, although the consistency and focus of such quality control and the involvement of external actors varied. By 2022, most PRIs met KSI’s criteria for producing quality outputs for KSI funded work. At an organisational level, PRIs had a better understanding of how stakeholder involvement during research design could increase uptake and legitimacy and therefore research quality. PRIs overall improved their quality assurance (and research management) processes (including peer review). There appeared to be more dialogue among staff through for instance, regular internal seminars, the establishment of technical working groups, about research proposals, designs and preliminary findings, which had driven up their quality.

With regards gender, half of PRIs in 2015 had a basic understanding of the term and did not consider this during research unless the topic explicitly called them to do so, while the other half worked with vulnerable groups and were more aware of the issue. By 2022, almost all PRIs made improvements in relation to considering GEDSI throughout both KSI and non KSI funded research. Some PRIs developed a GEDSI sensitive framework to use throughout the research process, helping them to pay attention to the role and needs of marginalised groups. Some PRIs suggested they were looking to work on issues which more explicitly touched on GEDSI issues.

Networks and profile: in 2015, organisations generally considered themselves to be known and viewed positively among all stakeholders and considered at least some of their research products to be known and considered relevant and credible. Most PRIs said they tended to work/collaborate more frequently with CSOs and less so with policymaking institutions, and did so in a limited or sporadic way. By 2022, all PRIs said their reputation among stakeholders had improved while their networks and relationships with various stakeholders had both deepened and expanded. These included government, including central level agencies as well as Bappenas, research and academic circles (especially among university-based PRIs), as well as CSOs which were approaching PRIs for training in data and research management. PRIs seemed to have a better profile among and relationship with media outlets such as Kompas and The Jakarta Post – being approached for comment and opinion and featured in articles, with PRIs less reluctant to engage. In a few cases, PRIs benefited from being recognised in their own right, in addition to their (previously more prominent) researchers or board members. Interestingly, some PRIs said that engagement with KSI had influenced a shift in their identity from a research organisation serving clients to one with the intention of influencing policy and practice.

Engagement and influence: in 2015, some PRIs integrated engagement with external actors into their research process. However, half PRIs had only begun to turn their attention to policy engagement and influence. Most PRIs suggested they could use more appropriate formats in their engagement with stakeholders. Engagement with stakeholders tended to be ad hoc, based on the initiative of specific individuals and not part of a plan unless funders made specific demands. Engagement was seen as consuming a lot of time and resource which some PRIs felt they had little of. Both policymakers (national and sub-national) and civil society sometimes or frequently used parts of organisations’ research results, but PRIs had few mechanisms to track research use.

By 2022, All PRIs said they took a more systematic and structured approach to engaging with their key stakeholders including policymakers. This involved researchers having more formal discussions early on in a research project about what they wanted to achieve, who they wanted to influence and how they would do so. PRIs now had more options (in terms of e.g. communication outputs) to consider in engaging different stakeholders, beyond traditional research reports, supported by specialist communication staff who had been hired. Several PRIs said they were now able to track the impact of their policy engagement work to help account for resources but also help them to improve their approach. All PRIs shared examples of changes in policy that they believed they had contributed to. Most examples referred to changes in government regulation which they had advocated for or actually drafted themselves. This included collective efforts among PRIs through a KSI working group to enable government to procure multi-year research from NGOs.

Financial sustainability: in 2015, the majority of PRIs were predominantly or exclusively funded by donor organisations, although most received funding from a variety of different donors. Some PRIs said they did not need to write research proposals to secure funding and relied on their reputation among and relationships with funders to do so. On financial and operational management, PRIs had finance and operations systems that covered finance, procurement, asset management, and fraud prevention, which were (generally) applied consistently. Some PRIs said they had started to direct some of their funds into reserves or endowment funds, with 1 PRI saying they had invested this in government bonds.

By 2022, PRIs were thinking more seriously about their financial sustainability and the need to diversify funding sources. Many PRIs which had not already developed business units to generate additional income, did so. But it was unclear whether they brought in any significant new revenues. Some PRIs undertook more marketing/branding activities, while others were exploring possibilities from businesses and government through the Swakelola Tipe III mechanism. Several PRIs suggested they had a better understanding of their income and expenditure, which some were able to use to better price their research proposals. There seemed few discernible trends in the growth in the proportion of domestic funding and non-DFAT funding, with little correlation between such trends and the financial health of the PRI.

Adapting to Covid-19: some PRIs had their funding re-allocated away from research towards Covid-19 relief efforts, while in contrast, a small number of PRIs realised opportunities to make covid-19 and their impacts the focus of their research and secured funding to do so. Some PRIs delayed research given travel restrictions and limited capacity to conduct research online, coinciding with the pause of formal policy processes, which somewhat limited some PRIs’ opportunities to engage with policy. Other PRIs, especially those familiar with digital platforms, embraced the challenge of conducting both their research and engagement entirely online (or telephonically). Many PRIs found that they had better and more access to stakeholders including policymakers with whom they had existing relationships, using platforms such as WhatsApp and Zoom. Many also found over time stakeholders were less likely to respond to invitations to engage and when they did, were often distracted particularly during longer conversations/meetings. With restrictions having eased, some PRIs have embraced hybrid forms of work, giving staff more flexibility especially in the context of long commute times in Jakarta.

Mediating factors: more than half the PRIs suggested that since Joko Widodo came to power in 2014, the government had been more open to inputs from civil society including research inputs. In some cases, this openness manifested itself in increased demand for expertise and advice from PRIs which could vary depending on the issue. The continued growth of online and social media provided plenty of channels for PRIs and their supporters to reach various stakeholders. However, about half the PRIs said they were in no position to control how and the extent to which their inputs were considered, used and/or applied, while several PRIs highlighted the challenges of tracing whether one’s policy research had influenced change, due to the often complex nature and opacity of policy processes.

PRIs suggested that changes that emerged happened due to the commitment, desire, actions and relationships of specific people and groups of people in the organisation – founders, senior researchers, younger researchers, board members and others. Despite increased profile and recognition of PRIs being a key outcome of KSI’s Phase 2, a large number of PRIs suggested that it was also a pre-condition for the changes they experienced (especially in engaging with and influencing government). Furthermore, the propensity for PRIs to make progress in KSI’s areas of interest appears to be dependent on the identity of the PRIs at the time of engagement with KSI and their openness towards adjusting their approach.

Effectiveness of KSI approaches and inputs

- PRIs praised KSI for providing at least 7-8 years of continuous support, which was rare among current research funders.

- PRIs would have preferred a continuation of core funding into Phase 2 but welcomed the more collaborative approach between them and PRIs where KSI staff were seen as an ‘equal partner’ and a ‘critical friend’.

- During the transition, communication from KSI was poor leaving PRIs uncertain about, for instance, the rationale behind the changes (in funding and approach) and what the implications might be for their respective organisations.

- A circular or mutually reinforcing relationship between all 4 outcome areas during Phase 2: improvements in engagement and influence, network and profile, research quality and financial sustainability helped to multiply effects of KSI’s support.

- The capacity of PRIs to sustain the changes they have achieved in each of the 4 areas of interest will be dependent on funders willingness to fund processes to ensure research quality and policy engagement and influence

- Most PRIs found the program logic, although a little ‘painful’ to understand, helped them to identify particular outcomes and tracking back, identify which stakeholders they needed to engage with and what outputs they needed to produce. Some PRIs suggested that reaching consensus between KSI and the PRI on a program logic was too time consuming. And a few PRIs suggested that KSI’s interpretation of the program logic was too narrow, as it emphasised a focus on tangible changes such as regulations and technical guidance issued by national level government officials within the executive over more intangible changes among other stakeholders.

- Recommendations:

The evaluation suggests that

      - PRIs can: 1) continue, and build on, the work initiated by KSI by e.g. developing the capacity of their researchers and addressing GEDSI in research as well as proactively engaging with key relevant stakeholders, monitoring the impact of research on policy and improving their financial practices; and 2) collaborate with one another by for instance maintaining the working group and alliances set up during KSI.

      - Donor agencies can 1) do more to acknowledge the complexity and nuance of change and change processes; 2) fund third parties to play a critical friend role in relation to PRIs and broker relationships between them and other key stakeholders including government and overseas researchers; and 3) better manage transitions that come with starting, evolving and ending capacity development programmes.

H.13 Evaluating the knowledge-to-policy pilot in South Sulawesi

Completed in 2022

In 2021, KSI – in collaboration with BaKTI – conducted a knowledge-to-policy pilot in South Sulawesi, which helped in the development of a Governor Regulation on the labelling of natural silk. As this initiative was completed in late 2021, an evaluation of the initiative can yield valuable insights.

The study looked at how the evidence was generated and used during the policy process, the changes in perception/knowledge/behaviour among stakeholders, and gathered lessons learned from the pilot, as well as the success factors, the challenges and the opportunities. In-depth analysis in the evaluation was given to sustainability and replication prospects of similar initiatives for other regions.

Key findings

Changes in perception/knowledge/behaviour

- The perception changes are among researchers from universities where previously they focused on one field of study/science, and are now opting for a multi-disciplinary and comprehensive approach of doing research. In addition, the pilot of collaborative study has led to a paradigm change among the researchers to have more applicable research results. Throughout the collaboration, there was a positive interaction which made the actors understand each other better. Policymakers are increasingly convinced of the importance of evidence and the involvement of non-governmental actors in policymaking. Researchers feel that the quality of the results has improved due to the transfer of knowledge and the strengthening of the partnership spirit.

- Changes in perception and understanding of the use of evidence are shown by the formulation of a silk labelling policy and Collaborative Research by the Government of South Sulawesi as well as the replication of commodity value chain activities. Also, a strengthened understanding of the importance of a multi-disciplinary approach and aspects of GEDSI in policy research.

- Recommendations/aspirations for successful implementation and replication of K2P in the regions include:

- To the Regional and Central Governments: Bappelitbangda as an orchestrator, optimizing regulations, making collaborative Roadmaps, strengthens coordination of planning and budgeting for Province, District/City and strengthens the capacity of the State Civil Apparatus (ASN) researchers.

For universities: to actively contribute to doing and sharing funding K2P activities, encourage multi-disciplinary research, provide research databanks and increase the benefits of research for users.

For NGOs: to strengthen their capacity through partnerships and strengthen networks with policymakers.

- The prerequisites for the implementation of Sub-National K2P are: conducive policies, adequate capacity of human resources, institutions and other resources. K2P initiatives can be initiated by a collaborative group as an embryo formed by regional leaders. Previously, information was needed on the potential, availability of knowledge actors and policies that were conducive to collaboration in the regions.

H.14 Study of the public discourse on the knowledge and innovation ecosystem

Completed in 2022

The objective of this evaluation was to assess the extent to which public discourse has influenced policy processes, i.e. what contributions public discourse made to policy processes, network connectivity and perceptions.

The evaluation set out to answer a set of questions, and found the following:

- What changes in the network are observable pre- and post- discourse campaign?

As a result of the KSI activities, the network expands, and changes occur at the nodes where KSI activities take place, but the network contracts again after the activities or events held by KSI are completed.

- What was the quality/nature of the public discourse?

This information will primarily be obtained from the in-depth interviews, and this analysis is not yet concluded. The Social Network Analysis indicates a fair amount of discussion on ‘innovation’ but that relates mostly to individual and casuistic technical innovations, rather than innovations related to research or public policy. One other discussion topic that drew a lot of attention was on BRIN, with the advantages and disadvantages of the BRIN consolidation.

- How did the public discourse activities influence policy processes?

The influence on policy processes happens in different ways, and the response to various types of media may also be different. For example, trending topics on social media can trigger echelon 1 officials to hold meetings, which may not be good governance for public policy. KSI’s approach, which aims to stimulate public discourse from many fields, including social media, is considered very appropriate. However, influencing public discourse may take a lot of time, and KSI is coming to an end. It should also be pursued with different tools and instruments, as it is difficult to predict which one will be most successful.

- What influence did the public discourse activities have on the policy process?

According to several sources, KSI’s public discourse has had a great influence. However, this is often not direct in the form of policy influence, but through the effect it has on the process, the references used, and the policy landscape. In terms of the process, public discourse is able to provide impetus and cross-understanding between policy actors, while the debated discourse becomes an additional reference. Furthermore, as long as the public discourse is pursued, it adds to or strengthens the landscape in which the policy process is taking place.

Program Management Support Costs consist of MERLA and Program Communication costs, while Program Management Cost is a combination of expenditures, which consists of GEDSI, Media Engagement, Public Discourse, Sub-national, and Program Management Support Costs.

PPIM UIN’s research recommendations regarding tolerance were adopted in the Islamic Religious Education Learning Focus guideline by the National Education Standards Agency (BSNP) in February 2021. However, BSNP was dissolved in August 2021, following the release of government regulation number 57 of 2021 regarding national education standards.

Solidaritas (2021). Annual Swakelola Tipe III Evaluation; use cases from 2020.

Yusadiredja, I. N. (2021). Evaluasi Pengarusutamaan Kesetaraan Gender, Disabilitas dan Inklusi Sosial pada Riset Universitas Melalui Hibah Penelitian Kementerian Riset, Teknologi/Badan Riset dan Inovasi Nasional, 2017-2020.

At the time of submission of this report, only preliminary findings had been shared.