| STRIVE Stage 2 ANNUAL PLAN 20010/11 |  |
| --- | --- |
| ANNEX | A |
| Logframe |  |

| CODE | NARRATIVE DESCRIPTION | VERIFIABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
| GOAL | To contribute to the improvement in the quality of and access to basic education in the Visayas | Improved education and access performance in the target Regions and Divisions (indicators, such as, annual national standardized test results, completion, participation, drop-out and retrieval rates) | - Qualitative feedback on improvement/ satisfaction of DepED educational managers and other stakeholders including community, parents, teachers, students and pupils. - Quantitative measures of improvement from BEIS and Division/ School EMIS | - GOP/ DepED policy continues to promote quality of education service delivery, particularly to disadvantaged areas. - Economic development of the Provincial, Regional & National levels continues in a climate of social cohesion. |
| PURPOSE | To develop, support and strengthen education management and learning support systems for improved access to quality basic education, within the national Basic Education Sector Reform Agenda | Improved education system level performance in the target Regions and Divisions: - Increased number of schools with improved SBM practices; - Improved teaching-learning practice; - Improved access to quality learning materials; | - Report on the change in the level of SBM practices of schools - Analysis report on the change in teaching-learning practices of teachers and students - Analysis report on the change in the level of utilization of instructional materials | - DepED’s Basic Education Sector Reform Agenda continues as a priority policy focus. - There is both sufficient commitment from all stakeholders and adequate resources to continue improving and effectively utilising basic education support systems |
| COMPONENT 1: School Based Management Support System | Develop a functional management support system for continuing school improvement at regional, division and school levels | - Increased percentage of public schools with SIP/AIP prepared, implemented and monitored through a participatory process, led by school heads working with organized stakeholders and meeting specific quality dimensions included in an SIP assessment instrument. | - Report on the number of schools monitoring and continuously improving the implementation of the SIP in collaboration with stakeholders according to specified quality indicators; QAA report at the region level regarding implementation of basic education plans | - A desire and willingness exists among key stakeholders to develop closer partnerships as a strategy to improve basic education services. - Clear policy and guidelines in the implementation of BESRA are available - DepED's willingness to reorganize and designate staff to run the systems |
|  |  | - Increased transparency, accountability and integrity resulting from a participatory development Basic Education Support Plans | - Basic education support plans endorsed by education stakeholders - Report on the participation of stakeholders in the conduct of planning and implementation of the Basic Education Support Plan - Region/division/school -wide Report on plan implementation and results including utilization of all funds - Report on the perception of education stakeholders regarding transparency, accountability and integrity |  |
|  |  | - Increased number of effective initiatives undertaken by the region/division/schools to improve Access | - Report on the "access" initiatives (includes acceptability by stakeholders, replicability, results against indicators and sustainability of actions) |  |
|  |  | - Increased number of educational leaders utilizing management practices supportive of SBM | - Report on Assessment of education leadership and management practices. |  |
| COMPONENT 2: Human Resource Development (In-Service Education and Training - INSET) Systems | Development of a Regional Training and Development system for quality professional development of teachers and educational leaders | - Increased percentage of schools in the pilot divisions using the National Competency-Based Teacher Standards (NCBTS) to determine teacher / learning facilitators’ development needs and priorities | - Division report on the use of NCBTS in schools to determine development needs and priorities | - Appropriate and adequate budgetary support for Training and Development , including allocation of human resource to implement T&D systems - Clear policy and guidelines in the implementation of T&D are available - Regional personnel can coordinate training and development activities and work effectively with various agencies for the professional development activities - There are specialists in the DepED available as trainers - Available training and development modules can be adopted for use in these Regions (e.g. BEAM modules, NEAP materials) |
|  |  | - Increased percentage of School Heads in the pilot divisions using the Training Development Needs Assessment to determine development needs and priorities | - Division report on the use of TDNASH by School Heads to determine development needs and priorities |  |
|  |  | - Increased percentage of Regional and Division managers and trainers supporting provision of opportunities for continuous professional development of teachers and educational leaders | - Regional and Division report of Training and Development managers, trainers, trained educational leaders and teachers |  |
|  |  | - Increased percentage of trained teachers applying NCBTS competencies | - Report on teaching and learning practices |  |
| COMPONENT 3: Learning Resources Materials Development System | Develop the LRMDS to provide access to quality teaching and learning resources. | - Improved alignment of learning resource materials provided to teachers and students to identified requirements or needs. | - Analysis report on the matching of needs with available /provided learning resource materials | - Appropriate financial support for LRMDS, including allocation of human resource to implement the systems - Clear policy and guidelines in the provision of and access to LRM available - A desire and willingness exists among key stakeholders to develop closer partnerships as a strategy to improve access to quality learning resources |
|  |  | - Increased/widened the range of instructional resources available to teachers and students following set standards and specs. | - Inventory of types of instructional resources available/developed |  |
|  |  | - Increased/widened the participation of internal stakeholders in the operation of the LRMDS. | - Report on the contributions of internal stakeholders in the operation and maintenance of the LRMDS |  |
|  |  | - Increased access to instructional materials other than textbooks | - Analysis Report on the use of LRM in instructional settings |  |
| COMPONENT 4: | Manage the Project in an effective, efficient and responsive manner | Project implemented on time and within budget | - Project reports | - DepED remains committed & provides appropriate counterpart resources & support at national, regional and division levels |

COMPONENT 1:  SCHOOL BASED MANAGEMENT SUPPORT SYSTEM

| CODE | NARRATIVE DESCRIPTION | VERIFIABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
| Objective: | Develop a functional management support system for continuing school improvement at regional, division and school levels | - Increased percentage of public schools with SIP/AIP prepared, implemented and monitored through a participatory process, led by school heads working with organized stakeholders and meeting specific quality dimensions included in an SIP assessment instrument. | - Report on the number of schools monitoring and continuously improving the implementation of the SIP in collaboration with stakeholders according to specified quality indicators; QAA report at the region level regarding implementation of basic education plans | - A desire and willingness exists among key stakeholders to develop closer partnerships as a strategy to improve basic education services. - Clear policy and guidelines in the implementation of BESRA are available - DepED's willingness to reorganize and designate staff to run the systems |
|  |  | - Increased transparency, accountability and integrity resulting from a participatory development Basic Education Support Plans | - Basic education support plans endorsed by education stakeholders - Report on the participation of stakeholders in the conduct of planning and implementation of the Basic Education Support Plan - Region/division/school -wide Report on plan implementation and results including utilization of all funds - Report on the perception of education stakeholders regarding transparency, accountability and integrity |  |
|  |  | - Increased number of effective initiatives undertaken by the region/division/schools to improve Access | - Report on the "access" initiatives (includes acceptability by stakeholders, replicability, results against indicators and sustainability of actions) |  |
|  |  | - Increased number of educational leaders utilizing management practices supportive of SBM | - Report on Assessment of education leadership and management practices. |  |
| Output 1.1 | Enhance Educ. Policy & planning system | - Regional policy and planning framework developed | - Baseline report on status of planning in the region; Regional policy & planning framework document; Expression of acceptance by the RD on the Policy and Planning framework | - Regional/Divisional leadership open to stakeholder participation in the policy and planning process; - Stakeholders willing to participate. |
|  |  | - Region/Division/School planning teams organized / mobilized | - Terms of reference of planning teams - Master list of planning teams organized / mobilized - Memorandum Order signed by RD/SDS re organization/ mobilization of the team | - Education leaders pursue and support the education development policy/planning process |
|  |  | - 3 Regional Planning Teams |  |  |
|  |  | - 3 Division Planning Teams |  |  |
|  |  | - 300 School Planning Teams |  |  |
|  |  | - Organization skills on policy and planning developed/enhanced | - Report on the enhancement of policy and planning skills |  |
|  |  | - Education Planning Technology developed/enhanced: | - Planning Guides and Educational Plans developed |  |
|  |  | - Regional Education Development Plan Technology | - REDP Manual - REDPs of Regions 6, 7 & 8 |  |
|  |  | - Enhanced Division Education Development Planning Technology | - Enhanced DEDP Manual - DEDPs of Bohol, Tagbilaran City, Northern Samar, Negros Occidental |  |
|  |  | - SIP-AIP Adjustment Technology | - 100 SIPs (Negros Occidental) - SIP-AIP Adjustment Guide - 300 Adjusted AIPs |  |
|  |  | - Planning related policies formulated and recommended | - Copy of planning-related policies formulated and recommended |  |

| Output 1.2 | Education Governance : Strengthen Participatory mechanisms for educational governance | - Participatory educational governance framework developed | - Baseline report on existing regional and local participatory mechanisms, including quality of participation - Expression of acceptance by the RD/SDS of the participatory educational governance framework | - DepED and stakeholders willing to work together to improve basic education services |
| --- | --- | --- | --- | --- |
|  |  | - Regional and local participatory mechanisms in educational governance improved | - Report on the mechanisms improved including the improvement process |  |
|  |  | - Developed recommendations on improving Participatory mechanisms for Education Governance | - Report containing recommendations for improving participatory mechanisms in education governance |  |
|  |  | - Innovation Fund utilized and managed | - Innovation Fund Operations Manual - Project Proposals - Proposal evaluation report of review committee - Letters of award - Progress monitoring reports - Project completion reports |  |
| Output 1.3 | Enhance Human Resource Management system* | - Proposed Regional Human Resource Management Framework* developed | - Draft Conceptual Framework on Human Resource Management duly endorsed to DepED Regional officials | - Allocation of human resources to implement the systems in the Region & Division - Policy and clear guidelines to implement the systems |
|  |  | - Proposed Regional Organization Structure & Functions developed for Pilot | - List of functions of the Region based on RA 9155 - DepED Order on Guidelines for Regional Restructuring - Proposed Framework For Re-Structuring the Regions and Divisions Of DepED |  |
|  |  | - Recommendations on the Regional Organizational Structure & Functions developed | - Report on the Pilot Results of the Regional Restructuring |  |
|  |  | - Division Technical Assistance Team organized in Negros Occidental; Bohol and Tagbilaran City; and Northern Samar | - List of organized Technical Assistance teams per Division | - Divisions recognize the need or importance of organizing Technical Assistance Teams to provide support to schools - Region and Division Managers supports the implementation of the mechanism in their respective area of governance |
|  |  | - Technical Assistance Mechanism for the Region and Division established | - Document on Technical Assistance Mechanism for the Divisions duly endorsed by the Region and Division Managers |  |
|  |  | - Regional staff of Regions 6, 7 & 8 trained on key functions such as, but not limited to:. | - Training Program Designs - Training Completion Reports |  |
|  |  | - General Competencies for regions |  |  |
|  |  | - Policy Formulation And Standard Setting |  |  |
| Output 1.4 | Quality assurance & accountability system | - Regional QAAS framework enhanced | - Technical paper on the QAA System’s framework | - All players and stakeholders recognize the need for a set of minimum standards to guide future action. - There is strong consensus among educators on what quality education is. - DepED's willingness to reorganize and designate staff to run the QAAS. - Desire and willingness of the divisions and regions to receive feedback on schools' progress. |
|  |  | - QAA mechanisms for education planning, implementation and evaluation established | - Report on more than 50% of schools with SIPs implemented in target divisions with their annual plans reviewed and adjusted for another year of implementation |  |
|  |  | - Implementation system for Quality Assurance and Accountability (QAA) established | - QAAS Implementation Handbook |  |
|  |  | - QAA teams organized at school, division and regional levels: | - Regional / division memoranda designating the members of the Quality assurance teams/units. - M&E Reports submitted by organized Quality Management Teams from at least 50% of target schools, 3 pilot divisions & regions. |  |
|  |  | - Regions 6, 7 and 8 |  |  |
|  |  | - Divisions of Negros Occidental; Bohol and Tagbilaran City; and Northern Samar |  |  |
|  |  | - 300 schools |  |  |
|  |  | - Recommendations for QAAS implementation developed | - Report containing recommendations for implementation of QAAS generated from the pilot submitted to the CO& RO |  |
| Output 1.5 | SBM M&E System | - Regional M&E framework developed | - Handbook on Regional SBM M&E framework. | - Recognition of the need to monitor the progress of schools, division and region to achieve the desired levels of student outcomes and school performance. - Commitment of the trained personnel to manage the system. |
|  |  | - Coordinated Region and Division M&E teams organized | - Regional memorandum issued by RO designating the members of the M & E teams for the region and the pilot division. |  |
|  |  | - SBM M&E System established at the region/division/schools | - Operations Handbook of SBM M & E System |  |
|  |  | - Organizational M&E skills enhanced | - Report on at least 50% of target schools, three pilot divisions and regions with staff trained on M&E skills. |  |
| Output 1.6 | - Program to improve access | - Framework to Improve Access established | - Master list of members duly recognized by management - Memorandum/Letter of Appointment of the Regional and Division Access Teams - Terms of Reference defined and accepted | - Stakeholders of disadvantaged/ challenged schools recognize the need to address access issues or problems and are willing to act on those issues. - Appropriate commitment of the DepED personnel (region, division, schools) sustained. |
|  |  | - Access Team organized, engaged and strengthened |  |  |
|  |  | - 3 Regional Access Teams |  |  |
|  |  | - 3 Division Access Teams |  |  |
|  |  | - System for planning and managing access programs established | - Manual for Planning, Implementation, and Evaluation of Programs to Improve Access - Improved SOBE Fund Operation Manual |  |
|  |  | - Capacities of 46 target schools on planning, implementation and evaluating access programs enhanced | - Rapid assessment report on the current capacity of the target schools on planning, implementation and evaluation of programs to improve access - Reports on the implementation and evaluation of programs to improve access - Report on the access related performance indicators of the target schools (i.e. Drop-out rate, Completion rate, Cohort survival, Enrolment rate) |  |
| Output 1.7 | Enhance the Regional Unified Information System | - UIS Architecture for the region developed | - ICT Workplan - UIS Functional & Technical Architecture - School Information System Functional & Technical Design - Enhanced BEIS Functional & Technical Design - LRMDS Functional & Technical Design - T&D Information System Functional & Technical Design | - DepED Management supports the UIS Architectural design. - Functions of Region and Division ICT Coordinators in terms of supporting the implementation of the ICT protocols and standards are recognized. - Consistent support of Regions 6, 7 and 8 in the establishment and continuing maintenance of the ICT technology infrastructure - Funds are allocated for the procurement of ICT equipment and recurring costs of services |
|  |  | - ICT Protocols & Standards identified | - ICT Protocols and Standards Document endorsed by Regions and Divisions |  |
|  |  | - Regional UIS established | - Documentation of the Enhanced BEIS - Documentation of the LRMDS Portal which includes installation and testing - Documentation of the T&D Information System which includes installation and testing |  |
|  |  | - ICT Support Infrastructure for Regional UIS installed in Regions 6, 7 and 8 | - Documentation report on the installation of the UIS server infrastructure established in Region 7, which includes specifications per ICT Functional and Technical Design - Documentation report on the installation of the LRMDS ICT infrastructure in Regions 6 and 8, which includes specifications per ICT Functional & Technical Design |  |
|  |  | - Competencies of region and division personnel on the Regional UIS are aligned with the requirements of SBM, T&D & LRMDS. | - Capability Building Program on UIS competencies - List of competencies required by SBM, T&D and LRMDS - Regional UIS Pilot Implementation Monitoring and Evaluation Reports |  |
|  |  | - Recommendations for UIS developed | - Regional UIS Monitoring & Evaluation Reports - Regional UIS Pilot Implementation Report |  |

COMPONENT 2:  HUMAN RESOURCE DEVELOPMENT (IN-SERVICE EDUCATION AND TRAINING - INSET) SYSTEM

| CODE | NARRATIVE DESCRIPTION | VERIFIABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
| Objective: | Development of a Regional Training and Development system for quality professional development of teachers and educational leaders. | - Increased percentage of schools in the pilot divisions using the National Competency-Based Teacher Standards (NCBTS) to determine teacher / learning facilitators’ development needs and priorities | - Division report on the use of NCBTS in schools to determine development needs and priorities | - Appropriate and adequate budgetary support for Training and Development , including allocation of human resource to implement T&D systems - Clear policy and guidelines in the implementation of T&D are available - Regional personnel can coordinate training and development activities and work effectively with various agencies for the professional development activities - There are specialists in the DepED available as trainers - Available training and development modules can be adopted for use in these Regions (e.g. BEAM modules, NEAP materials) |
|  |  | - Increased percentage of School Heads in the pilot divisions using the Training Development Needs Assessment to determine development needs and priorities | - Division report on the use of TDNASH by School Heads to determine development needs and priorities |  |
|  |  | - Increased percentage of Regional and Division managers and trainers supporting provision of opportunities for continuous professional development of teachers and educational leaders | - Regional and Division report of Training and Development managers, trainers, trained educational leaders and teachers |  |
|  |  | - Increased percentage of trained teachers applying NCBTS competencies | - Report on teaching and learning practices |  |
| Output 2.1 | A Training & Development System Framework | - Supplementary baseline on the provision of professional development opportunities for teachers and education managers established | - Baseline Study Report for T&D | - RO & DOs assign personnel with the required basic skills to manage the system in the future - Trained staffs are the ones who are actually designated to run the system. - Regional personnel can coordinate training and development activities and work effectively with various agencies for the professional development activities |
|  |  | - Framework for Training & Development System and its sub-systems developed | - Training and Development System Framework that includes: enabling policies, structure, system designs and management functions, standards for professional, procedures/ processes, support infrastructure (Volume 1) |  |
|  |  | - Enhanced Organizational competencies of key regional (15) and division (15) staff on managing Training & Development for teachers and educational leaders | - Competency development program for the T&D personnel in relation to the Training & Development TOR |  |
|  |  | - 15 Regional staff across the 3 STRIVE regions | - Training Completion and Post-training Reports on Regional Training & Development Competency Development programs |  |
|  |  | - 15 Divisions staff across the 3 STRIVE pilot divisions | - Training Completion and Post-training Reports on Divisional Training & Development Competency Development programs |  |
|  |  | - Recommendations for the T&D implementation developed | - Regional and Division T&D implementation plans |  |
| Output 2.2 | Establish the Training Development Needs Analysis (TDNA) System for Teachers and Educational Leaders | - Processes for training and development needs analysis (TDNA) established/enhanced | - Operations Manual for the TDNA System (Volume 2) containing framework, structure, roles and responsibilities, system design, standards, procedures/ processes, tools and M&E mechanism | - High degree of commitment to use the TDNA tools and use of the results |
|  |  | - TDNA tools developed for Teachers and School Heads |  |  |
|  |  | - Self assessment TDNA instrument for teachers | - NCBTS-TSNA Orientation Package containing Guide, Manual and Tools |  |
|  |  | - Self assessment training strengths and needs analysis tool for school heads | - Manual and Tools for the TDNASH |  |
|  |  | - Organizational TDNA tools for the Region | - Manual and Tools for the Organizational TDNA for the Region |  |
|  |  | - Organizational TDNA tools for the Division. | - Manual and Tools for the Organizational TDNA for the Division |  |
|  |  | - Key regional (15) and division (15) staff obtained competencies on TDNA | - Summary Report of TDNA Implementers |  |
| Output 2.3 | Strengthen the Professional Development and Training System (Professional Development Planning, Program Designing and Resource Development, and Program Delivery) | - Processes for T&D planning, designing and resource development enhanced | - Operations Manuals for Planning System (volume 3) and for Program Designing and Resource Development (Volume 4), containing framework, structure, roles and responsibilities, system design, standards, procedures/ processes, templates/tools and M&E mechanism | - There are existing training models which are accessible for use. - Available training and development modules can be adopted for use in these Regions (e.g. BEAM modules, NEAP materials) |
|  |  | - Professional Development plans, designs and resource packages developed for selected priority professional development needs (per TDNA results) | - Samples of IPPD, SPPD, Division MPPD, Regional MPPD - Samples of Program designs for teachers, school heads, educational leaders at the division and regional levels. - Samples of Professional Development Resource Packages - Report on Pilot of T&D Planning, Designing and Resource Development |  |
|  |  | - Standards and processes for Training of Trainers identified | - Operations Manual for Program Delivery (Volume 5) containing standards for training, processes and M&E mechanism and tools |  |
|  |  | - Professional Development Delivery models for regional, divisional and school based programs in prioritized professional development areas applied | - Reports on pilot of Sample PD models delivered |  |
|  |  | - 3x25 region/division staff across the three regions | - Capability Program on T&D and Activity Report –Regional Level |  |
|  |  | - 60 Division Education leaders | - Professional Development Program for Div. Education Leaders and Activity Report –Div. Education Leaders |  |
|  |  | - 108 School Heads | - Professional Development Program for School Heads and Activity Report –School Heads |  |
|  |  | - 40 teacher- trainers - 360 teachers | - Professional Development Program and Activity Reports –Teachers |  |
|  |  | - Post-training technical assistance mechanism established | - Post-training Handbook and Report on its utilization |  |
|  |  | - Key regional (15) and division (15) staff obtained competencies on Professional Development Planning, Program Designing and Resource Development, and Program Delivery | - Summary Report on Pilot and Evaluation of Competencies of Implementers of the Professional Development Planning, Program Designing &Resource Development, and Program Delivery |  |
| Output 2.4 | Strengthen the Training & Development Monitoring & Evaluation Scheme | - T&D M&E framework developed | - M&E framework - M&E section in each of the T&D Operations Manual | - Degree of commitment, and use of, framework and M and E instruments |
|  |  | - T&D M&E instruments developed | - M&E Tools for each of the subsystems |  |
|  |  | - T&D M&E processes and reporting mechanism installed | - Report on utilization of M&E Instruments for Training & Development sub-systems |  |
|  |  | - Key regional (15) and division (15) staff obtained competencies on Monitoring & Evaluation of professional development programs | - Summary Report on Pilot and Evaluation of Competencies of Implementers of the M&E component of each subsystem |  |
| Output 2.5 | Establish the support infrastructure for quality Training & Development at the Region | - Architectural plans and program of work for civil works in Region 6, 7 and 8 | - Physical Facilities refurbishment plan based on approved Specs and Standards | - The building/properties of the RELC can be constructed/refurbished without legal impediments. - Funds are allocated for the recurring costs for T&D Center services |
|  |  | - TDC equipment and furniture delivered in Region 6, 7 and 8 | - Relevant documents, e.g. receipts, purchase order, canvass results, contracts, contracts, acceptance certificate on deliveries equipment/software |  |
|  |  | - Construction of TDC for Region 6 | - Turn-over documents of TDC for Region 6 |  |
|  |  | - Refurbished facility for Region 7 TDC | - Turn-over documents of TDC for Region 7 |  |
|  |  | - Construction of TDC for Region 8 | - Turn-over documents of TDC for Region 8 |  |

COMPONENT 3:  LEARNING RESOURCES MATERIALS DEVELOPMENT SYSTEM

| CODE | NARRATIVE DESCRIPTION | VERIFIABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
| Objective: | Develop the LRMDS to provide access to quality teaching and learning resources. | - Improved alignment of learning resource materials provided to teachers and students to identified requirements or needs. | - Analysis report on the matching of needs with available /provided learning resource materials | - Appropriate financial support for LRMDS, including allocation of human resource to implement the systems - Clear policy and guidelines in the provision of and access to LRM available - A desire and willingness exists among key stakeholders to develop closer partnerships as a strategy to improve access to quality learning resources |
|  |  | - Increased/widened the range of instructional resources available to teachers and students following set standards and specs. | - Inventory of types of instructional resources available/developed |  |
|  |  | - Increased/widened the participation of internal stakeholders in the operation of the LRMDS. | - Report on the contributions of internal stakeholders in the operation and maintenance of the LRMDS |  |
|  |  | - Increased access to instructional materials other than textbooks | - Analysis Report on the use of LRM in instructional settings |  |
| Output 3.1 | Develop the Framework for Learning Resource Materials Development System (LRMDS) | - Supplementary baseline on provision of and access to a variety of learning resource materials established | - Final Baseline report (Stage II) | - Role of LRMs in the entire reform program (BESRA) is CLEAR - Data or information needed is accessible to researchers as required by baseline studies. |
|  |  | - Standards and specifications of LRMD established | - LRMDS Assessment and Evaluation Guidelines, LRMDS Development and Production Guidelines, Storage and Maintenance Guidelines |  |
|  |  | - LRMD Framework | - LRMD Framework documents - Documentation on the presentation and comments/recommendations made on the Framework Plan |  |
|  |  | - Policy Review and Recommendations | - Document: Policy Report (for the NLS) - Policy recommendations in the Baseline Report s (Stages I and II) |  |
| Output 3.2 | Enhance LR Assessment and Evaluation System | - LR Assessment and Evaluation (A&E) System Design | - Documents: LRMDS Assessment and Evaluation Guidelines | - DepED’s commitment to provide the personnel for the enhancement and pilot implementation of the LT A&E System |
|  |  | - LRMD A & E criteria, guidelines and tools for assessing and evaluating LR developed | - Tools, Instruments for LRMDS Evaluation |  |
|  |  | - Inventory & catalogue of LRS completed | - Inventory report - Documentation on metadata schema used |  |
|  |  | - LRMD A & E System installed | - LRMD A & E Syst. Conformance report - Documentation on conformance testing; recommendations |  |
| Output 3.3 | Enhance LRMD development and production system developed | - Design for LRM Development & Production System established | - Document: LRMD DEVELOPMENT AND PRODUCTION SYSTEM guidelines | - Curriculum officials of Bureaus at various levels participate in the identification of priority LR needs - Central Office is supportive of the reform agenda and the requirements of pilot implementation in the Visayas Regions, Divisions and Cluster/Lead schools |
|  |  | - Tools for LRM Development and Production System developed | - Tools, templates, instruments for developing and producing LRs |  |
|  |  | - Sample set of LRs developed |  |  |
|  |  | - Sample set of digitised LRs developed | - Prototypes of existing LRs digitized (according to specs, requirements and identified priorities) (minimum of 10 across pilot regions and divisions) - Prototype LRs included in the inventory /clearinghouse |  |
|  |  | - Sample set LRs re-developed | - Prototypes of existing LRs in priority subject areas redeveloped (according to specs, requirements and identified priorities) (at least 15 across regions and divisions - Prototype re-developed LRs included in the inventory /clearinghouse |  |
|  |  | - LRM development and production system installed | - LRM Development and Production System Conformance report - Documentation on conformance testing; recommendations |  |
| Output 3.4 | Establish System for Storing and Distribution | - Design for storing/distribution system established | - Document: LRMD Storing and Distribution System Guidelines |  |
|  |  | - Tools for storing/distribution developed | - Tools, templates, instruments |  |
|  |  | - System for Storing and Distribution installed | - LRMD Storing and Distribution System Conformance report - Documentation on conformance testing; recommendations |  |
| Output 3.5 | Install LRMDS Organization and management Plan | - Organizational competencies for LRMDS identified | - Document: LRMDS FRAMEWORK describing organizational structure | - Regional DepED commitment to reorganization and regional/ division willingness to hire/designate required personnel exist |
|  |  | - LRMDS job functions and competencies identified | - Documents: Job descriptions and listing of competencies/per function |  |
|  |  | - Management & Maintenance plan developed | - Management and Maintenance Plans (Regions and divisions) - Regional/division strategic and implementation plans |  |
|  |  | - LRMD skills of key personnel developed | - Training design, program, copies of handouts and other resources - ACR report of training including evaluation of training - Attendance reports | - Region directors and SDS have designated/appointed the minimum personnel for the LRCS based on proposed qualifications and allowed them ADEQUATE time to be trained |
|  |  | - 30 Regional Staff trained across 3 STRIVE regions trained on the LRMDS and their specific functions in the LRC |  |  |
|  |  | - 162 field personnel trained on the system |  |  |
|  |  | - 56 School heads trained on LRMDS, with focus on LR planning |  |  |
|  |  | - 56 teachers trained on LRMDS, with focus on LR planning |  |  |
| Output 3.6 | Establish the support infrastructure for LRMDS | - Architectural plans and program of work for civil works in Region 6, 7 and 8 | - Documents: copies of architectural plans - LRMDS region/division strategic and implementation plans | - SPHERE delivers the construction/ refurbishment of infrastructure and the provision of base level furnishings in the regional and division LRCS on time for STRIVE to complete the LR ICT infrastructure. - Funds are allocated for the recurring costs for T&D Center services |
|  |  | - LRMC equipment, software and furniture delivered in Region 6, 7 and 8 | - List of equipment software and furniture received by regions and divisions matched against base level requirements - List of base level equipment, furnishings in the LRMDS framework - Certificate of acceptance |  |
|  |  | - LRC Region 6 construction | - Certificate of turnover and acceptance |  |
|  |  | - Region 7 LRC refurbished | - Certificate of turnover and acceptance |  |
|  |  | - Region 8 LRC constructed | - Certificate of turnover and acceptance |  |
|  |  | - Bohol Tagbilaran LRC constructed | - Certificate of turnover and acceptance |  |
|  |  | - Negros Occidental LRC constructed | - Certificate of turnover and acceptance |  |
|  |  | - Northern Samar LRC constructed | - Certificate of turnover and acceptance |  |
| Output 3.7 | Establish QA & M & E Plan for LRMDS | - Quality Assurance Framework for LRMDS established | - Document: Quality Assurance Plan - Sample quality Assurance Reports |  |
|  |  | - Quality Assurance tools developed | - Tools, Instruments for QA |  |

COMPONENT 4:  PROJECT MANAGEMENT

| CODE | NARRATIVE DESCRIPTION | VERIFIABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
| Objective: | Manage the Project in an effective, efficient and responsive manner | Project implemented on time and within budget | - Project reports | - DepED remains committed & provides appropriate counterpart resources & support at national, regional and division levels |
| Output 4.1 | Planning system & operationalization | - Developed the Management Systems Framework | - Documentation of project meetings/workshops regarding the development or validation of the Project Operations Manual - Annual Implementation Plan containing Project Management Framework and Implementation Structure - Project Operations Manual | - DepED fully cooperate & actively participate as the lead agency in project management & implementation. |
|  |  | - Finalized Project Annual Plans (Implementation Plans) based on documented and approved adjustment parameters | - Documentation of project meetings/workshops regarding the development and validation of the Project Annual Plans with WFP Adjustments - Three (3) Annual Plans containing the Annual Project Implementation & Financial Plan based on adjustments parameters |  |
|  |  | - Developed the Risk Management Plan | - Documentation of project meetings/workshops regarding the development, validation and adjustment of the Risk Management Plan - Risk Management Plan and adjusted plans. |  |
| Output 4.2 | Coordination & Communications System & operations | - Project Teams & Committees organized | - Terms of reference of the committee - Function and duties of the committee members - Guidelines on the selection of committee members - Documentation on the selection of the members for the Project Management Committee |  |
|  |  | - Conducted regular Regional Implementation Coordination meetings (for project implementation) | - Minutes of Regional Implementation Coordination meetings and dissemination of document to stakeholders |  |
|  |  | - Conducted regular Management Coordination meetings (for Project Integration) | - Minutes of Management Coordination meetings and dissemination of document to stakeholders |  |
|  |  | - Conducted Senior Management Guidance meetings (Costing c/o joint MEA for RPCs only) | - Minutes of Senior Management Guidance meetings and dissemination of document to stakeholders |  |
|  |  | - Conducted regular semi-annual Oversight Management Meetings | - Minutes of Oversight Management meetings and dissemination of document to stakeholders |  |
|  |  | - Developed, implemented and monitored Advocacy and Communications Plan | - Inspection of Advocacy & Communications Plan - Documentation on Orientation of RO & DO on content/design of Stage 2 & its relation to BESRA - Documentation on Project Launching in three (3) Regions - Proceedings on Education Forum - Inspection of contribution to DepED website and Press Releases - Dissemination of the advocacy materials to AusAID & regular/local media |  |
| Output 4.3 | Human Resource development | - Conducted Training and Development on Project Management | - Documentation of workshops re: different capability building programs - Inspection of Training Completion Reports | - Extensive resource generation for incentives, rewards and recognition |
|  |  | - Developed and implemented System of Incentives, Rewards, & Recognition (SIRR) | - Documentation of consultations re: SIRR - Inspection of SIRR guidelines, instruments, personnel, enabling documents - Inspection of documentation on recommendations and incentives, rewards & recognition given |  |
|  |  | - Finalized Safety and Security Plan based on approved adjustment parameters | - Inspection of SSP - Documentation of dissemination and orientation on SSP |  |
|  |  | - Un-Programmed Capability Building Programs | - Documentation of workshops re: different capability building programs - Inspection of Training Completion Reports |  |
| Output 4.4 | Financial System & operations | - Financial Operations Manual | - Finance Operations Manual |  |
|  |  | - Financial Reports | - Inspection of Financial Reports - Transmittal letters re: submitted financial reports |  |
| Output 4.5 | Monitoring & Evaluation system | - M & E framework developed | - Expression of acceptance by AusAID and DepED (all levels incl. pilot schools) - Document on the M & E framework - Inspection of finalized M & E framework by DepED - Documentation of validation meetings/workshops in the development of the M & E framework | - DepED provides guidelines & directions in the establishment of the M & E system. - DepED's personnel willing and competent to operate the M & E system - DepED has both the resources & the will to meet any recurrent costs to maintain the project benefits. - Internal & external mechanisms used to verify quality of outcomes & milestones - Approval & implementation of DepED's ICT Master Plan & Enterprise Architecture Plan |
|  |  | - Developed and piloted effective and sustainable PROGRESS M&E Processes & Tools Quid | - Documentation of project validation meetings/workshops on M & E processes, tools and reporting system developed - Inspection that M & E guidelines, instruments, structures (physical, equipment & organizational) and organizational competence are in place - M & E reports from the Regional and Division level |  |
|  |  | - Developed comprehensive and doable/user-friendly M & E Operations guidelines | - Documentation of validation meetings/workshops on the M & E Operations Guidelines - M & E Operations Guidelines - Inspection of M & E Operations Guidelines |  |
|  |  | - Developed a Sustainability plan that is comprehensive and anchored on BESRA indicators | - Inspection of the Sustainability Plan - Report /documentation of implementation strategies that applied the sustainability measures |  |
| Output 4.6 | M&E reports // operational M&E System | - Submitted timely and relevant input/output M & E reports (a.k.a. Progress M&E Reports) | - Report to Stakeholders - Received copy of transmittal letter re: submission of M & E reports | - Transparency among the stakeholders and implementers |
|  |  | - Submitted timely & relevant Milestone Reports | - Final report to AusAID, DepED - Received copy of transmittal letter of Milestone submissions |  |
|  |  | - Submitted timely Intermediate Results Reports | - Minutes of validation meetings/workshops on the development of IR Reports - Final report on intermediate results to concerned stakeholders (AusAID, DepED, others) - Received copy of transmittal letter re: submission of M & E reports |  |
|  |  | - Submitted Project Completion Report (PCR) | - Minutes of validation meetings/workshops on the development of PCR - Received copy of transmittal letter re: submission of PCR |  |
| Output 4.7 | Project Administration | - Established Project Management Units (PMUs) / offices | - Relevant documents, e.g., receipts, physical facilities plans, inspection reports on the refurbishment/construction of offices |  |
|  |  | - Office Operations and Administration |  |  |